## Slide 1: Element 3 Space Data Support to GFOI R&D
A. Rosenqvist, S. Yabe-Ogawa
SDCG-11 Session #3

## Slide 2: Session 3 outline

## Slide 3: Status Overview of 3-Year Work Plan Tasks and Outcomes

## Slide 4
3-Year Work Plan

## Slide 5
2017 Status: On schedule.
El-3 v2.0 endorsed by SIT-31
V 2.2 update completed prior to CEOS Plenary, Oct 2016.
V3.0 in the pipeline for SIT-32 (to be sumbitted “for info”). SDCG agencies asked to review the sections related to their missions.
3-Year Work Plan

## Slide 6
2017 Status: On schedule & good progress
  All SDCG agencies have completed selection of R&D teams to support
  All agencies have begun tasking and/or data provision to the selected teams
  (agency reporting next agenda item)
3-Year Work Plan

## Slide 7
2017 Status: On schedule
Private sector engagement
  AD&S (SPOT 6/7) – confirmed support but details pending (to be reported by CNES)
  Planet (RapidEye + Doves) – TBC
  SSLT (NovaSAR) – Support confirmed by SSTL in March 2017. NovaSAR launch foreseen in June 2017 and data provision ~6 months later
3-Year Work Plan

## Slide 8: El- 3 document (v3) update

## Slide 9
Revision to reflect
Updates to the agency data provision status (section 4)
  All agencies to review and revise as required
  Updates due by April 18 in order to make it into the SIT-32 version
Updates to the R&D group info (Annex A)
(Minor) updates to group data requests
  Group 14 (WUR, NL) – change of study site
  Group 7 (Tromsø U, Norway) – change of TSX request
  Group 15 (ADS, Germany) – change of study site
  Group 16 (CSIR, South Africa) – requests for additional data (Pléiades, Radarsat-2, TanDEM-X)
Element-3 doc revision

## Slide 10
Version 2.1 (SDCG-10, Sept 2016)
Element-3 doc revision

## Slide 11
Revision 3.0 (April 2017)
Element-3 doc revision

## Slide 12: GFOI R&D Coordination and R&D Programme

## Slide 13
GFOI R&D Study Sites & R&D teams
Currently 18 R&D teams from GFOI countries and national and int’l research organisations
Currently 32 multi-disciplinary sites, addressing multiple GFOI Priority R&D topics
Including Study Sites in former GEO-FCT National Demonstrator countries
GFOI R&D Programme
GFOI R&D Study Site interactive map at
http://www.gfoi.org/rd/study-sites/

## Slide 14
Detailed Study Site info
Interactive map at http://www.gfoi.org/rd/study-sites/
GFOI R&D Programme

## Slide 15
Example: Sensor interoperability: L- and C-band complementarity
GFOI R&D Programme
Courtesy of Dirk Hoekman, Wageningen Univ (Group 6)

## Slide 16
Technical Progress report 2017
Released March 31, 2017
Progress reports by all 18 R&D groups
  Research progress
  Data access summary
Available at GFOI.org/RD
GFOI R&D Programme
Notes: ESA BIOMASS mission,

## Slide 17
Joint SDCG – R&D Coordination session tomorrow:
GFOI R&D Coordination
Notes: ESA BIOMASS mission,