## Sheet1
The following table is mapping the recommendations made in the GHG white paper to the various CEOS and CGMS bodies that are needed to establish the operational monitoring system
| Recommendation | Lead/Coordinator | Support | Comment | Resource needs
1 | A prototype system, based on available space-based and ground-based atmospheric measurement assets and modelling capabilities, should be designed and implemented in time to inform the first global stocktake in 2023. To support this stocktake, the initial global atmospheric CO2 and CH4 flux products must be available by 2021. | WGClimate | AC/VC, WGCV, GSICS, WGISS | This recommendation is understood as a statement of two major programmatic assumptions that determine the work outlined in the roadmap mentioned in Rec #3. | None
2 | The initial operational system should exploit the lessons learned from the development and use of the prototype product as well as new space-based measurement and modelling capabilities to produce space-based CO2 and CH4 flux products in time to support the second global stocktake in 2028. | WGClimate | AC/VC, WGCV, GSICS, WGISS, WCAPD, CGMS WG-II,III, and IV | This recommendation is understood as a statement of two major programmatic assumptions that determine the work outlined in the roadmap mentioned in Rec #3.
3 | To meet these goals within a decade, it is imperative that individual research and operational space agencies work within CEOS, CGMS and other international coordination bodies (i.e. WMO IG3IS, GCOS, GEO-C) to define a roadmap with specific programmatic milestones for developing virtual and then dedicated constellations that can deliver harmonized, space-based climate data records for CO2 and CH4. | WGClimate | AC/VC, WGCV, GSICS, WGISS, WCAPD, CGMS WG-II,III, and IV | This should actually be the first thing to be addressed to develop individual areas/tasks for the coodination bodies in CEOS and CGMS. CGMS has a portfolio of task forces that could also contribute to the roadmap, e.g., user preparedness, VlaB, meta data, etc. | WGClimate needs a specific Carbon Coordinator that can devot time being the book caption of the roadmap and monitors the implementation.
4 | The preparation of this report has demonstrated the benefits of the complementary viewpoints provided by CEOS and CGMS for advancing the implementation of system that incorporates both research and operational elements within the timeframe available. In particular, the CGMS partners could provide insight into the process of gathering user requirements for timeliness, reliability, traceability, reprocessing, quality assurance, and providing user support for an operational product. A continued engagement by both entities is required and some formalisation of the relationship would be advantageous. The joint CEOS/CGMS Working Group on Climate could lead this effort. | WGClimate |  | This recommendation has been followed with the inclusion of activities into the WGClimate. | None
5 | As recognised in Chapter 2, a broad system approach is required to develop a top-down atmospheric inventory approach that complements the bottom-up inventories. This system integrates the satellite observations, in situ (surface, aircraft, and balloon) measurements, modelling components (retrieval, inversion, biogeochemical processes and transport), prior information and ancillary data. | WGClimate | all relevant groups in CEOS, CGMS, etc. | To be coordinated by WGClimate. The broad system needs to be designed as spelled out in REC#16. | Resources as in REC#16.
6 | To ensure that the space agencies are working together and building the necessary partnerships with the relevant stakeholders (i.e. UNFCCC/SBSTA) to address the overall system implementation goals, they should work through CEOS and CGMS to strengthen the ties to these stakeholders. | WGClimate | all relevant groups in CEOS, CGMS, etc. | The connection is already available in WGClimate. Other groups need to support this. | This will be done by the WGClimate Chair and does not need additional resources.
7 | In Chapter 6, the GCOS requirements were adopted as the basis in the formulation of a baseline operational CO2/CH4 constellation because GCOS provides an independent basis for the requirements. However, these requirements predated the Paris Agreement, which changed the focus of CO2 and CH4 monitoring efforts to anthropogenic emissions at national scales. Further analysis and revision of the space-based measurement and analysis requirements are needed to address this new focus. The CEOS and CGMS agencies should work with GCOS and other partner organizations and stakeholders in an iterative approach to further refine those requirements over the next few years. | WGClimate | AC/VC, CGMS WGII GCOS AOPC and SG | The goal is to develop updated requriements and include them into the 2021 GCOS IP. The mechanism to achieve this is already established in WGClimate since the 2016 GOCS IP. | This is a dedicated activity and would benefit from additional resources in the WGClimate
8 | CEOS, CGMS and their partners should continue to support the necessary OSSE experiments, which remain of critical importance in further refining the detailed requirements of the space-based elements of the constellation (sensor precision, accuracy, and resolution, orbit and mission coordination). The near-term objective is to develop a prioritized list of the required OSSE experiments and end-to-end system simulations to optimize the overall system design, resolve system-level uncertainties, and facilitate the coordination of activities among the CEOS and CGMS agencies. The output from these experiments should be made available to the CEOS and CGMS Principals periodically, in a format conducive to discussions with their mission and orbit planning organizations. | WGClimate | AC/VC plus other technical groups that inherit experience in performing OSSE experiments such as Task Team on reanalysis in WCRP DAC. | It is evident that these experiments will be performed by NWP centres such as ECMWF but need to be organised by groups that share expertise on the measurements and the models to be used. This is certainly the AC/VC. The overall coordination should still lie within the WGClimate as it is intimately connected to the wider systems simulations programme. | WGClimate may not need additional resources but the OSSE experiments need to be funded by CEOS and CGMS agencies.
9 | Over the last 15 years, research missions have provided considerable insight into instrument calibration, validation and the broader aspects of uncertainty quantification and quality control. Appendix 4 of this report summarizes the lessons learned from SCIAMACHY, GOSAT, and OCO-2. In the short-term, these lessons represent best practices that should be extracted and generalised by the CEOS/CGMS Working Group on Calibration and Validation (WGCV) and the Global Space-based Intercalibration System (GSICS) so that they are available as Cal-Val strategy "protocols" for space agencies that are now considering missions. | WGCV | GSICS (CGMS WGII), AC/VC | The strategy for the constellation shall be developed by WGCV with strong involvement of CGMS bodies to ensure its operational implementation. | To perform this in acceptable time WGCV should come up with a plan how this could be done and if more resources are needed.
10 | The strategy for cross-calibrating the GOSAT and OCO-2 instruments has employed common standards, including observations of the sun, Moon, and surface vicarious calibration sites, such as Railroad Valley, Nevada, U.S.A. Additional effort by WGCV and GSICS is needed to maintain and improve the quality of these standards to better address the calibration needs of space-based CO2 and CH4 sensors. | WGCV and GSICS | AC/VC | The understanding is that the activity shall concentrate on the establishment of an operational system from the beginning. This means that WGCV shall take on all fundamental calibration items and operational sensor cross-calibration needs to be implemented by GSICS based on AC/VC experience. | Given the established interaction of WGCV and GSICS the coordination may not need additional resources but the work itself in particuar in GSICS requires investments by the contributing agencies.
11 | TCCON has provided the primary transfer standard to relate space-based XCO2 and XCH4 estimates to the ground-based in situ standards maintained by the WMO GAW network. This network must be maintained and augmented using portable, ground-based remote sensing instruments (e.g. EM27/SUN), in situ sensors on fixed-wing aircraft (commercial aircraft, such as CONTRAIL, IAGOS) and balloons (AirCore), and airborne remote sensing instruments (MAMAP, CHARM-F etc.) to provide a more robust and accurate operational validation approach. | WGCV | AC/VC | WGCV seems best suited to develop network design supported by AC/VC. | To perform this in acceptable time WGCV should come up with a plan how this could be done and if more resources are needed.
12 | CGMS and CEOS should work with their member agencies to identify and promote standards in product specification, formats, pre-processing etc. and product inter-comparisons should be routinely undertaken and supported on a sustained basis to produce seamless, interoperable datasets that can be used in the broader system implementation. | AC/VC and CGMS WGII for Level2/3 product specification; WGClimate for integrated,e.g., reanalysis outputs; WGCV for product inter-comparison. |  | Details to be contained in roadmap document from Rec#3. | Resource needs for coordination of these pieces is hard to estimate but should be attempted when establishing the roadmap.
13 | Agencies should consider a centralized (but possibly geographically distributed) repository for hosting quality-controlled CO2 and CH4 products, with internal capability for product inter-comparison. | WGISS and CGMS WG-IV | AC/VC | Details to be contained in roadmap document from Rec#3. | Resource needs for coordination of these pieces is hard to estimate but should be attempted when establishing the roadmap.
14 | The capabilities required to meet the needs of the UNFCCC and the Parties to the Convention are already at the limit of the state-of-the-art for existing, space-based measurement technology. The CEOS and CGMS agencies should therefore continue to pursue complimentary technologies for both sensors (e.g. wide swath passive CO2 and CH4 imagers, active lidar) and mission design (e.g. HEO). These development efforts should be coordinated to keep the Principals updated on additional needs and capabilities that would be useful to consider for future mission opportunities. | AC/VC | CGMS WGIII | This field needs a strong collaboration between CEOS and CGMS to enable implementation of new technology to the operational system in the future. | Normal work of AC/VC, additional resources needed.
15 | There is a significant need for systematically produced ancillary measurements. These measurements are needed both to improve the accuracy of the XCO2 and XCH4 retrievals (i.e. coincident observations of clouds and aerosols) and to facilitate their interpretation within the context of the anthropogenic and natural carbon cycle (i.e. SIF, NO2 and CO). Here, the proposed atmospheric CO2 and CH4 monitoring system could substantially benefit from the full scope of carbon cycle observations included in the CEOS Carbon Strategy. The CEOS partner agencies should therefore continue to support that strategy. The coordination mechanism identified to address follow-up to the current work should provide an assessment of prioritized products to be addressed in a coherent way, across agencies, to ensure seamless input to the system. | WGClimate | All groups involved in the implementation of the CEOS Carbon Strategy. | The new governance approach foresees that the home of the Carbon Strategy will be the WGClimate. The distributed character of the actions of that strategy will remain in the future as this is expert driven. In terms of ancillary measurements the WGClimate ECV Inventory shall provide via its gap analysis a description of the situation and derive coordinated CEOS/CGMS Actions that will also be distributed. One could also think of integrating the currently open Carbon Actions into the WGClimate Coordinated Action Plan. | The above mentioned Carbon Coordinator within the WGClimate needs to be equipped to perform this coordination. WGClimate means for gap analysis might be sufficient depending on other "urgent" requests for gap analysis.
16 | To ensure that the initial operational constellation and associated atmospheric CO2 and CH4 monitoring system can meet the sustained operational needs, a system engineering effort should be undertaken early in the implementation. This effort is needed to ensure that the requirement-reliability-traceability-fitness-for-purpose cycle is adequately planned and that the user uptake, user support and training and capability building elements are defined and prototyped. The CEOS and CGMS agencies and their partners at WMO have the necessary competences to start addressing these requirements and can help to assess the scope of these activities at the different levels of the implementation. | WGClimate | All relevant groups as for the establishment of the roadmap | This activity is an essential activity to arrive at a reliable roadmap for establishing the operational systemn. It should be coordinated by the WGClimate to as it is cross-cutting through CEOS and CGMS also including the user side (stakeholders such as UNFCCC) and other supporting organisations as WMO. | This activity directly supports the establishment of the roadmap and needs additional resources that should be allocated with the Carbon Coordinator.