## WGISS-32 Actions
Actions from WGISS-33 Last updated April 30, 2012 by Michelle Piepgrass, WGISS Secretariat
Action Number | Action Description | Actionee | Due Date | Status | Comments
WGISS-33-1 | Andrew Mitchell to investigate how WGISS can support QA4EO. | Andrew Mitchell | 2012-06-30 | Open
WGISS-33-2 | Brian Killough to work with the CEOS IDN to map CEOS MIM nomenclature to the IDN set of keywords for data queries. | Brian Killough, Andrew Mitchell | 2012-07-01 | Open
WGISS-33-3 | Ivan Petiteville and Andrew Mitchell to provide Brian Killough (SEO) with DATA-CORE information. | Ivan Petiteville, Andrew Mitchell | 2012-05-31 | Open
WGISS-33-4 | Brian Killough (SEO) to find the specific FY datasets issues in the DIF and send the information to Lei Feng and Chaoliang Wang. | Brian Killough | 2012-05-31 | Open
WGISS-33-5 | Steven Hosford to present the VC portal proposal concept to the CEOS-SEC for approval after further engagement with WGISS. | Steven Hosford | 2012-06-07 | Open
WGISS-33-6 | Satoko Miura to check with Liping Di and Lorant Czaran about their ISO/TC211 involvement. | Satoko Miura | 2012-05-31 | Open
WGISS-33-7 | Liu Chuang to send to WGISS-All and to WISP the link of the English version of the Digital GEO Museum. | Liu Chuang | 2012-05-31 | Open
WGISS-33-8 | Lola Olsen and the IDN to engage with the WG Climate with regard to the Climate Diagnostics Portal. | Lola Olsen, Andrew Mitchell | WGISS-34 | Open
WGISS-33-9 | WGISS members to provide feedback to GA.4.Disasters regarding case studies; Karen Moe will request this formally. | WGISS-All | 2012-05-31 | Open
WGISS-33-10 | Kerry Sawyer to send Wyn Cudlip information on WGCapD on the SRTM DEM | Kerry Sawyer | 2012-05-31 | Open
WGISS-33-11 | WGISS members to communicate with John Faundeen, an LSI co-chair, on the merits of hosting (by the LSI) a "Post 2020 Terrestrial Mission Planning Workshop" with the goal to truly coordinate CEOS future space missions. | WGISS-All | 2012-06-01 | Open
WGISS-33-12 | John Faundeen to provide a data logger to UKSA and NRSCC. | John Faundeen | 2012-05-31 | Open
WGISS-33-13 | Karen Moe to document lessons learned on sensor web activities. | Karen Moe | WGISS-34 | Open
WGISS-33-14 | Richard Moreno to send to the CWIC email distribution list, a list of European satellite data that can be searched and accessed by the public, along with information about how the data can be searched and accessed (e.g. which GCI component, HMA, etc.) | Richard Moreno | 2012-06-15 | Open
WGISS-33-15 | Andrew Mitchell to send the URL of the NASA ISO 19115 wiki to WGISS-All. | Andrew Mitchell | June Exec teleconference | Open
WGISS-33-16 | Michael Burnett to determine and communicate the status of CSW OpenSearch related to OGC profile. | Michael Burnett | 2012-05-31 | Open
WGISS-33-17 | WISP to reconfigure the WGISS website, including finding and posting the repository for historical documents of WGISS. | WISP, Secretariat | WGISS-34 | Open
WGISS-33-18 | WGISS members to discuss technical topics for WGISS-34 with interest group and project leads. | WGISS-All | 2012-05-31 | Open
WGISS-33-19 | Martin Yapur to seek a point of contact with WMO and WIS. | Martin Yapur | June Exec teleconference | Open
WGISS-33-20 | Andrew Mitchell to develop a profile for the Technology Exploration group and send to WGISS-all for review. | Andrew Mitchell | 2012-06-30 | Open
WGISS-33-21 | Andrew Mitchell, Michael Burnett, Wyn Cudlip, Michelle Piepgrass to revise the 5-Year Plan according to the changes outlined at WGISS-33. | Andrew Mitchell, Michael Burnett, Wyn Cudlip, Michelle Piepgrass | WGISS-34 | Open
WGISS-33-22 | Satoko Miura to request each CEOS member agency to identify a WGISS representative or point of contact for technical issues. | Satoko Miura | 2012-05-30 | Open