## Slide 1: Data Interoperability Session Summary of Actions
Rob Woodcock (CSIRO)
Hosted by VAST/VNSC, Ha Noi, Vietnam
8-11 October 2019
Committee on Earth Observation Satellites
WGISS

## Slide 2
Actions from previous meetings
Number | Description | Actionees | Due Date | Status | Comments
WGISS-47-08 | Robert Woodcock to define next steps and schedule for FDA-08 White paper | Robert Woodcock | 20-May-19 | In progress | June 6: Rob will work to make document more complete and circulate the draft, but he needs more engagement from others.
WGISS-47-09 | Mirko Albani and Iolanda Maggio to complete FDA-09 Inventory deliverable | Mirko Albani | 31-Jul-19 | In progress | September 18: dedicated presentation during WGISS#48 meeting
WGISS-47-10 | ESA to present progress of European Data Cube at next WGISS | ESA | WGISS-48 | Closed | Presented at WGISS#48
WGISS-47-13 | Andrea Della Vecchia and Robert Woodcock to define with SEO a roadmap and short term activities on interoperability between ODC / HMDC / DCFS Data Cubes (e.g. Jupyter notebooks with XArray API and WCS / WPS) | Andrea, Robert, SEO | WGISS-48 | In progress | Aug 20: Rob reached out to Andrea to begin this task. Sep 24: joint call, follow-up at WGISS#48
WGISS-47-15 | Andrea Della Vecchia and Robert Woodcock to define with WGCV (Medhavy Thankappan, Phillipe Goryl, and Cindy Ong) coordinated roadmap and short term activities on WGISS-WGCV Data Cubes (ESA and ODC DEA) and possibly demo to be shown at SIT TW in September 2019 | Andrea, Robert | 30-Jun-19 | In progress | Aug 20: Rob met with Medhavy, who suggests revising one of the actions. This will be discussed with Mirko and Cindy.
WGISS-47-16 | Robert Woodcock to liaise with AquaWatch representatives to gather their requirements/needs and further define how WGISS could support | Robert Woodcock | 30-Jun-19 |  | 

## Slide 3
Actions from previous meetings
Number | Description | Actionees | Due Date | Status | Comments
WGISS-47-35 | SLT and Ad-hoc team led by Valerie Dixon (Michael Morahan, Andrea Della Vecchia, Chris Lynnes, Cristiano Lopes, Richard Moreno) to look into OGC Testbed 14 results and assess possible use and application within WGISS FDA interoperability activities | Valerie Dixon, CDA SLT | 31-Jul-19 | Ongoing | 
WGISS-47-20 | Liping Di and Kenneth Casey to confirm EXEC of closure of Action CARB-15 (i.e. when next version of Carbon portal is available online) | Liping Di | 31-Jul-19 | Closed | Aug 20: The new version is online
WGISS-47-33 | WGISS to give a demonstration of the Carbon Portal at the WGClimate meeting in September | WGISS | 31-Aug-19 | Closed | September: demo done. Next steps with WGClimate to be addressed.
WGISS-47-19 | Iolanda Maggio and Andrew Cherry finalise SW Inventory database tool, present to WGISS-Exec and publish on CEOS website | Iolanda Maggio | 31-Jul-19 | Ongoing | September 18: Dedicated presentation and final demo at WGISS#48 meeting
WGISS-47-22 | David Borges to share with WGISS the WGDisasters Generic RO white paper to identify opportunities where WGISS could support WGDisasters Generic RO technical requirements | David Borges | 31-Jul-19 | Closed | July 17: paper being finalized. Aug 28: WGDisasters Generic Recovery Observatory White Paper distributed.

## Slide 4
Actions from previous meetings
Number | Description | Actionees | Due Date | Status | Comments
CARB-15 | Carbon Data Portal prototype | Liping Di | Q2 2019 | Closed | Portal online
DATA-13 | Single Sign-On white paper | Marco Leonardi, Mirko Albani | Q2 2019 | Ongoing | September 28: DLR comments being integrated, final version will be distributed by end November.
FDA-05 | Promote awareness on FDA | WGISS | Q3 2019 | Closed | September: FDA webinar held. Material/recording to be published online.
FDA-08 | Common description of FDA functional blocks and interfaces. | Robert Woodcock | Q3 2019 | Ongoing | September 18: Draft with Rob, need more engagement.
FDA-09 | Inventory of FDA elements | Iolanda Maggio, Mirko Albani | Q4 2019 | Closed | Sep 28: inventory finalised, to be circulated to WGISS-EXEC.
FDA-10 | Inventory of SW and Tools plus discovery mechanism | Iolanda Maggio, Mirko Albani | Q3 2019 | Ongoing | Sep 28: inventory finalised, access through WGISS web site being implemented with SEO.
FDA-14 | Discovery/Access of SW/tools/Services through WGISS CDA | Andrea Della Vecchia, Robert Woodcock, Yonsook Enloe, Michael Morahan | Q4 2020 | Ongoing | Definition of metadata model for CEOS agencies tools and services ongoing. Once metadata model is agreed, content of the SW and Tools and FDA inventories (actions FDA-09 and FDA-10) will be used to populate the metadata repositories which will be made accessible thrpough the WGISS CDA.

## Slide 5
WGISS Federated Single Sign On
Mirko Albani
04/10/2019
Status and plans for the next release

## Slide 6: Status
The first draft version of the WGISS Federated Single Sign On white paper was delivered to the WGISS community on May 2019 according to what requested in Action WGISS-47-21
Feedback was expected until mid July 2019
DLR is the only organization that has provided a feedback with comments and proposals for improvement
Reviewed version of the document is expected by Q4 2019

## Slide 7: Overview
The first draft version included background, definitions and basic use cases for Federated Single Sign On:
  Federated Access
  Federated Single Sign On
  Authorization
  Accounting and Monitoring
In addition some interesting use cases have been proposed by DLR that are currently under evaluation:
  Single Log Out, Federated Single Log Out
  Dynamic Authorisation Updates
  User Profile Matching
  Privacy-preserving Authentication and Authorisation
Plus an additional proposal for improving aspects related to the Data Protection and Privacy

## Slide 8
New Actions from WGISS#48
Number | Description | Actionees | Due Date | Status | Comments
WGISS-48-XX |  |  | 31-Dec-19 | To be started |