**SDCG-10 Actions**

V1.0

|  |  |  |
| --- | --- | --- |
| **No.** | **Action** | **Due date** |
| **SDCG-10-1** | SDCG SEC to follow-up with the GFOI Office on the GFOI fact sheet for GEO Secretariat | **COMPLETE**GFOI Fact Sheet ("Opportunities to Help" in the GEO-XIII document) has been released |
| **SDCG-10-2** | SDCG SEC to follow up with GFOI Leads on representation at GEO Plenary | **COMPLETE** Doug Muchoney will not attend due to US travel constraints, Stephen Briggs will attend. Stephen Ward following-up on participation |
| **SDCG-10-3** | Frank Martin Seifert to send Shizu Yabe details of some examples of the use of the PALSAR 25m mosaics for biomass monitoring | September 2016 |
| **SDCG-10-4** | SDCG EXEC to confer on a communication to JAXA requesting that they maintain the long term continuity of systematic L-band SAR acquisitions | **COMPLETE**Letter sent to JAXA 19 Oct 2016 |
| **SDCG-10-5** | Ake Rosenqvist to draft a response to INPE’s offer to acquire over Africa for revision, comment and finalisation by SDCG EXEC | September 2016 |
| **SDCG-10-6** | SDCG members to provide feedback on the Conclusions and Recommendations of the Global Data Flows study | 16th September 2016 |
| **SDCG-10-7** | SDCG Element 3 (lead by Ake) to work with the GFOI R&D component to coordinate on a potential NovaSAR request for areas of interest for GFOI R&D, and coordinate this with UK community and contacts (John Remedios, Caroline Slim, Beth Greenway) | SDCG-11 |
| **SDCG-10-8** | Ake Rosenqvist to send invitations for the GFOI/GOFC-GOLD Science meeting in The Hague, Netherlands (31st October 31 – 4th November 2016) to Caroline Slim and Erik Lindquist | **COMPLETE**Ake has extended invitations to both Erik Lindquist and Caroline Slim |
| **SDCG-10-9** | Brian Killough to send Erik Lindquist and Gene Fosnight the link to the SPOT-5 pre-processed data that Steven Hosford has provided | **COMPLETE**<https://theia.cnes.fr/rocket/#/search?collection=SpotWorldHeritage> |
| **SDCG-10-10** | SDCG EXEC to follow-up with Steven Hosford on the status of the SPOT-4 and SPOT-5 archive pre-processing activity | **COMPLETE**~100,000 scenes from the SPOT archive downloadable from the link below, including some images over Africa.  Another ~100,000 are currently prcessed. An update on processing the rest of the archive should be available at SDCG-11. <https://theia-landsat.cnes.fr/rocket/#/search?collection=SpotWorldHeritage> |
| **SDCG-10-11** | Yves Crevier to write a one page summary on the call for interest in the 2010-2016 tiled RADARSAT-2 archive | October 2016 |
| **SDCG-10-12** | Ake Rosenqvist to coordinate an email and telecon consultation within the R&D data providers on the content and approaches to enhanced accountability | October 2016 |
| **SDCG-10-13** | Ake Rosenqvist to work with the Element 3 agencies to finalise the Element 3 strategy document revision and have it uploaded to gfoi.org | October 2016 |
| **SDCG-10-14** | Gene Fosnight to provide Brian Killough with information on the API call to the USGS Sentinel-2 data archive | September 2016In progress, appears Kristi Klein is the point of contact. The API interface used for Landsat is also used for Sentinel-2 data at EROS. |
| **SDCG-10-15** | Brian Killough to assess ability to add ALOS-2 to the COVE metadata browser | October 2016 |
| **SDCG-10-16** | Brian Killough to follow-up with Erik Lindquist on access to a demonstration account for the SEPAL system | Follow-up in October 2016 once the updated SEPAL system is released |
| **SDCG-10-17** | Erik Lindquist to circulate the announcement of the release of SEPAL once completed | Follow-up October 2016SEPAL release expected in the next few weeks |
| **SDCG-10-18** | SDCG EXEC to work with Sylvia Wilson and the GFOI Office to set up a meeting with Jenny Hewson on the upcoming REDDCompass training workshop in Colombia to discuss how to leverage the workshop to promote the GFOI end-to-end country demonstration | 22 September 2016 |
| **SDCG-10-19** | SDCG EXEC to confer on a communication to CONAE requesting a status update on the anticipated data policy for SAOCOM | **COMPLETE**Letter sent to CONAE 19 Oct 2016. |
| **SDCG-10-20** | Frank Martin Seifert to check whether SAOCOM will be included in the ESA TPM programme | **September 2016**In progress - SAOCOM is listed as a potential ESA TPM mission – Frank Martin will check with Bianca Hoersch to see if there have been any updates |
| **SDCG-10-21** | Pedro Rodriguez to report on his late-September visit to the Kenyan Forestry Ministry regarding the potential to leverage work Brian’s Data Cube has done for Kenya | **COMPLETE**Pedro has sent Brian his report from Kenya |
| **SDCG-10-22** | Ake Rosenqvist to follow-up with JAXA on the potential release for the JERS-1 1996 global mosaic, starting first Colombia (include in communication related to action SDCG-10-4) | **COMPLETE**Letter sent to JAXA 19 Oct 2016 |
| **SDCG-10-23** | SDCG EXEC to follow-up on having first version of the radar guide that Brian Killough and Ake Rosenqvist have been preparing uploaded to the GFOI space data portal once complete | October 2016 |
| **SDCG-10-24** | SDCG EXEC to communicate with the GFOI Leads on the GFOI end-to-end demonstration to ensure there is a plan to take it forward. Include the suggestions of a top-down approach via the Colombian GEO ExCom member, and that the Leads consider other countries for future end-to-end demonstrations | September 2016SW has asked Masonobu Shimada to add this to the GFOI Leads meeting |
| **SDCG-10-25** | SDCG Work Plan thread leads (Frank Martin, Gene, Brian, Ake, Stephen, George) to provide revised outcomes for the 2017-2019 Work Plan | September 2016Inputs being gathered. |
| **SDCG-10-26** | SDCG SEC to finalise updated 2017-2019 SDCG Work Plan | Penultimate draft for CEOS PlenaryFinalise by end November 2016 |
| **SDCG-10-27** | Stephen Ward to communicate the message to the GFOI Leads that the space data component, and the other GFOI components, are awaiting the result of the GFOI Review as a part of considering their future plans | September 2016SW has communicated this to the Leads |
| **SDCG-10-28** | SDCG EXEC to follow-up with Stephen Briggs on his report from this week’s UK policy session and the GEO Programme Board to the GFOI Leads | September 2016COMPLETE – Tom recently circulated a report from Peter Moore |
| **SDCG-10-29** | George to circulate a poll of SDCG-11 weeks to assess availability for feedback to the GFOI Leads | COMPLETEhttp://doodle.com/poll/5q4avz9ykwn9b4dd |
| **SDCG-10-30** | SDCG EXEC to follow-up with the GFOI Leads to get clarity around the future of funding of the GFOI Office, and the promotion of MGD uptake | September 2016 |