## Slide 1: Element 3 Space Data Support to GFOI R&D
A. Rosenqvist (for JAXA)
SDCG-13 Session #1 Item 1

## Slide 2: Session 1 outline
Tuesday March 13, 2018

## Slide 3: Status Overview of 3-Year Work Plan Tasks and Outcomes

## Slide 4
3-Year Work Plan – Element-3

## Slide 5
2017 Status: On schedule.
El-3 v4.0 to be submitted “for information” to SIT-33 (April 2018).
3-Year Work Plan – Element-3

## Slide 6
2017 Status: On schedule & good progress
  All SDCG agencies have completed selection of R&D teams to support
  All agencies are in the process of tasking and/or provision of data to the selected teams
3-Year Work Plan – Element-3

## Slide 7
2017 Status: Minor updates since SDCG-12
Private sector engagement
  AD&S (SPOT 6/7) – No feedback from Airbus. Further efforts to engage AD&S aborted.
  SSLT (NovaSAR) – Support confirmed by SSTL in March 2017. Contact point shifted to UKSA (Joanne). NovaSAR in El-3 or El-1 – to be discussed further
  Also exploring special NovaSAR data provision though CSIRO.
  Planet – renewed efforts to engage. Planet is present at this meeting. Will join on Thu PM?
3-Year Work Plan – Element-3

## Slide 8
New 2018 Objective (added by SW)
  Pursuit of a dedicated GFOI R&D fund with the main GFOI donors to address and remove the main technical obstacles to use of EO satellite and other data in reporting of countries. (Related to Carbon observing system strategy of EC CEOS Chair?)
3-Year Work Plan – Element-3

## Slide 9
Element-3 Strategy document – annual revision

## Slide 10
Element-3 version 4.0 in the pipeline for SIT-33
Updates to the agency data provision status (section 4)
  No updates received
  New section on UKSA required (after NovaSAR launch – perhaps more suitable for v 5.0 (2019) update)
  Ditto for CSIRO?
Updates to R&D group composition
  Group 11 (UNSW, Australia) – withdrawn.
  CESBIO, France – Invited to join the R&D programme on request by CNES. Invitation issued in June 2017. No response.
Element-3 Strategy document – annual revision

## Slide 11
R&D Group Technical Progress report to CEOS agencies
First report released March, 2017 by GFOI R&D Coordination (RDC) component
Progress reports by all 18 R&D groups
  Research progress
  Data access summary
Available at GFOI.org/RD
Second report due prior to SIT-33
“Light report” to be issued by GOFC-GOLD as funding for RDC component still pending
R&D reporting to CEOS agencies
Notes: ESA BIOMASS mission,