## Slide 1: GFOI R&D Component - Report
Ake Rosenqvist, Anthea Mitchell, Alex Held
Prepared in collaboration with
Brice Mora (GOFC-GOLD) and Frank Martin Seifert (ESA)
GFOI Components meetings
Sydney, Australia, March 2-6, 2015

## Slide 2: Proposed R&D Plan for 2015+
1. Launch of R&D programme.
- Establishment of agreements with R&D teams outlining responsibilities and time schedules
- Consolidation of requests for satellite observations for the SDCG Element-3 Strategy
Timeframe: April 2015
2. Coordination of R&D activity
- Manage participating (external) research teams and coordinate reporting and communication of results to space agencies and other GFOI components
- Interface between research teams and SDCG and CEOS space agencies.
Timeframe: Continuous during 2015
3. Coordinate Expert workshops
- Coordinate at least one Expert workshop on key Priority R&D Topics during 2015
Tentative host: CONABIO, Mexico
Timeframe: Q3 2015 (TBC)

## Slide 3: Proposed R&D Plan for 2015+
4. Update of R&D Review
- Continuous review of scientific literature and reports (i.e., 'science scanning') for methods and approaches that can be considered operational, and that have been developed outside of the GFOI R&D programme.
Timeframe: Annual
5. Liaison with other GFOI components
- Liaison with the SDCG, MGD and Capacity Building components to improve awareness of, and encourage their input to the R&D programme, and facilitate contributions to the MGD and future training programmes.
Timeframe: Continuous during 2015

## Slide 4: R&D Component – Open issues
GFOI R&D Plan:
  Provided to GFOI Leads for consideration and feed-back
Governance:
  Since February 2015 no Lead for R&D Component
  Critical: Leads to assure transition of Lead for R&D component without gaps
  Positive to option of GOFC-GOLD LC Office as lead for R&D
Funding:
  Leads need to re-establish funding mechanism without further delay to assure coordination of R&D component
Membership:
  Current R&D coordination membership proposed to be maintained