## Slide 1
Committee on Earth Observation Satellites
SIT Vice-Chair
Plenary Agenda Item #26
29th CEOS Plenary
Kyoto International Conference Center
Kyoto, Japan
5 – 6 November 2015
Report on Carbon
Strategy Implementation

## Slide 2
CEOS Strategy for Carbon Observations from Space was endorsed during Plenary session at SIT-29.
Carbon Strategy Implementation Study Team formed to analyze recommendations of CEOS Carbon Strategy and propose concrete way forward.
CEOS-28 in Tromsø agreed to:
            Instruct the identified CEOS entities to prioritise and include relevant CSIST-identified actions in their programs of work.
            Establish SIT Chair oversight of all Carbon actions (CARB-08) and request regular consolidated status reporting.
Context

## Slide 3
Latest Discussions
Dedicated working session was held during the SIT Technical Workshop 2015 VC/WG Day focused on VC and WG contributions.
All relevant VCs and WGs presented and:
Took the opportunity to clarify expectations
Updated on progress
Discussed challenges and blockers
Discussed linkages
Identify issues/requests to be raised to Plenary or SIT as appropriate.
Results were consolidated during the SIT Technical Workshop.

## Slide 4
Key Points
Limited concrete progress has occurred
All relevant VCs and WGs confirmed:
Their understanding of the actions.
That internal planning is under way, with a number of groups having processes on foot.
That no resource limitations have been identified.
The group noted the broad nature of some of the actions was presenting challenges for planning:
Some will take many years to complete.
Progress could be made on a number of fronts.
‘Grand plans’ difficult in a ‘best efforts’ context.

## Slide 5
Way Forward
VCs and WGs were reassured that Principals understand that ‘finishing’ many of the actions is a long-term effort and that an ‘agile’ approach is appropriate.
Noting the need to build momentum the SIT Vice Chair suggested that:
VCs and WGs focus specific near-term (1 year) steps that are achievable and will show progress.
Principals be engaged to determine their support for these proposed ‘next steps’; with this helping give VCs and WGs confidence in their direction.
VCs and WGs agreed to propose such next steps with a 1-year time horizon, for consideration at SIT-31
The Incoming SIT Chair will retain oversight role.

## Slide 6
The SIT Technical Workshop noted the cross-cutting long-term nature of the Carbon Actions:
They cross 3 VCs and WGs.
Many actions require collaboration.
Many will take years to complete.
Specific progress will depend on agency resources and priorities at the time – ‘grand plans’ unlikely.
The current process is providing valuable lessons on responding to a cross-cutting external mandate.
This is likely to become more common in the next decade of GEO with its increased focus on defining SBA-level requirement sets.
Broader Implications

## Slide 7
Requests for Plenary
No specific requests identified for CEOS-29.
Following consolidation of proposed ‘next steps’ at the next SIT meeting requests to Plenary may be identified.