## Slide 1: Action Status
Steven Hosford
CEOS Executive Officer
CEOS Plenary 2018
Agenda Item 1.3
Brussels, Belgium
17th – 18th October 2018
Committee on Earth Observation Satellites

## Slide 2
31st CEOS Plenary
SIT-33
2018 SIT Technical Workshop

## Slide 3
No. | Action | Due Date
CEOS-31-01 | WGClimate to explore development of a brief, consolidated statement of space agency contributions in support of each Article of the Paris Agreement. | 32nd CEOS Plenary
CEOS-31-04 | SIT Chair to coordinate feedback from the Virtual Constellations on how they will take the Feasibility Study on Satellite Missions/Instruments Focused on Water Quality Measurements into account in their work going forward. | COMPLETE
CEOS-31-05 | SIT Vice-Chair to coordinate establishment of a steering committee to determine the focus, scope, and arrangements of a CEOS “Water from Space” observations strategy workshop in Q2 2018. The matter of inclusion of the ocean component needs to be answered, with consideration being given to renaming the workshop if it will be excluded entirely, or if only coastal water will be included. | IN PROGRESS
31st CEOS Plenary Actions

## Slide 4
SIT-33 Actions
Agenda 6.10

## Slide 5
SIT-33 Actions
Agenda 2.2

## Slide 6
SIT-33 Actions
Agenda 3.6

## Slide 7
SIT-33 Actions

## Slide 8
2018 SIT Technical Workshop
No. | Actionee | Action | Due date
SITTW-2018-01 | WGClimate Chair | Manage process of review and submission of CEOS statement to SBSTA-49 | 26 Nov 2018
 | Rationale: Incoming CEOS Chair unable to attend SBSTA-49/COP-24 and WGClimate has agreed to give the CEOS/CGMS Statement. |  | 
SITTW-2018-02 | CEOS Chair | Circulate the Carbon Workshop minutes to the CEOS mailing lists | 20 Sep 2018
 | Rationale: Background for GHG issues to be debated at Plenary. |  | 
SITTW-2018-03 | Osamu Ochiai | Coordinate suggested CEOS Agency inputs to the IPCC Final Government Draft for the Good Practice Guide (GPG) report | Jan 2019
 | Rationale: CEOS Agencies may still influence the text via their governments. |  | 
SITTW-2018-04 | SIT Chair | Propose WGISS participation in the GEO Expert Advisory Group | 30 Sep 2018
 | Rationale: Because this EAG is tasked with providing guidance on how to implement a results-oriented GEOSS, it would be beneficial to have a WGISS representative participate in the EAG. |  | 
SITTW-2018-05 | SIT Vice Chair | Develop a discussion paper on a broad CEOS ARD Strategy | SIT-34
 | Rationale: SIT Vice Chair has adopted the CEOS ARD strategy as a priority theme for their term. |  | 
Agenda 2.1
Agenda 3.4
Agenda 5.4

## Slide 9
2018 SIT Technical Workshop
SITTW-2018-06 | All Responsible CEOS entities | Report WP progress in the CEOS Deliverables Database (ceos-deliverables.org) in preparation for CEOS Plenary | 30 Sep 2018
 | Rationale: In line with SIT Chair priorities, close monitoring of CEOS's progress against the annual work plan is critical to ensuring a correctly functioning organization. |  | 
SITTW-2018-07 | CEO | Share the invitee list and draft agenda for the Freshwater from Space Workshop with CEOS SEC and other relevant Principals to encourage participation by Agency representatives | 30 Sep 2018
 | Rationale: Agency support in securing registration of invitees. |  | 
SITTW-2018-08 | SEO CEO | Review the CEOS Deliverables Database, including linkages to GEO WP, and suggest improvements in information and reporting via CEOS SEC | SIT-34
 | Rationale: Significant scope for consistency improvements year-to-year identified in analyses presented at SIT TW. |  | 
SITTW-2018-09 | CEO SIT Chair | Review and revise reporting and tracking practices for CEOS WP activities | SIT-34
 | Rationale: Significant scope for consistency improvements year-to-year identified in analyses presented at SIT TW. |  | 
Agenda 1.4
Agenda 1.4

## Slide 10
2018 SIT Technical Workshop
SITTW-2018-10 | Co-Leads of SDCG, GEOGLAM AHWG, SDG AHT | Prepare to request a one-year extension to their term at CEOS Plenary | CEOS Plenary
 | Rationale: These three groups have proposed to have a final year of operation in their current state. |  | 
SITTW-2018-11 | Co-Leads of LSI-VC, SDCG, GEOGLAM AHWG | Bring to CEOS Plenary the proposed path for the new structure for the three groups’ activities | CEOS Plenary
 | Rationale: The joint meeting at JRC had significant debate and provided a recommendation for the GFOI and GEOGLAM AHTs to be housed under LSI-VC within the year. |  | 
SITTW-2018-12 | CEOS Chair | Invite GEO Secretariat Director to CEOS Plenary to underscore the desire for a CEOS-GEO leadership-level dialogue and encourage continuation of annual bilateral CEOS-GEO meeting. | 21 Sep 2018
 | Rationale: GEO Secretariat Director has changed and CEOS should stress the convention of the CEOS-GEO engagement and yearly Work Planning meeting. |  | 
Agenda 6.9
Agenda 6.8

## Slide 11
2018 SIT Technical Workshop
SITTW-2018-13 | SIT Chair CEO | Manage process of review and submission of CEOS written statement and interventions for GEO Plenary | CEOS Plenary
 | Rationale: Ensure clarity on CEOS positions in the context of changes to GEO direction under new GEO Secretariat Director. |  | 
SITTW-2018-14 | NOAA | Coordinate with WGDisasters and WGCapD on the flood monitoring initiative for GEO-LEO | SIT-34
 | Rationale: Significant potential and interest identified during the SIT TW. |  | 
SITTW-2018-15 | SIT Chair | Develop a transition plan, as appropriate, for sustained GEO-LEO activities into existing CEOS entities | Draft for SIT-34 Final for SIT TW 2019
 | Rationale: GEO-LEO initiative is seen as a future priority by SIT Vice Chair and we should ensure consistency with the process improvements under discussion. |  | 
Agenda 4.2
Agenda 5.6
Agenda 5.6