## Slide 1
Cindy Ong, CSIRO, WGCV
Akihiko Kuze, JAXA, WGCV
CEOS 33rd Plenary 2019
Session 5.1
Hanoi, Vietnam
14 – 16 October 2019
Working Group Calibration & Validation

## Slide 2
Deliverable | Q3 2019 | Q4 2019 | Q1 2020 | Q2 2020 | Q3 2020 | Q4 2020 | Q1 2021 | Q2 2021 | Q3 2021 | Q4 2021
CV-3 (pre-flight workshop) | Strong community interest. Joint GSICS/WGCV letter signed, workshop Q2 Q3 2020. Key aspect GHG sensors. | Due date extended to Q3 2020 |  |  |  |  |  |  |  | 
CV-9 (RadCalNet) | Ongoing task renewable each year |  | Ongoing task renewable each year |  |  |  |  |  |  | 
CV-14 (CMIX) | On track for delivery. 9 teams participating & have delivered their results over 5 evaluation datasets (Landsat-8 & Sentinel-2 scenes). Results currently being evaluated & will be published & discussed in 2nd ACIX II-CMIX WS (3-5 December 2019, ESA/ESRIN) (https://earth.esa.int/web/sppa/meetings-workshops/hosted-and-co-sponsored-meetings/acix-ii-cmix-2nd-ws) |  |  |  |  |  |  |  |  | 
CV-15 (L1 inter-operability) | Solar reference spectrum completed, WGCV/GSICS SI-traceable workshop, community white paper & proceedings to be published early 2020 |  |  |  |  |  |  |  |  | 
CV-17 (Continental SR) | Report distributed to community |  |  |  |  |  |  |  |  | 
CV-18 (GHG ref standards) | Apr 2019 meeting discussed TCCON. Workshop planned Q1 2020. Formal invitations distributed. |  | Extension to Q3 2020 (NB. Links to GHG) |  |  |  |  |  |  | 
CV-19 (biomass pro) | On track to be completed |  |  |  |  |  |  |  |  | 
FDA-12 (CEOS product inventory) | Work in progress as part of CARD4L peer review, CV-15 & WGISS/WGCV cooperation on QI |  | Deadline extended to Q2 2020 after WGCV46 meeting in March 2020 |  |  |  |  |  |  | 
CARB-16 (biomass SS) | On track to be completed |  |  |  |  |  |  |  |  | 
Status of WGCV’s Contribution to CEOS Work Plan

## Slide 3: WGCV’s Roles in GHG Road Map
WGCV ACSG
  Identify best practices for prelaunch calibration of CO2 and CH4 concentration sensors and facilitate the exchange and harmonization of approaches and reference standards (CV-18)
  Identify best practices for on-orbit calibration of GHG sensors and disseminate standards including solar, lunar, and surface vicarious validation sites (CV-3, CV-9, CV-15)
  Define an operational validation approach
In collaboration with GSICS
  Coordinate efforts to develop operational cross-calibration approaches based on prior work in AC-VC and WGCV

## Slide 4
Field Surface Reflectance “Round-Robin” (S3R) inter-comparison exercise represents a joint effort to test user-based differences in surface reflectance fiducial reference measurements used for validation of current SR satellite products, and to ensure consensus on field protocols and global SR validation protocols. It is a continuation of CV-17, including the use of drones and extending to other biomes/conditions and conducted in the framework of the ESA FRM4Veg project. These objectives shall be achieved inviting the scientific community to a “Round Robin” inter-comparison exercise and two international workshops to discuss the design of the S3R exercise and the main outcomes. In addition, the fiducial reference measurements collected during the exercise will serve to validate SR ARD products.
Objectives:
  Perform RR inter-comparison exercise of SR for:
  - Testing user-based differences in surface reflectance measurements (including instrument and operator biases as well as measurement collection procedures);
- Helping design field measurement protocols and validation methodology that are clear and can be easily applied by all users; and
- Ensuring international buy-in and consensus on the field measurement protocols and global SR validation methodology developed.
  Organize two workshops before and after RR for discussion on protocols, field experiment and outcomes
  Publish RR inter-comparison results
  Develop protocols for global SR validation (field radiometry, drones, others)
Outcome:
  Report summarising the S3R inter-comparison results
  Peer reviewed article co-authored by all participants who wish to publish the outcomes of the activity.
  SR validation protocols including field measurements and drones for CEOS WGCV LPV/IVOS endorsement.
Period: 2020 – 2021
  Experiment Call (Q2 2020)
  First Workshop (Q4 2020)
  S3R exercise (Q2 2021)
  Second workshop (Q3 2021)
  S3R inter-comparison report (Q4 2021)
  SR validation protocol (Q4 2021)
Contributing Entities: ESA, GA, NPL, CSIRO, IVOS, LPV
Funding support: ESA Earthnet (FRM4Veg project)
Field Surface Reflectance “Round-Robin” (S3R) inter-comparison exercise, and development of community endorsed SR validation protocols
CV-17

## Slide 5
BRIX-2 represents a joint effort to intercompare algorithms specifically for biomass mapping used for current and future spaceborne missions.
These objectives shall be achieved by making available standardised test cases (based on airborne campaign and spaceborne simulated data), inviting the scientific community to develop and apply retrieval algorithms based on this test case, and finally compare and evaluate the performance of submitted results.
Objectives:
  Provide an objective, standardized comparison and assessment of biomass retrieval algorithms developed for the BIOMASS, NISAR and GEDI missions, and fusion of these mission datasets.
  Establish a forum to involve scientists in the development of retrievals that have so far not been part of the biomass community.
  The adoption of vetted validation standards and methods to compare biomass estimates to reference datasets (e.g. field plots or airborne lidar biomass maps).
  Collect inputs from the biomass user and scientific community on data formats and characteristics towards the generation of Analysis Ready Data.
Outcome:
  The evaluation will be done by ESA/NASA, following standards from the CEOS LPV protocol. This should guarantee a fair evaluation. ESA/NASA will release a report to the participants summarising the evaluation results.
  Evaluation scripts available. This allow people to repeat the experiment and compare their results against the published ones.
  The results should easily be adapted for publication as a peer reviewed article co-authored by all participants who wish to publish the outcomes of the activity.
Period: 2020 – 2021.
  Experiment Call Q12020.
  First Workshop (Target: Q3 2020)
  Results Submission Deadline (date of first workshop + 6 months?)
  Results Evaluation Report (date TBD)
  Second workshop (date of first workshop + 9 months)
Contributing Entities: LPV, ESA, NASA (JPL, University Maryland)
With contribution from Scientists team involved in BIOMASS, GEDI, NISAR
Second Biomass Retrieval Intercomparison Exercise BRIX-2

## Slide 6
Justification
  Multiple upcoming SAR missions;
  Capability to support multi-mission SAR calibration / validation would facilitate an independent verification of data quality (radiometric, geometric)
  Ongoing discussion between NASA, GA for NISAR L-band calibration, ISRO interest for S-band calibration noted with implications for NovaSAR calibration; Other interested
Objectives
  Define a set of criteria / requirements and characteristics for setting up SAR supersites (similar to RADCALNET);
  Need to cater for multiple calibration validation and observation requirements e.g. CRs, transponders, PARCs, left / right looking, temporal stability;
  A model of sustainable operations be central to SAR supersites;
Definition of the work plan with resources and timelines to be prepared by the SAR subgroup for discussion at the CEOS SAR SG Nov 2019 meeting in Frascati;
New: SAR Supersites for multi-mission SAR radiometric / geometric calibration, cross-calibration & validation

## Slide 7
Outcome of workshop on Global Digital Elevation Model (DEM) Benchmarking - JRC/EC & geomorphometry.org
  reactivate the Terrain Mapping Sub-Group (TMSG) of the CEOS-WGCV;
  work towards a comparison of state-of-art global DEMs based on a set of harmonized metrics;
Scope and Products to be included: All datasets which have an at least continental coverage and are available under a free & open data policy, including latest versions of
  NASADEM (NASA, JPL, most recent decent of the SRTM product line, eventually also NGA’sTFRMv4)
  AW3D30 (JAXA, f&o version of the Japanese ALOS based global DEM)
  ASTER-GDEM, (METI, NASA)
  TanDEM-X90, (DLR, free version for scientific of the TanDEM-X mission)
  Copernicus DEM90 (EC/ESA, f&o version of WorldDEMTM, the commercial version of TanDEM-X procured by Airbus)
New: Digital Elevation Inter-Comparison

## Slide 8
DEMIX to be performed in 4 phases
  General agreement among main contributors (data owners) on approach & scope; Call for expression of interest to further partners (commercial tbd); circulation of JRC Workshop report (in preparation) & selection of base (△x, △y, △z) & extended (slope, aspect, morphology) testing methods and algorithms; Identification of suitable test areas (at least 1 per continent);
  Cross-comparison of all participating data sets on test areas and, if feasible, identification of a reference dataset (at DGED L1). If available and where applicable cross-comparison to suitable orthorectified (reference?) imagery (Sentinel-2?); Workshop to exchange experiences from the test areas and agree on details of an eventual global roll-out;
  Feasibility testing & potential global roll out of at least base tests & determination of suitable aggregation scale for reporting;
  Calculation of agreed comparison metrics for all candidates and publication of results.
Timeline
New: Digital Elevation Inter-Comparison
Q4 2019 |  | Q1 2020 |  | Q2 2020 |  |  | Q3 2020 |  | Q4 2020
 | Phase I |  |  |  |  |  |  |  | 
 |  |  | Phase II |  |  |  |  |  | 
 |  |  |  |  | Phase III |  |  |  | 
 |  |  |  |  |  |  |  | Phase IV | 

## Slide 9
Collaboration between Microwave SG and Ocean Surface Vector Wind –VC
VC-15 “OSVW Standards and Metrics” revival following agreement at quarterly SIT teleconference for this activity to be renewed as collaboration between OSWV-VC and WGCV MSSG;
Objective: defining standards and metrics to enable cross calibration/comparison between scatterometers and wind retrieval approaches;
Collaborators: KNMI, EUMETSAT, ICM, NSOAS, NSSC
Other potential collaborators: NOAA, ISRO
Timeline: TBA
New: Ocean Surface Wind Vector Standards & Metrics

## Slide 10: Building on collaboration between WGCV & WGISS
Concurrent in-situ & satellite data availability on ESA Cube
Demonstration with RadCalNet & ACIX, LPV
Resolve challenges with inconsistencies with LPV supersites
Extension to other validation sites?
Data Formats, processing, etc.
Access to WGCV beta testers
Potential appln: new S3R, BRIX-2, DEMIX WPs, GHG
ARD SR data available for site on ODC
Field data uncertainties
Satellite data uncertainties
Potential appln: new SAR SS

## Slide 11
CEOS WGCV LPV joint biomass & supersite meeting 2-6th March 2020, Canberra Australia
  Explore & build on synergies of supersite & biomass validation protocol;
  Recommendations of the biomass protocol;
  TERN supersites for EO validation;
  Australian use case for biomass missions and relevance of TERN network for biomass validation;
  Co-operation between international network (FORESTGEO, FORESTPLOTS, etc.);
  Interoperability and access of data from sites such as TERN supersites, GBOV, FRM4Veg, etc.
Field trip, 4th March 2020, Tumbarumba, Australia
  Assessment of sites and demonstration of biomass & other relevant CEOS WGCV LPV protocols at LPV supersite / TERN supersite;
WGCV activities contributing to future SIT chair initiative

## Slide 12
Opening for vice-chair position;
Europe is the next on list of the rotation but any nominations from qualified candidates will be considered;
Interested candidates please contact cindy.ong@csiro.au or kuze.akihiko@jaxa.jp
Resources Requirements

## Slide 13
Questions?