**CEOS SIT-26 Actions**

Final v1.0

*SIT-27 Status Update*

|  |  |  |
| --- | --- | --- |
| No. | Action | Due date |
| SIT 26-1 | CEOS agencies to urgently review draft Version 0 of the 2012-2015 GEO Work Plan, and send comments to the CEO for coordination. | COMPLETE (26 May 2011) |
| SIT 26-2 | CEOS agencies to undertake best efforts data acquisitions in support of the 2011 coverage requirements of the GEO FCT. | COMPLETE |
| SIT 26-3 | CEOS agencies to review and feedback on the draft ‘CEOS Strategy for Space Data Coverage and Continuity in Support of the GFOI and FCT Task’. | COMPLETE SDCG established at Plenary.  SDCG-1 Meeting held 6-8 March |
| SIT 26-4 | Carbon Task Force Co-Chairs to report progress to the CEOS Plenary. | COMPLETE Further update at SIT-27 |
| SIT 26-5 | CEOS Chair to work with CEOS and GEO Secretariats to develop a planning process for CEOS inputs and outcomes in relation to Rio+20. | Ongoing To be reported under item 12 |
| SIT 26-6 | CEOS SIT Chair to identify a CEOS Agency to lead efforts on the integration of satellite observations and data in support of the Water Cycle Integrator initiative. CEOS agencies encouraged to support regional GEO Water Workshops currently in planning. | GEO Water Strategy Report initiated. JAXA as Water SBA Coordinator is leading the CEOS interface. |
| SIT 26-7 | Guy Seguin to report to CEOS Plenary on progress towards the GEO Supersites initiative, including outcomes of the June coordination meeting and recommendations for the way forward. | COMPLETE CEOS Plenary |
| SIT 26-8 | CEOS agencies encouraged to be represented in the JECAM Space Data Coordination meeting (21-23 June, Ottawa) and to establish points of contact for JECAM. | COMPLETE  GEO-GLAM update provided to SIT-27 |
| SIT 26-9 | CEOS agencies to provide comments on the proposed new GEO Task on polar ecosystems, the CEOS role therein, and expressions of interest in participation and support. | COMPLETE |
| SIT 26-10 | WGISS, in coordination with SIT Chair, to enable CEOS IDN metadata accessibility via the GCI and to propose a plan for maintenance of this capability. | COMPLETE CEOS Plenary |
| SIT 26-11 | CEOS agencies to register metadata describing available datasets made available to the GCI in the IDN. | COMPLETE CEOS Plenary |
| SIT 26-12 | CEOS agencies encouraged to ensure datasets meeting DataCORE criteria are added to the GCI and corresponding product catalogues and repositories interfaced. | COMPLETE |
| SIT 26-13 | Mitch Goldberg to remind CEOS agencies of the public review period of the GCOS Satellite Supplement and to develop a consolidated commentary for GCOS. | COMPLETE |
| SIT 26-14 | CEOS agencies encouraged to review and respond to the draft report of the Climate Architecture Writing Team (expected 12 Sept). | COMPLETE |
| SIT 26-15 | CEOS agencies invited to nominate representatives to the GHRSST Advisory Council. | OPEN – NO RESPONSE |
| SIT 26-16 | SST VC leads to submit their Constellation proposal document in time for consideration during a SIT session at CEOS Plenary. | COMPLETE |
| SIT 26-17 | CEOS Agencies encouraged to provide nominations to WGCV Chair for the WGCV Vice-Chair, with the role commencing at WGCV-34 (February 2012, Australia), and transition to WGCV Chair at WGCV-35 (September 2012, TBD). | OPEN |
| SIT 26-18 | WGCV Chair to prepare a detailed proposal to augment QA4EO capacity and requesting CEOS agency resources. | TBC |
| SIT 26-19 | WGCV to provide a minimum instrumentation list and suggested activities for CEOS recommended instrument Cal/Val sites. | TBC |
| SIT 26-20 | Incoming SIT Chair to manage execution of the CEOS Self Study and to deliver a report to CEOS Plenary. | COMPLETE |
| SIT 26-21 | CEOS Chair, in consultation with CEOS SEC, to represent CEOS interests in the debate around formulation of the GEO working structures for the new WP. | COMPLETE |
| SIT 26-22 | CEOS Chair, in consultation with CEOS SEC, to explore options for CEOS presence and input at COP-17. | COMPLETE |
| SIT 26-23 | CEOS Chair to establish and oversee a small study team charged with the drafting of terms of reference for a new WG - being a merger of WGEdu and Data Democracy. | COMPLETE |
| SIT 26-24 | CEOS Chair to invite Principals to be represented at a WGEdu / Data Democracy strategy planning meeting to be held in Washington in September around the SIT workshop. | COMPLETE |