## Slide 1: WG Capacity Building & Data Democracy (WGCapD)
Nancy D. Searby, PhD., NASA & Prakash Chauhan, ISRO, WGCapD Vice-Chair & Chair
CEOS SIT-34
Session and Agenda Item # 3.9
Miami, FL, USA
3 – 4 April 2019
Committee on Earth Observation Satellites

## Slide 2
CEOS Work Plan 2019-2021v0 – WGCapD’s 17 deliverables, 13 in 2019, 4 in 2020; * new this year
  Global activities
    CB-28, 30, 31: MOOCs on Radar Backscatter (Q1), SAR applications (Q1), LCLUC (Q4 2019 – delayed, in procurement, now likely 2020)
    CB-29: Webinar series on multiple topics, e.g. GEOGLAM, Hyperspectral Remote Sensing and Disasters (Q4), LCLUC (Q3 2020)
  Regional activities – training in GEO regions
    CB-35, 36: AmeriGEO (Aug 19-23) (Q3), AfriGEO (Aug 13-16) (Q3)
    CB-27: AOGEO (Q4 2020)
    CB-32: Regional hands-on training in Land Cover Land Use Change (Q4)
  *National in-person training
    CB-33: SAR and EO data training for VNSC Chair initiative (Q3 – completed 1 of 2 workshops)
    CB-39: hands-on training on forest monitoring & Orfeo Tool Box for AEM (Q1)
    CB-40: hands-on training on flood monitoring for Vietnam School of Earth Observation (Q3)
WGCapD Linkages to Work Plan, SIT, SIT TW Actions
Notes: Provide max total of five slides to address these points in your final presentation
Suggestion - 1 slide each to address
  Linkages to CEOS Work Plan (e.g. action numbers), open SIT and Plenary actions
    Indication of required decisions and discussion points
  Team Achievements and Planned Outcomes [See slide 9]
  Synergies amongst teams (e.g. VC-VC, VC-WG, WG-VC, WG-WG, other) [See slide 10]
  Sustainable commitment [See slide 11]
  Proactive Consideration of Plenary and SIT TWS deliverables and discussion items

## Slide 3
CEOS Work Plan 2019-2021v0 – WGCapD’s 17 deliverables, 13 in 2019, 4 in 2020; * new this year
  CB infrastructure
    CB-21: portal-based access to CB and training resources (Q4 2020)
  * CB training materials
    CB-38: hyperspectral training resources on line (Q2 2020)
  WG collaborations
    CB-41: with SDG AHT, promote use of EO for SDG’s (Q3)
      Hands-on with AmeriGEO Week on SDG 6.6.1/6.3.2
    FDA-5: FDA´s awareness building and outreach (Q3)
  Broader CB collaborations
    CB-37: white paper describing how CB networks, e.g. UN’s, can work together with WGCapD (Q2 – provided to SIT for discussion)
CEOS-32-10 & SITTW-2018-14: GEO-LEO project coordination with CGMS, WGDisasters - ongoing
WGCapD Linkages to Work Plan, SIT, SIT TW Actions, cont’d
Notes: Provide max total of five slides to address these points in your final presentation
Suggestion - 1 slide each to address
  Linkages to CEOS Work Plan (e.g. action numbers), open SIT and Plenary actions
    Indication of required decisions and discussion points
  Team Achievements and Planned Outcomes [See slide 9]
  Synergies amongst teams (e.g. VC-VC, VC-WG, WG-VC, WG-WG, other) [See slide 10]
  Sustainable commitment [See slide 11]
  Proactive Consideration of Plenary and SIT TWS deliverables and discussion items

## Slide 4
Completed 3 deliverables
  CB-20 AmeriGEOSS Week in person training
  CB-26 AfriGEOSS Symposium in person training
  CB-19 SDG Awareness webinar
Lessons learned
  Needed improved outreach and possible funding of participants to improve attendance at AmeriGEO Week training
  Good participation in SDG awareness webinar; not much response to post-webinar survey
  Clarity of needs and sufficient lead time essential for training success
Planned outcomes in 2019
  Execute and deliver deliverables per the Work Plan
2018 Accomplishments and Lessons Learned

## Slide 5
White paper drafted provided for capacity building community review
  WGCapD, GEO, WMO, Vlab
  Incorporated suggestions
  Now provided to SIT for discussion
CB-37: white paper describing approaches for CB networks, e.g. UN’s, can work together (due Q2 ‘19)
Framework for coordinated capacity building

## Slide 6
Existing synergies – strengthened since last SIT
  WGISS/SEO – participation in each others’ meetings, joint FDA-5 deliverable
  SDG AHT – joint awareness webinar delivered December 2018
  WGDisasters – joint virtual meeting discussion in March, discussing joint deliverables
  GEOGLAM AHT – overlapping people engaged in both, potential to strengthen further
  WGClimate, WGCV – have explored synergy but have not (yet) identified collaborative opportunities
  VCs – no engagement
Obstacles/barriers and how to overcome them
  Travel constraints prohibit attending other WG/AHT/VC meetings – arrange virtual meetings to discuss work planning
Synergies Among Teams

## Slide 7
Active agencies in your team:
  WGCapD Core has 13 Deliverables due this year: CNES, DLR, ESA, INPE, ISRO, NASA, VNSC
  Annual meeting virtual participation also included: SANSA, UK’s National Centre for Earth Observation (UK NCEO), CRECTEALC, GODAN, GEO Sec CD Coordinator, AfriGEO, AmeriGEO, VLab
Obstacles to the future viability of your team meeting its objectives?
  Need a new Vice Chair this fall!
Status and outlook
  We have a well-engaged core group, and we are growing.
Sustainable Commitment

## Slide 8
Thanks
Chair: Dr. Prakash Chauhan
Vice Chair: Dr. Nancy Searby
& WGCapD Members