## CEOS Deliverables 4Feb2016a.csv
CEOS SEO proposed effort to contribute to this action | Number | Status | Completion Date | Responsible CEOS Entities | Title | Description | Progress Report
| CARB-08-01 | Open | 2016-Q2 | SIT Chair | Defined requirements for quantifying aboveground carbon storage in vegetation. | CEOS Member Agencies with interests in missions and data products for forest canopy height and aboveground biomass will sponsor or co-sponsor one or more workshops (and require a written report) to define the scientific and policy requirements to quantify aboveground carbon storage in vegetation. These meetings should involve the key international science, applications, and remote sensing communities in specifying the technical foundation and scientific requirements for as well as the societal benefits of future missions to quantify aboveground carbon storage in vegetation globally.? The workshops should consider these requirements in the context of the added value to be derived from coordinated mission planning and associated data compilation activities both in the future and by exploiting archive data.
| CARB-08-02 | Open | 2017-Q4 | LSI-VC | Inclusion of IGCO continuity priorities in VC and WGClimate activities | The relevant CEOS VCs and CEOS WG Climate will act to include IGCO priorities for continuity carbon-related observations of the land surface from space in their respective activities to coordinate the VCs and climate-related measurements.
The SEO will develop a list of moderate resolution satellite data records measuring land properties relevant to carbon science and describe their data policies, measurement type, domain, time of record, resolution and other relevant product details. The results will be given to the LSI-VC for review. | CARB-08-03 | Open | 2017-Q4 | LSI-VC | Public availability of historical moderate-resolution satellite data records | CEOS Agencies with historical moderate-resolution (~250 m - 1 km) satellite data records will strive to ensure these data are publicly available and used to create the moderate-resolution (~250 m - 1 km) records of land properties over the historical satellite record that are useful for carbon science.? They will coordinate their efforts with relevant CEOS WGs and VCs.
The SEO will develop a list of medium resolution satellite data records measuring land properties relevant to carbon science and describe their data policies, measurement type, domain, time of record, resolution and other relevant product details. The results will be given to the LSI-VC for review. | CARB-08-04 | Open | 2017-Q4 | LSI-VC | Public availability of historical medium-resolution satellite data records | CEOS Agencies with historical medium-resolution (~30 m -100 m) satellite data records will strive to ensure these data are publicly available and used to create the medium-resolution records of land properties over the historical satellite record that are useful for carbon science.? They will coordinate their efforts with relevant CEOS WGs and VCs.
| CARB-08-05 | Open | 2017-Q4 | WGCV ??? | Ongoing production of consistent well-calibrated bias-free time-series carbon products | CEOS Agencies with interests in and/or mandates for developing multi-sensor, multi-mission time series data products for the land (and ocean) will strive to ensure consistent, well-calibrated, bias-free satellite time-series carbon products are produced and continued into the future.? They will coordinate their efforts in consultation with relevant CEOS WGs and VCs to ensure appropriate merging of data and products from multiple sensors.
| CARB-08-06 | Open | 2016-Q2 | LSI-VC | Coordination of efforts to develop satellites to observe wetlands/inland waters and produce derived products | Individual CEOS Agencies with interests in and/or mandates for developing 1) satellites to observe wetlands and inland waters and 2) wetland and inland water data products will coordinate their efforts in consultation with relevant CEOS WGs and VCs.
This should be pushed to GEO and the new GD-06 task focused on In Situ coordination | CARB-08-07 | Open | 2017-Q4 |  | Encouragement agencies to expand in-situ observations required for calibration of land products | CEOS and CEOS Agencies will encourage national and international agencies to improve and expand upon the availability of the in situ observations needed for the calibration and validation of satellite land data products used for carbon science.? This will include coordinating with national and international agencies collecting in situ data to 1) assess the quality and coverage (spatial and temporal) of validation data and 2) employ design features that entice data sharing and provide safeguards.
| CARB-08-08 | Open | 2016-Q2 | WGCV ??? | Expanded validation of satellite land data products | The CEOS WGCV's Land Product Validation (LPV) Subgroup will continue its work to validate satellite land data products and expand the number of land variables addressed as priorities are identified and available resources permit, and where no other body takes responsibility (e.g., GOFC-GOLD).
| CARB-08-09 | Open | 2017-Q4 | WGCV ??? | Prioritised carbon data product intercomparison activities | CEOS WGCV and its relevant subgroups, in consultation with the CEOS Carbon Subgroup (recommended in Carbon-Action-38), will organize and coordinate carbon data product intercomparison activities as they are identified as priorities for CEOS action and in coordination with the wider carbon cycle science community.
| CARB-08-10 | Open | 2017-Q4 | OCR-VC | Inclusion of IGCO priorities for extended time-series of medium-resolution observations in VC and WGClimate activities | The relevant CEOS VCs and CEOS WG Climate will act to include IGCO priorities to extend the time series of moderate-resolution carbon-related observations of the open ocean from space into their respective activities to coordinate the VCs and climate-related measurements.
| CARB-08-11 | Open | 2017-Q4 | OCR-VC | Inclusion of IGCO priorities for extended time-series of high-resolution observations in VC and WGClimate activities | The relevant CEOS VCs and CEOS WG Climate will act to include IGCO priorities for continuity in high-resolution (better than 0.5 km) carbon-related observations of coastal waters from space in their respective activities to coordinate the VCs and climate-related measurements, noting the higher temporal and spatial resolutions? and spectral coverage required, compared with open-ocean measurements. ?
| CARB-08-12 | Open | 2017-Q4 | OCR-VC | Coordination of efforts to develop satellites to observe phytoplankton and other water properties and increase resolution for coastal and inland waters | CEOS Member Agencies with interests in and/or mandates for developing and deploying new types of satellite missions to provide 1) new information on phytoplankton functional types, phytoplankton carbon by type, detritus, particulate carbon, and aerosols, and/or 2) higher spatial, temporal, and spectral resolution data for coastal and inland waters will coordinate their efforts in consultation with relevant CEOS WGs and VCs.
| CARB-08-13 | Open | 2017-Q4 | SIT Chair | Coordination of efforts to develop satellites to measure salinity | CEOS Member Agencies with interests in and/or mandates for developing and deploying new satellites to measure ocean salinity will coordinate their efforts in consultation with relevant CEOS WGs and VCs.
| CARB-08-14 | Open | 2016-Q2 |  | Progress efforts to validate and characterize errors of ocean carbon-relevant products | The CEOS WGCV, in close consultation with the relevant VCs (that are doing some of this work now), will establish a subgroup dealing with validation and error characterization of ocean carbon-relevant products analogous to the Land Product Validation Subgroup.
| CARB-08-15 | Open | 2016-Q2 | OCR-VC | Strengthen linkages with GEO Blue Planet initiative | CEOS Agencies will maintain and/or act to strengthen their linkages with the Blue Planet initiative and support of GEO Task SB-01, which brings together the ocean communities engaged in satellite as well as in situ observations, to ensure that user requirements are taken into account and products are produced in carbon units.
| CARB-08-16 | Open | 2016-Q2 | AC-VC | Refined requirements for quantitative data on atmospheric CO2 and CH4 from LEO | CEOS Member Agencies with interests in CO2- and CH4-measuring LEO missions will sponsor or co-sponsor one or more workshops (and require a written report) to refine the scientific and policy requirements for quantitative data on atmospheric CO2 and CH4 from low Earth orbit. These meetings should involve the key international science and applications communities in specifying the technical foundation and scientific requirements for as well as the societal benefits of future missions to quantify atmospheric CO2 and CH4 from low earth orbit. | Reported under action VC-05
The SEO could support the AC-VC by conducting LEO constellation trade studies to measure coverage and temporal sampling of constellation options. | CARB-08-17 | Open | 2017-Q1 | AC-VC | Coordinated detailed planning/preparation of a constellation of instruments to measure CO2 and CH4 from LEO | The CEOS Atmospheric Composition VC will coordinate the detailed planning and preparation for a constellation of passive and active remote sensing instruments to measure CO2 and CH4 from low Earth orbit with the higher spatial and temporal resolution and accuracy needed to monitor carbon sources and sinks. | Reported under?action VC-05
| CARB-08-18 | Open | 2017-Q4 | AC-VC | Refined requirements for quantitative data on atmospheric CO2 and CH4 from GEO | CEOS Member Agencies with interests in CO2- and CH4-measuring GEO missions will sponsor or co-sponsor one or more workshops (and require a written report) to refine the scientific and policy requirements for quantitative data on atmospheric CO2 and CH4 from geostationary Earth orbit.? These meetings should involve the involve the broad, international science and applications communities in advancing the technical foundation and scientific requirements for as well as the societal benefits of future missions to quantify atmospheric CO2 and CH4 from geostationary orbit. | Reported under?action VC-05
The SEO could support the AC-VC by conducting GEO constellation trade studies to assess and optimize coverage. | CARB-08-19 | Open | 2017-Q4 | AC-VC | Coordinated detailed planning/preparation of a constellation of instruments to measure CO2 and CH4 from GEO | The CEOS Atmospheric Composition VC will coordinate the detailed planning and preparation for a constellation of passive remote sensing instruments to measure CO2 and CH4 from geostationary orbit covering all longitudes with the spatial and temporal resolution and accuracy needed to monitor carbon sources and sinks. | Reported under action VC-05
| CARB-08-20 | Open | 2017-Q4 | AC-VC | Cross calibration/validation/coordination of all satellite CO2- and CH4-measuring sensors | The CEOS Atmospheric Composition VC, in cooperation with the CEOS WGCV Atmospheric Composition Subgroup, will provide coordination and support for the cross calibration of all? satellite CO2- and CH4-measuring? sensors, coordinate their observations, and cross validate their CO2 and CH4 products against accepted international standards, so that they can be integrated into single continuous global climate record. | Reported under action VC-05
| CARB-08-21 | Closed | 2017-Q4 |  | Prioritisation of carbon observations and data products that transcend traditional scientific domains | The CEOS Carbon Subgroup (recommended in Carbon-Action-38) will coordinate with other relevant CEOS WGs and VCs to ensure that the carbon observations and data products that transcend traditional scientific domains (e.g. black carbon, nutrient fertilization) are accorded appropriate priority in CEOS activities and future plans and that key satellite products to permit scientific studies of these phenomena are produced and made available.
| CARB-08-22 | Open | 2017-Q4 |  | Increased compatibility, comparability and consistency of carbon products | CEOS Agencies engaged in development of carbon products will coordinate to achieve compatibility, comparability and consistency of carbon products across all relevant domains (land, oceans an
| CARB-08-23 | Open | 2017-Q1 | AC-VC | Coordinated efforts to improve information on natural and anthropogenic emissions of carbon | Individual CEOS Agencies with interests in and/or mandates for providing improved information on natural and anthropogenic emissions of carbon (CO2, CH4, CO and black carbon) will coordinate their efforts in consultation with relevant CEOS WGs and the Atmospheric Composition VC. | Reported under action AC-05
| CARB-08-24 | Open | 2017-Q4 | WGClimate | Production and availability of high-quality consistent long time-series data products based on multiple sensors and missions | The CEOS Carbon Subgroup (recommended in Carbon-Action-38)? will work to encourage the production and availability of high-quality, consistent long time series data products based on multiple sensors and missions for carbon and climate science and for model-data and data-data intercomparison exercises. ?
| CARB-08-25 | Open | 2017-Q4 | SIT Chair | Periodic releases of technical information regarding readiness for transitions from research to operations for long time-series carbon observations | The CEOS Carbon Subgroup (recommended in Carbon-Action-38) and relevant VCs will provide periodic technical information to the research and operational space agencies regarding readiness for and issues regarding transitions from research to operations for long-time series carbon observations.
| CARB-08-26 | Open | 2017-Q1 |  | Comparison of protocols for the generation of carbon products to ensure long-term consistent datasets relevant to carbon cycle community needs | The CEOS Carbon Subgroup (recommended in Carbon-Action-38), in consultation with the CEOS WGCV, will encourage comparison of protocols for the generation of carbon products from satellite data and? recommend adoption of the best protocols by CEOS agencies to ensure long-term consistent datasets relevant to carbon cycle community needs. This work shall include accounting for ancillary data dependence (e.g., land cover, aerosol, cloud, DEM, reanalysis products, etc.) such that there is consistency across individual products and variables.
| CARB-08-27 | Open | 2017-Q4 |  | Public availability of information necessary to document the quality of satellite data | CEOS Agencies will make publicly available all information necessary to document the accuracy, clarity, and traceability of the satellite data and data products they produce. | Space Agency efforts on carbon have been updated as part of the final WGClimate response to the GCOS 2010 implementation plan. That report can be found on the CEOS web site
| CARB-08-28 | Open | 2017-Q4 | WGClimate | Coordinated efforts to develop compatible carbon data products from multiple missions | CEOS Agencies will coordinate their efforts to develop compatible (e.g., temporal and spatial resolution, grids, data formats, common auxiliary data, units) carbon data products from multiple missions, in consultation with relevant CEOS WGs and VCs.
| CARB-08-29 | Open | 2017-Q1 |  | Guidelines for the specification of uncertainty in carbon products | The CEOS Carbon Subgroup (recommended in Carbon-Action-38) will develop guidelines for the specification of uncertainty in products, from signal counts through the various CEOS Processing Levels.
The SEO could support this action using the content of the CEOS Data Policy Portal which includes information on data policies and access links. Mission/Instruments relevant to Carbon would need to be identified. | CARB-08-30 | Open | 2017-Q4 | WGClimate | Long-term accessibility of satellite data and data products for carbon cycle science and policy | CEOS Agencies will ensure the long-term accessibility of satellite data and data products for carbon cycle science and policy.? This must include arrangement for secure archives, documentation, and metadata as well as for provisions for easy discovery and access by the carbon science and policy communities.
| CARB-08-31 | Open | 2017-Q1 |  | Strengthened mechanisms for carbon product validation | CEOS through its WGCV and relevant VCs will strengthen its mechanisms for product validation by establishing validation methodologies, protocols and benchmark datasets.
| CARB-08-32 | Open | 2017-Q4 |  | Assessment of the provision of validation data and identification of additional validation sources | For each of the relevant variables in each of the domains CEOS will work with the carbon science community to assess the current provision of validation data in terms of quality (defined by protocols (e.g., WGCV LAI protocol) and or maturity matrices (e.g., WG Climate)) and spatial and temporal coverage.? This work should identify potential additional sources and develop a strategy to improve global in situ data distributions in relation to satellite validation and model parameterization. It should also exploit existing infrastructures to develop key intensive collection sites.
| CARB-08-33 | Open | 2016-Q2 | SIT Chair | Reinforced mechanisms to ensure coordination and effectiveness of intercomparison activities | CEOS will reinforce the mechanisms already in place in CEOS for all domains (WGCV, and VCs, and WG Climate) and clarify their responsibilities to ensure intercomparison activities are well-coordinated and effective.
| CARB-08-34 | Open | 2017-Q4 |  | Improved ability to compare, and integrate quantitatively, similar carbon data products | Individual CEOS Agencies producing the same (or similar) carbon data products will cooperate to ensure that their products are compared to the other relevant products and, if technically feasible, ensure efforts are made so that their products can be used quantitatively with these other products.
| CARB-08-35 | Open | 2017-Q1 | WGISS | Guidelines for appropriate data use of satellite data and data products | The CEOS Carbon Subgroup (recommended in Carbon-Action-38) will develop guidelines for appropriate data use of satellite data and data products.? This will require improved interactions between the carbon cycle community and the satellite community; comprehensive review of the current use of data products, including current data limitations; and reconciliation of methodological differences and spatial compatibility.? Such interactions may include co-sponsorship of joint workshops targeting specific data needs and investment in community product assessments, especially for key intercomparison exercises. | Not yet started.
| CARB-08-36 | Open | 2017-Q4 | SIT Chair | Strengthened linkages with relevant carbon communities and organizations | CEOS will strengthen linkages with relevant carbon communities and organizations to facilitate the communications and coordination necessary to ensure that the satellite data products provided by CEOS Agencies meet needs and are utilized appropriately.
| CARB-08-37 | Open | 2017-Q4 |  | Point of contact for carbon-relevant satellite products | The CEOS Carbon Subgroup (recommended in Carbon-Action-38) will serve as a point-of-contact for appropriate satellite products for major model-data intercomparison exercises related to the carbon cycle. | ?Stephen Plummer as WGClimate representative for the GEO Carbon Flagship
| CARB-08-38 | Closed | 2016-Q2 | SIT Chair | CARB-08-38 | CEOS will establish a group to be responsible for carbon activities within CEOS and for advancing the findings and recommendations of this report.? This group will take responsibility for overseeing, coordinating, and reporting on the actions identified in this report.? It is recommended that CEOS establish a Carbon Subgroup within the CEOS WG on Climate as a most efficient way of implementing this action (this recommended group will hereafter be referred to as the ?Carbon Subgroup?).? The Carbon Subgroup will report to (and through) the WG Climate.? It will establish strong working relationships with all relevant VCs and CEOS WGs, especially the WGCV.
| CARB-08-39 | Closed | 2016-Q2 |  | Sponsorship of efforts to identify, and promote, specific measurement requirements for continuing and new carbon observations from space | CEOS and individual CEOS Agencies will sponsor (or co-sponsor) work (e.g., one or more workshops, a written report) to 1) develop more specific measurement requirements for continuing and new carbon observations from space that will fulfill science and policy needs and 2) encourage further prioritization of these measurements.
| CARB-08-40 | Closed | 2016-Q2 |  | Plan efforts to identify, and promote, specific measurement requirements for continuing and new carbon observations from space | The CEOS Carbon Subgroup (recommended in Carbon-Action-38) will lead in the planning for activities to 1) develop more specific measurement requirements for continuing and new carbon observations from space that will fulfill science and policy needs and 2) encourage further prioritization of these measurements.? It will work, in consultation with the relevant VCs, to coordinate the incorporation of the refined requirements and priorities into multi-agency planning and preparation for future satellites.
| CARB-08-41 | Closed | 2017-Q4 | SIT Chair | CARB-08-41 | The CEOS Carbon Subgroup will report to the CEOS WGClimate.? It will track and report upon progress in responding to the actions in the CEOS Strategy for Carbon Observations from Space in a manner similar to that for the CEOS Response to the GCOS Implementation Plan (IP), which includes at a minimum annual reporting by the Carbon Subgroup through the WG Climate? to the CEOS SIT and Plenary.
| CARB-08-42 | Open | 2017-Q4 | SIT Chair | Periodic assessment of progress against CEOS Carbon Strategy | CEOS will periodically (approximately every 3-5 years) assess progress toward meeting the challenges identified in this report.? This may be accomplished through a variety of means, including but not limited to workshops, ad hoc studies, or discussions within or among relevant CEOS WGs and VCs.