## Slide 1: CEOS WGCV-55 Action Review
Harvey Jones,
WGCV Secretariat
Agenda Item W1.1
WGCV-56 / LSI-VC-19 Joint Meeting
Sioux Falls, SD, USA
20-24 April, 2026

## Slide 2
Cal/Val Portal pages exist for MSSG, SAR and IVOS, and LPV has a website hosted by NASA. No webpage for TMSG and ACSG.
Suggestion: repurpose this action to establish Cal/Val Portal pages for TMSG and ACSG.
Suggest that the CEOS webpages continue to host subgroup ToRs, governing documents, and contacts, and CVP detail subgroup activities / focus areas, repositories, and meeting information.
WGCV-55 Actions
WGCV-55-01 | WGCV Subgroup chairs to communicate subgroup activities to Paolo to be shared on the Cal/Val Portal at https://calvalportal.ceos.org/wgcv. | WGCV-56
CEOS website: ceos.org/wgcv/subgroups | Cal/Val Portal: calvalportal.ceos.org/web/guest/wgcv

## Slide 3
An action from WGCV-54 carried over to WGCV-55
Is this database still desired? Would it be useful on the PVP as well?
WGCV-55 Actions
WGCV-55-02 | Paolo Castracane to work with Nigel Fox to establish on the Cal/Val Portal an IVOS database on radiometric calibration capabilities. | Q4 2025

## Slide 4
To be addressed in item W4.5 this afternoon
WGCV-55 Actions
WGCV-55-09 | Medhavy and Paolo to communicate with Bruce and Stephane that WGCV Membership should be notified when new SARCalNet site submissions are ready for approval. A step in the review and approval process for SARCalNet sites should include that WGCV membership is notified. | To be addressed at WGCV-56

## Slide 5
WGCV-55-12 | Pre-flight Calibration Workshop team (Nigel, Albrecht, Philippe, Paolo) to develop a good practice guidance document to summarise the workshop’s outcomes and recommendations. | Q1 2026 In progress. Guidelines development telecons initiated October 30th.
Extend deadline?
WGCV-55 Actions

## Slide 6
WGCV-55-14 | Subgroup Chairs and WGCV members to consider adding other product validation tools beyond the optical domain onto a common front page of the CEOS Product Validation Platform. | WGCV-56
Reminder to Subgroup chairs to suggest additional platforms to add to the Product Validation Platform (email Nigel and Harvey)
Proposal to close action
WGCV-55 Actions

## Slide 7
WGCV-54 Actions
Keep in mind for GSICS session later!
WGCV-54-07 | Philippe and Nigel to initiate a discussion with WMO representatives on key in situ networks that could be brought in line with the FRM Assessment Framework / labelling. We would like to see broad utilisation of the FRM label.