## Slide 1
Work Planning & Deliverables Discussion
Session 8: Applying Learning to Future Activities
NASA
Lauren Childs-Gleason
CEOS WGCapD-9 Annual Meeting
Sunnyvale, California
10-12 March 2020

## Slide 2
CEOS work planning - takes place annually to create a new three year work plan
CEOS Work Planning
Deliverable
Updates
January
February
March
April
May
June
July
August
September
October
November
December
Work Plan development
CEOS
Plenary
SIT TW
SIT
WP Progress
Report (CEO)
Example:
2019-2021
CEOS Work Plan
ENDORSED
Mar 22, 2019
Annual progress on deliverables is reported at the CEOS Plenary by the CEO, WGs report progress on a rolling basis with a final update in September
Progress reported here:
http://deliverables.ceos.org/task_manager/deliverables/?status=2&sort=number
  Ex. Typically, the 2020-2022 CEOS Work Plan would be endorsed at the SIT-35

## Slide 3
Current Work Plan Planning
We need to revisit the open and new deliverables’ deadlines and assess for updates or modifications needed
Work to clear out open deliverables
Begin/continue discussions for near-term deliverables
Work with Kerry Sawyer to update the final list of WGCapD deliverables ahead of the SIT-35
WGCapD Work Planning Actions
Next Work Plan Planning
Look ahead to the end of 2020 when the next work plan inputs are due
We should reflect on the process we went through in Oct-Dec of 2019
Begin conversations regarding ideas and potential collaborations now
Identify a planning calendar for WGCapD with milestones we can meet leading up to submission in ~December 2020

## Slide 4
Global Deliverables
WGCapD’s 2019 Carry Over Open Deliverables
Tracking # | Completion | Title | Description | Responsible POCs | Contributors
CB-31 | Q2 2020 | Conduct global capacity building courses a MOOC (Massive Online Open Course) on Land Cover and Land Use Changes | ESA with support of other WGCapD members will provide a MOOC (Massive Online Open Course) on Land Cover and Land Use Changes, if feasible through the EO-College portal in cooperation with DLR | Robert Eckhardt, Univ Jena; Francesco Sarti, ESA; Amalia Castro Gomez, ESA; Michael Bock, DLR | ESA, DLR
CB-29 | Q3 2019 | Conduct global capacity building courses through Webinar on Asia-GEOGLAM, SAR Missions: Present and future, Disaster Risk Reduction (UNOOSA) (global training-interactive) | ISRO with support of NASA, DLR and other theme specialists will plan to conduct these webinar series on these specialized topics. | Prakash Chauhan, ISRO | ISRO, DLR, NASA, UKSA
CB-28 | Q1 2021 | Conduct global capacity building courses through a multi-lingual MOOC for advanced practitioners/experts on radar backscatter | DLR's SAREDU project by FSU Jena will provide a multi-lingual MOOC (German, English, French, Spanish, Portuguese tbc) on radar backscatter for advanced practitioners/experts through the EO-College portal. | Michael Bock, DLR | DLR, ESA
CB-38 | Q2 2020 | Provide CB support to Hyperspectral Remote Sensing. | The DLR funded HyperEDU initiative lead by the GFZ Potsdam will, provide free & open learning material for Hyperspectral remote sensing through the EO-College portal | Michael Bock, DLR | DLR, ISRO
Tracking # | Completion | Title | Description | Responsible POCs | Contributors
CB-21 | Q4 2020 | Explore future options for providing portal-based access to capacity building and training resources | Conduct a study of existing and potential new approaches to collect, coordinate, and synergize available capacity building and training resources related to satellite Earth observations, e.g. GEOCAB, the VLab training calendar, , the EO-College collection of resources, and more. | Prakash Chauhan, ISRO | ISRO
Tracking # | Completion | Title | Description | Responsible POCs | Contributors
CB-34 | Q3 2020 | Provide webinar on LCLUC theme | Focus will be on Land Cover/Land Use Change theme. Deliver lectures/training materials relating to Land Use/Cover Change in South/Southeast Asia countries either through Webinars or hands-on training to participants (in one of the South/Southeast Asian countries). | Garik Gutman, NASA; Krishna Vadrevu, NASA | NASA, ESA
CB-27 | Q4 2020 | Provide CB support to regional and thematic AOGEOSS initiative | Engage with AOGEOSS initiative and find out the needs of the region for possible training initiatives WGCapD could support | Prakash Chauhan, ISRO | ISRO
Infrastructure Deliverable
Regional Deliverables

## Slide 5
WGCapD’s New Deliverables: Infrastructure
Tracking # | Completion | Title | Description | Responsible POCs | Contributors
CB-46 | Q4 2020 | Space Capacity Development Advisory Board | Establish the Space Capacity Development Advisory Board | Nancy Searby, NASA; Senthil Kumar, ISRO; Sergio Camacho, CRECTEALC | NASA, ISRO, CRECTEALC
CB-48 | Q42020 | Best Practice Guide to E-Learning | Best practice guide to e-Learning | Robert Eckhardt, EO College | NASA
CB-50 | Q1 2021 (TBC) | Capacity Development Guidance Document for GEOGLAM | Support GEOGLAM CapDev Team in developing their capacity development guidance document. | NASA TBC | NASA, CNES, VITO, JRC; ISRO (TBC), JAXA (TBC)
CB-47 | Q4 2021 | Metadata Standards Tiger Team | Selection and definition of metadata standards for the exchange and processing of learning objects. We like to identify a Tiger Team to work on this | Robert Eckhardt, EO College | WGISS (TBC), NASA, IDN (TBC)

## Slide 6
WGCapD’s New Deliverables: Global
Tracking # | Completion | Title | Description | Responsible POCs | Contributors
CB-43 | Q2 2020 | COVE Webinar | Prepare a COVE webinar | Kim Holloway, NASA/SEO; Chris Barnes, USGS | WGCapD, SEO, USGS
CB-45 | Q1 2021 | Jupyter Notebooks Awareness Webinar | Explore hosting a Jupyter notebooks awareness webinar in 2020-2021 | Robert Woodock, CSIRO; Kent Ross, NASA | CSIRO, NASA, WGISS
CB-44 | Q3 2021 | CARD4L Awareness Webinar | Collaborate w/LSI-VC to host a CARD4L awareness webinar | Chris Barnes, USGS; Matthew Steventon | USGS (TNC), NASA (TBC), LSI-VC
CB-42 | Q4 2021 | SDG Training on Land Use Efficiency (11.3.1): EO Data, Indicator Methodology, and Tool Training Webinar | Land use efficiency -related training focused on UN HABITAT methodology & training module, relevant EO datasets, Trends.Earth 11.3.1 tool & some use cases to build awareness and enhance use at regional to national scale | Argie Kavvada, NASA | NASA, SDG AHT, CSA (TBC), ISRO (TBC), EC (TBC), SANSA (TBC)

## Slide 7
WGCapD’s New Deliverables: Regional
Tracking # | Completion | Title | Description | Responsible POCs | Contributors
CB-60 | Q3 2020 | In-Person Regional Training in South Asia | One regional training in South Asia on forest biomass | Prakash Chauhan, ISRO | ISRO, JAXA, NASA
CB-61 | Q4 2020 | SELPER 2020 | Chile will organise SELPER 2020, and ESA is planning to deliver a training on EO for applications relevant to the region | Francesco Sarti, ESA; Amalia Castro Gomez, ESA | ESA, NASA (LCLUC & ARSET), CRECTEALC, CONAE, INPE, AEM, CNES
CB-62 | Q4 2021 | Copernicus User Uptake in Africa | Copernicus User Uptake in Africa via technical support in the field of Disaster Management and Disaster Risk Reduction (mainly Capacity Building in cooperation with UN-SPIDER), starts 2020 (tbc till End of 2019, subject to EU funding) | Jens Danzeglocke, DLR | DLR, UNSPIDER, WGDisasters (TBC)
CB-63 | Q4 2020 | AOGEO Contribution | Coordinate a training in association with AOGEO on a mutually agreed topic (e.g. food security, forest, land use) | Prakash Chauhan, ISRO | ISRO (TBC), VNSC (TBC), JAXA (TBC), NASA (TBC)
CB-64 | Q3 2020 | AmeriGEO Contribution | Meeting in Mexico City, early Sept; support trainings; conduct a needs assessment for trainings | Sergio Camacho, CRECTEALC; Nancy Searby, NASA | NASA, CRECTEALC
CB-65 | Q4 2020 | Remote Sensing Training in Africa | GIS & Remote Sensing training for Users in Africa e.g. South African Geography educators, Training the Network of Science Centres in Africa (SAASTEC), and/or at the AFRIGEOSS Event 10/31-11/2 Port Elisatbeth in Cooperation with SANSA and AfriGEO | Dan Matsapola, SANSA; Dan Irwin, NASA; Michael Bock, DLR | DLR. NASA (SERVIR & DEVELOP), SANSA, GODAN

## Slide 8
WGCapD’s New Deliverables: National
Tracking # | Completion | Title | Description | Responsible POCs | Contributors
CB-58 | Q2 2020 | Provite CB support to AGEOS on forest monitoring | Provide training on the use of Sentinel 1 images for forest monitoring on a well instrumented local site. | Linda Tomasini, CNES | CNES, AGEOS
CB-53 | Q3 2020 | Collaborative Feasibility Study | 10-week dual capacity building feasibility study (June-Aug 2020) focused around data cube algorithm creation (focused in Vietnam, Mexico) | Kent Ross, NASA; Sergio Camacho, CRECTEALC; Pham Thy, VNSC | NASA (DEVELOP), SEO, CRECTEALC, VNSC
CB-56 | Q3 2020 | In-Person SAR training | SAR training for forest and rice monitoring | Pham Thy, VNSC; Amalia Castro Gomez, ESA | USTH, CNES, ESA (TBC)
CB-51 | Q4 2020 | In-Person Air Quality Training (Thailand) | Air Quality Training focused in Asia - Thailand | Dan Irwin, NASA; Ana Prados, NASA | NASA (SERVIR & ARSET), GISTDA, Asia Disaster Preparedness Center / SERVIR-Mekong
CB-57 | Q4 2020 | In-Person SAR training | SAR training for subsidence monitoring | Pham Thy, VNSC | CNES, ESA (TBC)
CB-59 | Q42020 | Provide CB to Recovery Observatory Project | Provide training to national Haïti institutes involved in Recovery Observatory project | Linda Tomasini, CNES | CNES
CB-52 | Q4 2021 | In-Person Air Quality Training (Vietnam) | Air Quality Training focused in Asia - Vietnam | Pham Thy, VNSC; Dan Irwin, NASA; Ana Prados, NASA | VNSC, NASA (SERVIR & ARSET)
CB-54 | Q4 2021 | Indigenous Peoples-focused In-Person Training (Canada) | Engage with indigenous peoples in one or more workshops to build their capacity in the use of Earth observation information for their community needs, and share the learning gained from these national programs to improve methods for engagement with indigenous people internationally through collaboration with CEOS partners. | Cindy Schmidt, NASA; Janin Huard, CSA | NASA, SEO, GODAN, CSA, GA
CB-55 | Q4 2021 | Indigenous Peoples-focused In-Person Training (Australia) | Engage with indigenous peoples in one or more workshops to build their capacity in the use of Earth observation information for their community needs, and share the learning gained from these national programs to improve methods for engagement with indigenous people internationally through collaboration with CEOS partners. | Cindy Schmidt, NASA; John Pring, Geoscience Australia | NASA, SEO, GODAN, GA
CB-58 | Q2 2020 | Provite CB support to AGEOS on forest monitoring | Provide training on the use of Sentinel 1 images for forest monitoring on a well instrumented local site. | Linda Tomasini, CNES | CNES, AGEOS

## Slide 9
CEOS deliverable numbering system is being updated
Heads Up
149 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Climate Monitoring, Research, and Services (6) | CMRS-23 | CMRS-24 | CMRS-25 | CMRS-26 | CMRS-27 | CMRS-28 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | CMRS-19-02 | CMRS-19-03 | CMRS-19-04 | CMRS-19-05 | CMRS-19-06 | CMRS-20-01 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 2020 Q3 | 2021 Q3 | 2020 Q4 | 2020 Q3 | 2020 Q3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Carbon Observations, Including Forested Regions (11) | CARB-16 | CARB-21 | CARB-22 | CARB-23 | CARB-24 | CARB-25 | CARB-26 | CARB-27 | CARB-28 | CARB-29 | CARB-30 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | CARB-17-05 | CARB-19-02 | CARB-19-03 | CARB-19-04 | CARB-19-05 | CARB-19-06 | CARB-20-01 | CARB-20-02 | CARB-20-03 | CARB-20-04 | CARB-20-05 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 2022 Q4 | 2020 Q1 | 2020 Q3 | 2021 Q4 | 2021 Q4 | 2020 Q2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Observations for Agriculture (1) | AGRI-13 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | AGRI-19-04 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 2020 Q4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Observations for Disasters (12) | DIS-10 | DIS-16 | DIS-18 | DIS-20 | DIS-21 | DIS-22 | DIS-23 | DIS-24 | DIS-25 | DIS-26 | DIS-27 | DIS-28 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | DIS-15-04 | DIS-18-01 | DIS-19-01 | DIS-19-02 | DIS-19-03 | DIS-19-04 | DIS-20-01 | DIS-20-02 | DIS-20-03 | DIS-20-04 | DIS-20-05 | DIS-20-06 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 2020 Q4 | 2020 Q4 | 2021 Q4 | 2020 Q1 | 2020 Q3 | 2020 Q3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Observations for Water (1) | WAT-6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | WAT-17-03 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 2020 Q4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Data Quality (10) | CV-3 | CV-14 | CV-15 | CV-18 | CV-19 | FDA-12 | CV-20 | CV-21 | CV-22 | CV-23 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | CV-14-03 | CV-16-02 | CV-17-01 | CV-18-02 | CV-18-03 | FDA-18-05 | CV-20-01 | CV-20-02 | CV-20-03 | CV-20-04 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 2020 Q3 | 2020 Q2 | 2019 Q4 | 2020 Q4 | 2020 Q2 | 2020 Q2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Capacity Building and Data Democracy (31) | CB-21 | CB-27 | CB-28 | CB-29 | CB-31 | CB-34 | CB-38 | CB-42 | CB-43 | CB-44 | CB-45 | CB-46 | CB-47 | CB-48 | CB-49 | CB-50 | CB-51 | CB-52 | CB-53 | CB-54 | CB-55 | CB-56 | CB-57 | CB-58 | CB-59 | CB-60 | CB-61 | CB-62 | CB-63 | CB-64 | CB-65 |  |  |  |  |  |  |  | 
 | CB-17-02 | CB-18-05 | CB-18-06 | CB-18-07 | CB-18-09 | CB-19-02 | CB-19-06 | CB-20-01 | CB-20-02 | CB-20-03 | CB-20-04 | CB-20-05 | CB-20-06 | CB-20-07 | CB-20-08 | CB-20-09 | CB-20-10 | CB-20-11 | CB-20-12 | CB-20-13 | CB-20-14 | CB-20-15 | CB-20-16 | CB-20-17 | CB-20-18 | CB-20-19 | CB-20-20 | CB-20-21 | CB-20-22 | CB-20-23 | CB-20-24 |  |  |  |  |  |  |  | 
 | 2020 Q4 | 2020 Q4 | 2020 Q1 | 2020 Q2 | 2020 Q2 | 2020 Q3 | 2020 Q2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Data Discovery, Access, Preservation, Usability (11) | DATA-9 | DATA-11 | DATA-13 | DATA-15 | DATA-16 | DATA-17 | FDA-2 | FDA-8 | FDA-10 | FDA-14 | DATA-19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | DATA-17-02 | DATA-17-04 | DATA-18-01 | DATA-19-01 | DATA-18-02 | DATA-19-02 | FDA-2017-02 | FDA-18-01 | FDA-18-03 | FDA-19-01 | DATA-20-01 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 2020 Q2 | 2019 Q4 | 2019 Q4 | 2020 Q4 | 2019 Q4 | 2019 Q4 | 2021 Q4 | 2020 Q2 | 2019 Q4 | 2020 Q4 | 2020 Q4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
CEOS Services (6) | DATA-2 | CV-09 | CMRS-17 | CMRS-20 | CMRS-21 | CB-XX-MIM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | DATA-14-01 | CV-14-09 | CMRS-16-06 | CMRS-17-01 | CMRS-17-02 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 2020 Q2 | 2020 Q4 | 9999 Q4 | 9999 Q4 | 9999 Q4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Advancement of the CEOS VCs (39) | VC-9 | VC-14 | VC-15 | VC-31 | VC-33 | VC-37 | VC-40 | VC-42 | VC-43 | VC-44 | VC-45 | VC-46 | VC-47 | VC-48 | VC-49 | VC-50 | VC-51 | VC-52 | VC-53 | VC-54 | VC-55 | VC-56 | VC-57 | VC-58 | VC-59 | VC-60 | VC-61 | VC-62 | VC-63 | VC-64 | VC-65 | VC-66 | VC-67 | VC-68 | VC-69 | VC-70 | VC-71 | VC-72 | VC-73
 | VC-14-09 | VC-14-14 | VC-14-15 | VC-18-01 | VC-18-03 | VC-18-07 | VC-19-03 | VC-19-05 | VC-19-06 | VC-19-07 | VC-20-01 | VC-20-02 | VC-20-03 | VC-20-04 | VC-20-05 | VC-20-06 | VC-20-07 | VC-20-08 | VC-20-09 | VC-20-10 | VC-20-11 | VC-20-12 | VC-20-13 | VC-20-14 | VC-20-15 | VC-20-16 | VC-20-17 | VC-20-18 | VC-20-19 | VC-20-20 | VC-20-21 | VC-20-22 | VC-20-23 | VC-20-23 | VC-20-24 | VC-20-25 | VC-20-26 | VC-20-27 | VC-20-28
 | 2021 Q4 | 2019 Q4 | 2018 Q4 | 2022 Q4 |  | 2021 Q4 | 2022 Q4 | 2020 Q4 | 2020 Q4 | 2020 Q4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Support to Other Key Stakeholder Initiatives (21) | SDG-5 | SDG-6 | BP-4 | BON-7 | COV-4 | COV-5 | COV-6 | SDG-7 | SDG-8 | SDG-9 | SDG-10 | SDG-11 | SDG-12 | SDG-13 | SDG-14 | SDG-15? | SDG-16? | SDG-17? | SDG-18? | SDG-19? | SDG-20? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | SDG-19-01 | SDG-19-02 | BP-17-02 | BON-19-02 | COV-17-04 | COV-18-01 | COV-18-02 | SDG-20-01 | SDG-20-02 | SDG-20-03 | SDG-20-04 | SDG-20-05 | SDG-20-06 | SDG-20-07 | SDG-20-08 | SDG-20-09 | SDG-20-10 | SDG-20-11 | SDG-20-12 | SDG-20-13 | SDG-20-14 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 2020 Q1 | 2020 Q4 | 2020 Q1 | 2020 Q2 | 2020 Q4 | 2021 Q1 | 2021 Q3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Organization Issues and Outreach (0) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Capacity Building and Data Democracy (31) | CB-21 | CB-27 | CB-28 | CB-29
 | CB-17-02 | CB-18-05 | CB-18-06 | CB-18-07
 | 2020 Q4 | 2020 Q4 | 2020 Q1 | 2020 Q2

## Slide 10
Potential Timeline
March – July: initial conversations
July: submit ideas to WGCapD Chair, ideas compiled and shared for discussion focus during the July WGCapD monthly call
July – Aug: enlist collaborators, refine ideas
Late Aug: submit refined ideas to WGCapD Chair and participate in an in-person meeting (WGCapD-10) to discuss and finalize
Sept – Nov: final refinement
Nov/Dec: Submit final list to CEOS CEO
Thoughts? Ideas?
Next Work Plan Planning Actions