## Slide 1: Greenhouse Gas (GHG) Task Team Meeting #3
Y.Meijer, ESA
GHG Task Team Lead
GHG TT Meeting #3
17th October 2023, ESA/ESRIN

## Slide 2
Consolidate Action list of GHG Roadmap
Discuss Cal/Val continuity in support of GHG observations
Discuss role and engagement of CEOS with New Space
GCOS IP response of CEOS
Review status of CEOS Deliverables
GHG Mission Portal
Action Status of Meeting #2:
Revise mission overview  closed, see agenda item 9
Action on Roadmap to set list of standards for New Space  John?
Update Annex C  to be assessed after agenda items 2 & 4
1. Objectives of Meeting #3

## Slide 3
Area leads (plus deputies) have been appointed using the thematic areas of Annex C (actions) in the GHG Roadmap:
Stakeholder Engagement - Mark (John, Wenying)
System Development Facilitation – Richard (John, Kevin)
Operational Preparation and Training – TT discuss
Sensor Development – John (AC-VC) (Yasjka)
L1 & L2 GHG Product Development – Ruediger & Dave
Flux Inv. Model Development – Kevin (Frederic)
Calibration & Validation – Hiroshi (Kuze)
Leads mailing list has been set-up ghg-tt-leads@googlegroups.com
Points of Contact of all WGs have been obtained
GHG TT mailing list has been set-up ghg-tt@googlegroups.com
Work has been supported by Symbios!
1. GHG Task organisation

## Slide 4
1. Challenges
        User engagement:
        UNFCCC (GST)
        CO2: policymakers at smaller spatial & temporal scales (covenant of mayors, finance)
        CH4: (policymakers) on non-O&G related emissions, e.g. landfills, wetlands
        Mission delays, Space Agencies false notion that New Space could do it all
        Tackle the aquatic (mainly coastal & open ocean) aspect of the carbon cycle
        Timely switch to missions capable to monitor the carbon cycle in a changing climate

## Slide 5
2. GHG Roadmap Update
Only soft update through Annex C of the GHG Roadmap
Update of action list by a thorough review per Area coordinated by Area Leads (add more milestones & specific (SMART) actions)
Split along various scales (point/area vs national/regional)
Split between CO2 & CH4

## Slide 6
Update of Action List (annex C) – 1/2
Stakeholder Engagement - Mark Dowell
System Development Facilitation – Richard Engelen
Calibration & Validation – Akihiko Kuze
Mark
Richard
Akihiko

## Slide 7
3. GHG Cal/Val Networks
GHG Cal/Val Networks Sustainment by WG-CalVal – Atmospheric Composition Sub-Group * Jean-Christopher Lambert, BIRA-IASB * Philippe Goryl
EUMETSAT’s Cal/Val Support Strategy – Thierry Marbach
Reflection on Action List in this Area?
Thierry
WGCV

## Slide 8
 |  | Action Description | Lead | Status | Revisit |  | 
Operational Preparation and Training Lead: GHG TT | Ops-1 | Establish and maintain an overview of the process followed for achieving operational readiness of the PS and IOS (including system commissioning and beta testing prior to the declaration of operational readiness) and provide feedback as appropriate | WGC-TT | 2. ON GOING | Annual | (jw) seems like these next 3 require determination of outcomes from the previous set of components (system development facilitation) | 
 | Ops-2 | Establish and maintain an overview of the governance arrangements for the operation of the PS and IOS and provide feedback as appropriate | WGC-TT | 2. ON GOING | Annual | (jw) again, this needs revisiting based on upcoming EIS | 
 | Ops-3 | Establish and maintain an overview of the arrangements and documentation for preparing end-users to exploit the outputs of the system, including training, and provide feedback as appropriate | WGC-TT | 2. ON GOING | Annual | (jw) again, this needs revisiting based on upcoming EIS | [DC]: It would seem that capacity building is a critical element of this task. Should WGCapD be involved?
Update of Action List (annex C) – 2/2
Operational Preparation and Training – TT discuss
Sensor Development – John Worden
L1 & L2 GHG Product Development – Ruediger Lang
Flux Inv. Model Development – Kevin Bowman
Lead
John
Ruediger
Kevin

## Slide 9
5. New Space Coordination
Topic led by John Worden
Development of evaluation criteria
Supporting validation activities
Climate finance
John
6. GCOS IP Response
Topic led by Yasjka Meijer
Response to GCOS IP 2022
Related activities in B3.1, F2.2, F5.2 & F5.4
Yasjka

## Slide 10
7. CEOS Work Plan Deliverables
        Status GHG Task Team actions in CEOS Work Plan
        CARB-23-01: Lessons learnt from pilot CO2 and CH4 products (delivered for GST-1) Summarise lessons learned from the pilot CO2 and CH4 pilot product delivered to UNFCCC for the 1st GST
         closed
        CARB-23-02: Standards for uncertainty monitoring of flux estimates Generate a set of standards for uncertainty reporting of flux estimates  closed*
        CARB-23-03: GCOS IP response for GHG-related activities Respond to GCOS IP 2022 for GHG related activities  closed
        CARB-23-04: Update GHG Roadmap (focus on Action List) Review and update the GHG Roadmap Action list (Annex C)  closed
        CARB-23-05: New Space and GHG product development and standards setting Engage with New Space and commercial sector in GHG product development and standards setting
         closed*
        * This will evolve further as normal work in GHG TT

## Slide 11
8. Auditing CH4 Emission Products
UKSA / NPL Auditing scheme for satellite‐derived methane emissions products
Topic led by Paul Green & Paul Palmer
UKSA
9. GHG Mission Portal
Presented by Stephen Ward
Stephen

## Slide 12
Actions from Minutes of Meeting #2:
Revise mission overview  John, CLOSED, see agenda item 9
Action on Roadmap to set list of standards for New Space  John?
Update Annex C  Leads, to be assessed after agenda items 2 & 4
Propose Roadmap action along the lines of “Prepare the community for the products of new upcoming satellite missions & ensure continuity to earlier/existing missions”  Leads, to be assessed after agenda items 2 & 4
Define Roadmap Action to converge AFOLU and GHG Roadmaps  Mark?
Organise meeting on uncertainty of flux estimates  CLOSED
Generate standards for uncertainty reporting of flux estimates  conclusion?
10. Action Status Meeting #2

## Slide 13
10. Way forward & AOB
        Next steps of GHG Task Team
        Presentation to SIT-TW; which points for attention
        Coordinate GHG TT activities with the AFOLU Roadmap
        Coordinate with New Space TT
        Ensure continuity to earlier/existing missions
        Engage with and ensure CEOS expertise is used in WMO’s G3W and UNEP’s IMEO
        AOB
        Anything, anybody?
        Date of next GHG Task Team meeting