## Slide 1
Annex L1 & L2 GHG Product Development – status
CEOS/CGMS WG-climate GHG task-team
3rd workshop
Ruediger Lang / Dave Crisp
17 October 2023

## Slide 2: Annex L1 & L2 GHG Product Development - status
ACTION ID | ACTION DESCRIPTION | LEAD | CONTRIBUTORS | DUE DATE | IMPLEMENTATION STATUS | Way forward
Prod-1 | Document the performance of existing and near term L1 and L2 products and their ability to meet WGClimate needs for ECV and FCDRs | AC-VC / GSICS | EUM / NASA / JAXA / … | 2026 | Existing products: Document the existing L1 and L2 products in the ECV inventory( https://climatemonitoring.info/ecvinventory/) Most of the information there is from 2018, pre-OCO, pre-TROPOMI. With 14 years of data from GOSAT and 8 from OCO-2, it is time to start thinking about an FCDR for CO2 and CH4. Near term products: Algorithms for retrieval of XCO2 and XCH4 level-2 products to meet the requirements of future MVSes (e.g. CO2M mission and the need of the European GHG Monitoring and Verification Support (MVS) capacity in 2026, GOSAT-GW, …). Target 2026ff Scientific algorithm developments from their current performance status towards anthropogenic and/or biogenic emission monitoring needs of future MVSes. Target: Achieve required performance integrated in MVS by 2026ff. Adding additional instrument measurement capabilities (cloud imaging, aerosol background measurement, as well as trace gas measurements / NO2) to improve on CO2/CH4 accuracy and plume detection. Target: 2026ff. Develop improved bias correction schemes and improved uncertainty characterization (or avoid them all together making use of additional instrument and algorithm capacities). Target: 2026ff. Improve operational product robustness by improved resilience with respect to instrument performance and in order to support (and improve efficiency of) the transition from commissioning into operations and creation of FCDRs CDRs. Target: 2026 | Document existing products in ECV inventory Produce FCDRs and CDRs of exiting 10+ years time-series Monitor/report progress on performance of MVS capacities GHG products for MVS availability and performance Complementary instrument and product capacities: aerosol, clouds and NO2. Bias correction scheme status, progresses, evaluation, .. Complementary/multi algorithm schemes (bias reduction, error analysis and characterisation, monitoring and reduction, and resilience wrt instrument performance)

## Slide 3: Annex L1 & L2 GHG Product Development - status
ACTION ID | ACTION DESCRIPTION | LEAD | CONTRIBUTORS | DUE DATE | IMPLEMENTATION STATUS | Way forward
Prod-2 | Establish product accuracy, precision, resolution, and coverage requirements needed to meet the flux requirements on various scales | AC-VC / GSICS | EUM / ESA / … | 2026 | Implementation status PROD-1, CEOS white paper, CO2M MRD and associated scientific Studies (ESA spectral sizing study, SMARTCARB, studies performed to support the CO2M mission definition) Recent publications by Byrne et al. (https://doi.org/10.5194/essd-15-963-2023) and Worden et al. (https://doi.org/10.5194/acp-22-6811-2022) assess the limitations of existing l1 products for quantifying fluxes on national scales. Schuh et al. (https://doi.org/10.1016/j.rse.2021.112473) investigate the L2 product requirements on these scales from a more theoretical standpoint. Lie et al. (https://doi.org/10.1016/j.rse.2021.112625), Wu et al. (https://doi.org/10.5194/gmd-14-3633-2021), Kiel et al. (https://doi.org/10.1016/j.rse.2021.112314), Rißmann et al. (https://doi.org/10.5194/amt-15-6605-2022) and others assess the L2 requirements for large urban areas. Work by Nassar et al. (DOI 10.3389/frsen.2022.1028240), Cusworth et al. (https://doi.org/10.5194/acp-2018-741), Varon et al. (https://doi.org/10.5194/amt-11-5673-2018) and others are exploring the L1 and L2 requirements for point sources. | Report and evaluate existing mission requirements (synergies, complementarity) Collect lessons learned from these efforts to develop recommendations for future missions.
Prod-3 | Facilitate coordination between national and international development efforts to identify best practices and develop a prototype product | AC-VC / GSICS | ? | ? | Documentation of best practices for the development of L1 and L2 products: L1: pre-launch and on-orbit calibration methods, standards, and metadata needed to make products interoperable. L2: algorithm inter-comparisons, common data needs (e.g., solar spectra, Met data), and validation approaches. Draw on methods specified through current operational MVS developments and existing operational mission Cal/Val standards (e.g. GSICS) | To document best practices for the development of GHG products from current operational implementation efforts (Operational MVSes, GSICS, etc..)

## Slide 4: Annex L1 & L2 GHG Product Development - status
ACTION ID | ACTION DESCRIPTION | LEAD | CONTRIBUTORS | DUE DATE | IMPLEMENTATION STATUS | Way forward
Prod-4 | Pursue consistency in product content, format, units, variable names, etc. to facilitate interoperability | AC-VC / GSICS | EUM / … | 2026 | Propose usage of similar formats and product maintenance mechanisms (e.g. xml to netcdf/docs) to establish consistent formats across GHG mission products. Starting point: harmonization of level-1 products of same instrument class of European missions (e.g. GOME-1/2, SCIAMACHY, OMI, S4, S5p, S5) using netcdf-4 during recent product update cycles (and corresponding conversion of original / native formats to netcdf-4). Implementation status This has already broadly been established for the European sensors / missions (of the relevant class). Examples: Establish CO2M product formats based on existing relevant European netcdf product templates for level-1.Target: Q3 2022. DONE Propose use of already established C3S operational product principle parameter lists (similar to OCO-2 user friendly product) for level-2 GHG products (and apply / establish similar maintenance protocols and mechanisms (e.g. xml-> netcdf, docx/pdf). Done for CO2M | Done for CO2M, S5p, S5,… Expand to other missions

## Slide 5: Annex L1 & L2 GHG Product Development - status
ACTION ID | ACTION DESCRIPTION | LEAD | CONTRIBUTORS | DUE DATE | IMPLEMENTATION STATUS | Way forward
Prod-5 | Pursue traceability of data quality | AC-VC / GSICS UVNS | NASA / JAXA / EUM / ESA … | ongoing reproting | For L1 products: ongoing vicarious calibration campaigns using pseudo-invariant targets provide a means of cross calibrating the radiometric performance of these instruments. Ongoing efforts to standardize top-of-atmosphere solar fluxes and Lunar radiometric properties provide additional tools for assessing L1 products. For L2 products: observations of TCCON provide the primary transfer standard for tracing the space-based measurements to the WMO in situ standards. EM27/SUN and aircore networks are expending the coverage and providing new insights into the quality of the products. | Monitor status / scientific publications and validation reports from Campaigns (Railroad valley, …), GSICS (lunar and solar models) Networks (TCCON, COCCON, …) Report on status w.r.t. traceability to WMO standard (e.g. CO2M ground-based network product requirements document)
 | OCO-2 vs GOSAT vs S5p |  |  | 2023 | Active collaboration among the GOSAT/GOSAT-2, OCO-2/OCO-3, and TROPOMI calibration team, including routine telecons and annual Railroad Valley Vicarious Calibration campaigns contribute to the assessment of the L1 products from these missions and maintain a critical calibration resource for the community. Significant contributions to the TCCON, COCCON and AirCore networks by these missions has fostered strong collaboration and provided new tools for assessing the quality of the L2 products from these missions. | 
 | GOSAT vs TANSAT |  |  | 2023 | Ongoing | 
 | MicroCarb vs OCO-2/3 |  |  | 2025 | TBD | 
 | CO2M vs MicroCarb |  |  | 2026 | GSICS SNO / TCCON/COCCON | 
 | CO2M vs OCO-x |  |  | 2026 | GSICS SNO / TCCON/COCCON | 

## Slide 6: Annex L1 & L2 GHG Product Development - status
ACTION ID | ACTION DESCRIPTION | LEAD | CONTRIBUTORS | DUE DATE | IMPLEMENTATION STATUS | Way forward
Prod-6 | Coordinate algorithm inter-comparisons to improve accuracy and speed of retrieval algorithms | AC-VC / GSICS UVNS | EUM / … | 2026 | Annual Algorithm inter-comparison, technical interface meetings including standard experiments, designed to assess the performance of algorithms for specific challenges. Development and implementation of internal/external multiple-algorithm product processing frameworks both in- and outside of operational systems (e.g. CO2M) for continuous product and algorithm performance characterization (uncertainties), monitoring, inter-comparison and validation: Implementation of multi algorithm product processing based (online/offline) uncertainty and bias characterisation. Usage of on- and offline (Cal/Val) parallel processing and continuous inter-comparison, product quality monitoring approaches. | Internal and / or external algorithm comparisons Dedicated workshop / sessions (IWGGMS?) (round robins?) Annual Algorithm inter-comparison, technical interface meetings including (round robins) standard experiments Development of multi-algorithm offline/online processing frameworks

## Slide 7: Annex L1 & L2 GHG Product Development - status
ACTION ID | ACTION DESCRIPTION | LEAD | CONTRIBUTORS | DUE DATE | IMPLEMENTATION STATUS | Way forward
Prod-7 | Facilitate exchange and harmonization of approaches to calibration and retrieval challenges | AC-VC GSICS-UVNS | EUM / JAXA / NASA … | 2026 | Ongoing collaborations among the GOSAT/GOSAT-2, OCO-2, OCO-3 and TROPOMI calibration teams are providing new insights into on-orbit calibration challenges, opportunities and techniques. Documented impact of ground, ground to-orbit and in-flight calibration accuracy limits and changes on product performance. GSICS - UVNS spectrometer sub-group inter-calibration related activities addressing the following aspects for current and future GHG NIR/SWIR spectrometers. On-ground characterization (GSICS workshop ) Solar calibration Lunar calibration Inter-calibration (SNOs) Polarization Development of common methods for use of invariant targets & vicarious calibration sites with homogeneous surface over sufficiently large area. Usage of on- and offline (Cal/Val) parallel processing and continuous inter-comparison, product quality monitoring approaches. Production of ground-based network product requirements taking into account sensor equipment, station environment and satellite platform specific observation and collocation conditions Dedicated ground-based calibration data workshop (CO2M and MicroCarb) has been held adjacent to IWGGMS, Paris. 2023 | Expand or transfer established on-board and vicarious calibration methods into operations Expand on GSICS UVNS sub-group activities, methods and standards, and the provision of resources for operational monitoring Regular ground-based calibration data workshops

## Slide 8: Annex L1 & L2 GHG Product Development - status
ACTION ID | ACTION DESCRIPTION | LEAD | CONTRIBUTORS | DUE DATE | IMPLEMENTATION STATUS | Way forward
Prod-8 | Follow and provide recommendations on development of laboratory spectroscopy needs | AC-VC | ESA / GSICS-UVNS/VIS | ? | Completed/In progress: ESA activity on Improved Spectroscopy for Carbon Dioxide, Oxygen, and Water Vapour Satellite Measurements. Active participation in the development of the HITRAN database by the OCO-2/OCO-3 team and the TROPOMI team has led to improved accuracy of the CO2, CH4, O2, and H2O line lists. | Follow-up spectroscopy measurements Develop SI-traceable spectroscopy standards.
Prod-9 | Define types of data (calibration, L1, L2) that must be exchanged to enable the integration of space-based systems into a constellation. | AC-VC | GSICS-UVNS/VIS | ? | Identify data that needs to be exchanged to be able to combine GHG products from different sensors (to improve resolution and coverage and to ensure data product continuity from one mission to the next) Produce product port-folio currently established by Copernicus CO2 MVS (EC CO2 Task Force) | Compile data-type list required for synergistic use of data Copernicus MVS product port-folio (Q4 2024)
No redefinition of actions (content clarified by way of practical status reporting)
Probably incomplete capture of implementation status
  To be complemented with input from GHG team members and others