## Slide 1: WGClimate & GHG-TT Action Review
Libby Rose, Secretariat
Agenda Item 1.5

## Slide 2: WGClimate Action Status
29 Actions recorded at WGClimate-22
  23 Completed (79%)

## Slide 3: Final reminders on the following
WGClimate-22-08 | WGClimate members to let WGISS know of any other datasets which may benefit from a global recovery effort.
WGClimate-22-12 | WGClimate members interested in engaging on the definition of the UNFCCC Global Goal on Adaptation (GGA) Indicators should contact Maryam Navi (UNFCCC) with their specific area of interest. Maryam will connect any interested members with the relevant experts.
WGClimate-22-19 | Agencies interested in supporting post-doctoral researchers for RECCAP-3 to contact Ben Poulter.
Will now be closed

## Slide 4: WGClimate-22-03
The CEOS-MIM DB is now used for a couple of mission/instruments which were missing from WMO OSCAR
A broader discussion about the prime source of information for is still needed - will be addressed in item 3.2
Action to be closed?
WGClimate-22-03 | ECV/CDR Inventory team to review the information available on the CEOS MIM Database, and consider establishing linkage with the CDR Inventory.

## Slide 5: WGClimate-22-20 & -21
Continue to be discussed under UNFCCC TT
Continue discussion at future Asia-Pacific regional workshop
Can we close these actions?
WGClimate-22-20 | WGClimate, with UNFCCC and IPCC TFI, to consider establishing regional satellite data experts to advise national inventory compilers.
WGClimate-22-21 | WGClimate to consider how best to provide capacity development resources around using satellite data for national inventories. This could be done as an expansion to the CEOS GST Portal.

## Slide 6: GHG-TT Action Status
GHG-TT-05 (Feb 2025):
  12 Actions recorded
  11 Closed
  1 In progress
GHG-TT-06 (SIT TW, Sept 2025):
  12 Actions recorded
  4 Closed
  2 In progress
  6 Open

## Slide 7: GHG-TT open actions
GHG-05-04 | Hiroshi Suto to coordinate a discussion on vicarious calibration campaigns for CO2M.
GHG-06-01 | At the next GHG-TT meeting, items should be scheduled for: How to provide better access to GEO data for IMEO -> item 8.3 (IMEO) ESA/EUMETSAT’s planned cal/val supersite
GHG-06-02 | Richard Engelen to ensure IMEO has access to the ECMWF GHGSat data, and coordinate acquisitions with those made through UKSA’s quota.
GHG-06-03 | Yasjka Meijer to re-share the use cases document for feedback.
GHG-06-05 | Hiroshi Suto to share the whiteboard calibration dataset with CMA, to allow for alignment of the activities.
GHG-06-06 | Lu Zhang to share the details for the Gobi Desert calibration campaigns with the GHG-TT members.
GHG-06-08 | Libby Rose to coordinate a call between Marie-Helene Rio, Laura Lorenzoni, Dave Crisp, Yasjka Meijer and Abhishek Chatterjee regarding the gap in validation over the oceans.
GHG-06-09 | Izitiar Irakulis Loitxate to share the Methane Common Practices document with the IMEO Oil & Gas partners.
GHG-06-10 | Paul Green and Annmaire Eldering to define an action for Annex C around the L2/L4 intercomparison of methane plume measurements and corresponding emissions.