## Slide 1: Recovery Observatory (RO) Pilot Haiti Hurricane Matthew RO Status and Next Steps Presentation to WGD #13 March 11, 2020 A Collet, H de Boissezon, C Proy, CNES Jens Danzeglocke, DLR Deodato Tapete, Francesca Cigna , ASI Jean Philippe Malet, CNRS / EOST Enrico Ponte, CIMA Andrew Eddy, RO Secretary with contributions of CNIGS, Copernicus, WB Haiti
Committee on Earth Observation Satellites

## Slide 2
Haiti Recovery Observatory Pilot
  Progress since last WGD meeting
  Capacity building
  Legacy planning and wrap-up
  Conclusion
Outline

## Slide 3
RO Haïti Status Overview
  Triggering of the RO by CEOS Chair - December 22, 2016
  Mission #1 to Haiti - end January 2017 Definition of activities in Haiti
  …
  Mission #5 to Haiti 10 – 14 Dec 2018 technical review, training
  Mission #6 to Haiti - May 2019 3th User Workshop (PàP + Jérémie)
  Sept 2019 – Dec 2019 : troubled period but some work progress however
A Reminder of Haiti’s diversity
Hurricane Matthew
in Haïti
Oct 4th 2016

## Slide 4
Key elements since Last WGD mtg
Riots in Haiti canceled the capacity building mission scheduled last December
Finalization of the Mid Term Evaluation Report
New Copernicus Risk and Recovery Mapping activation : EMSN063
Focus on Capacity Building (Internships, Trainings)
Links with WB Haiti post Matthew projects on agriculture: Les Cayes (ended) and Nippes (ongoing)
Links with IADB Haiti projects on environment: Parc Macaya /Ground Movement (on going)
Continued engagement of space agencies (ASI, CNES, DLR, ESA, NASA, NOAA) for data provision and value adding products (NOAA available for health products elaboration)

## Slide 5
Vector Borne Disease risk | Health Minister/ OMS | NOAA | L8, Images NOAA + statistic needs
Air pollution | ONEV / Ministère Santé | NASA | S5P Tropomi on going discussion
RO Thematic Products
Les Produits
 | Product | Key user | CEOS | Sat. Data
 | Buildings Mapping | CIAT / Planning Ministry | CNES/SERTIT, Copernicus EMS R&R | Pléiades, WorldView-3
 | Terrain Motion Change Detection | BME / URGeo | ASI, CNES/EOST | COSMO-SkyMed, Pléiades, Spot 6/7, TerraSAR-X
 | Watershed / Flood | ONEV / Agriculture Ministry | ASI/CIMA Foundation | Pléiades, COSMO-SkyMed
 | Agriculture | Agriculture Ministry | Copernicus EMS R&R | Sentinel-2, Spot 6/7, GeoEye-1, WorldView-2
 | Macaya Park Monitoring | ANAP / ONEV / Environment Ministry | Copernicus EMS R&R, CNES/SERTIT | Spot 6/7
 | Environmental Impact | ONEV / Environment Ministry | Copernicus EMS R&R | Sentinel-2, Spot 6/7, Pléiades, WorldView-2
 | Land Use | All | CNIGS, CNES | Sentinel-2
Notes: Rencontre avec le min de la Sante Haïtien. Courier officiel pour recup stats d’occurrence des maladies (dengue….)
Air pollution: meeting RO / NASA fait et mise en contact avec le CIAT et délégation européenne . Echange en cours

## Slide 6
RO Timeline
Disaster
Ouragan Mathieu Haïti
04/10/2016
Opening
Du RO Haïti par le CEOS
22/12/2016
01
2017
Q1
Q2
Q3
Q4
G-RO
First meeting
Q3 2018
03
2018
Q1
Q2
Q3
Q4
Evaluation
RO Haïti
Q4 2019
04
Today
Q1 2020
2019
Q1
Q2
Q3
Q4
REX
Feedback
Q3 2020
05
2020
Q1
Q2
Q3
Q4
Q4
First contacts
31 Jan – 3 Fev
M1
Workshop 1 (PàP)
29 Mai – 2 Juin
M2
ROOP
Du RO Haïti par le CEOS
Q3 2017
02
Technical Review
5-8 Dec
M3
Workshop 2 (PàP, Cayes)
8 - 11 Mai
M4
Training and Revue
10-14 Dec
M5
Workshop 3 (PàP, Jérémie)
26 Avr - 4 Mai
M6
Landuse Training
Q2
M7
RO post Matthew
Definition and
Implementation
RO post Matthew
Commissionning
RO post Matthew Operations
Lessons learnt for G-RO
RO legs
G-RO concept
Closing workshop
Q2 : PàP, Jérémie
M8

## Slide 7
Capacity Building 2020
Links with WB Haiti post Matthew project: Agricultural resilience in Nippes
  January Training of two Haitian partners (CNIGS) in Montpellier (France) at CIRAD on Land Use
January – April 4 Internships ongoing at CNIGS (work with CNES/SERTIT)
  Urbanization of agricultural areas: issues and challenges in Jérémie
  Analysis of the mutation of agricultural areas: Dame Marie and Jérémie
  Analysis of the dynamics of woodland cover and coastal erosion: Dame Marie
March – August 1 Internship by a Haitian student in France on Land-Use :
  "Characterization of land use in an agricultural environment in the Dame-Marie sector (Haiti) by the application of the Moringa chain".
Links with IADB Haiti projects : Macaya Park / Ground Movement
  March / April Training of two Haitian partners (CNIGS) in Italy at ASI with IADB & Macaya Park input (more info on ASI section)

## Slide 8
Copernicus EMS RRM
EMSN 051 “ Environment” (2018)
Area : Macaya Park, Port Salut, Les Cayes, Jérémie, Pointe Abacou and Costal line.
Agricultural activities
Coastal Line evolution
Macaya Park classification and monitoring forest damage
Mangrove monitoring
CNIGS/CIAT/ONEV have asked for two other RRM activations mid 2019 on two products, through EU delegation : Activation EMSN 063 launched in January 2020
Result expected beginning of April 2020.
  Agricultural monitoring
  Macaya Park land use map and wooden areas monitoring

## Slide 9
CNRS EOST / CNES
EOST RO activities on landslide mapping: EOST/CNES
On going Landslide Inventory on whole optical RO archive over 2 main areas

## Slide 10: POST-MATTHEWS EO DERIVED LANDSLIDE INVENTORY: FROM INVENTORY TO SUSCEPTIBILITY MAP
Previous works: ALADIM derived inventory from SPOT6/7 images and aggregated indicators
[0.0 – 0.1[
[0.1 – 0.4[
[0.4 – 0.7[
[0.7 – 0.9[
[0.9 – 1.0]
Number of landslides: > 7000
Landslide surface: 4km2
Landslide size (m2)
Landslide size (m2)
Landslide density (over 1 km2 mesh)

## Slide 11: POST-MATTHEWS EO DERIVED LANDSLIDE INVENTORY: FROM INVENTORY TO SUSCEPTIBILITY MAP
Les Anglais cordillera – SPOT 6
Les Anglais cordillera – SPOT 7
Space-based inventory from ALADIM
Landslide properties and rainfall properties (ex. of recent extreme rainfall)
Previous works: scaling laws – rainfall pattern vs. landslide size

## Slide 12: POST-MATTHEWS EO DERIVED LANDSLIDE INVENTORY: FROM INVENTORY TO SUSCEPTIBILITY MAP
Project 2020: sponsored by CNES
Provide a final version quality controlled of the optical derived landslide inventory for the full Spot6/7 coverage
Compare the optical derived landslide inventory to InSAR detection (based on the processing by ASI)
Propose a landslide susceptibility model (eg. a map presenting the possible spatial occurrence of landslides) for the region using a Random Forest classifier, and few exploratory variables (relief, geology, landcover)
Train Haitian users on Aladim/GEP and on the susceptibility modelling

## Slide 13
DLR – TerraSAR data
The 14th coverage starts in March 2020.
There are 170 scenes available on the TSX Supersites Portal of DLR: https://code-de.org/download/tsx-supersites/Haiti/ (access for registered science users)
There are 13 TerraSAR-X coverages of the whole area :
Ascending + Descending orbit
4 full coverages in 2019, one more between Dec 2019 and Feb 2020
Notes: Les italiens ont récupéré les donnés

## Slide 14
ASI – Terrain motion products
ASI’s scientific goal  To develop experimental scientific products tailored to obtain useful information on ground stability and motions for target areas of the RO
Capacity building
Apr-May 2019: scientific seminars on SAR data and applications held at LNBTP-Haïti during field mission
Mar-Apr 2020: visit of 2 CNIGS staff members in ASI in Rome, to learn how to process Sentinel-1 data in GEP
Satellite data analysis and ground truth activities
COSMO-SkyMed acquisition campaign with VHR SAR over 3 hotspots (Jeremie, Camp-Perrin, Carriere Arniquet), started in Dec 2017
X-band SAR change detection using COSMO-SkyMed and TerraSAR-X
Sentinel-1 data processing with ESA GEP hosted services, to create interferograms, amplitude change and coherence maps
Technical mission in Haïti in Apr-May 2019 (field checks, data validation, discussion with stakeholders)
Upcoming dissemination
Jun-Jul 2020: presentations at IGARSS and FRINGE 2020
COSMO-SkyMed SpotLight

## Slide 15
ASI – Terrain motion products
Dissemination via ESA GEP Blog
“Observing surface deformation in Haiti after Hurricane Matthew with Sentinel-1 in GEP”
https://discuss.terradue.com/t/observing-surface-deformation-in-haiti-after-hurricane-matthew-with-sentinel-1-in-gep/845

## Slide 16
ASI – Terrain motion products
Dissemination via RO website

## Slide 17
CIMA – RASOR Training
The training expected in April will cover 3 main components:
1.
2.
3.
Hazard:
Uploading and generating new hazard layer
Exposure and vulnerability:
Uploading different exposure shapefile and associating specific RASOR attributions and different vulnerability curves
Impact evaluation:
Generating impact reports and extrapolating the most relevant results

## Slide 18
Training at ASI and CIMA (RASOR) for 2 CNIGS experts
  Link with EOST using ALADIM on GEP and discuss methodologies
  To be rescheduled
Training Session end of May
  Training for Land Use Land Cover from S2 data based on IOTA2 tool
    The IOTA2 chain should be completely understood by the Haitian team
    After this training they should be able to operate IOTA2 S2 chain by themselves Planned : LULC map made by Haitian at the end of training
  => Following previous training made at CIRAD and ASI/RASOR
  Extra : Charter PM training
Planned events in 2020

## Slide 19
User Workshops #4
June 2020
First week of June 2020 :
  Opening of the 2020 cyclonic season
  High level presentation of RO achievements
Final User Workshops in Jérémie & Port-au-Prince
  RO products analysis and last delivery
  Haiti RO closure preparation
  Lessons learned
  RO Legacy preparation
Steering Committee # 6

## Slide 20
Project tasks in 2020
Development plan for Thematic products regularly updated with Haitians
8 New Optical images since September : Pléiades (being integrated on GEP)
Integration into the Web server of new products (25) and experience feedback from Value Adders

## Slide 21
RO Pilot ends in 2020 – presentation to CEOS plenary Q4 2020
RO legacy in Haiti will consist in EO data and products database and capacity building with Haitian organizations:
  Discussion with CNIGS to determine how RO database can be transferred to HaitiData.org
Significant work is being performed to ensure success is consolidated – Effort underway to identify specific projects which could fund follow-on efforts that build on RO success:
  National Environmental System Indicators (SIE) with UNEP
  Resilient agriculture projects with WB in Nippes and Les Cayes
  Forestry and Environment (mangrove) projects with IADB
Lessons learned for scalable and replicable RO
Legacy Considerations

## Slide 22
Troubled period in Haiti delayed the capacity building roadmap. However due to our strong links with WB projects and Haitian community, Haitians partners have benefited from training in Europe and will continue to do so with ASI and CIMA. So it does not affect the final planning for the moment.
In this final phase of Capacity building the last product are not forgotten and Copernicus EMS063 will respond to the last request from previous workshop (from several mayors).
The next mission will be focused on high-level and decision makers final workshops, as well as outreach linked to the cyclonic season opening.
Conclusions

## Slide 23
Thank you
Merci
Mesi