## WGDisasters_Actions
CEOS WGDisasters Actions
Action Status as of: WGD T30 [7 December 2021]
Action # | Action | Actionee | Due | Status | Comments
T30/1 | Provide names to GSNL for membership in Steering Committee and Management Committee. | Pierric Ferrier | WGD17 | Closed | Ex officio WGD chair for Steering Committee and DCT chair for Management Committee.
M16/1 | International Charter-CEOS WGDisasters relations. Contact the Charter ES and address the following points: Access to the Charter data [Clarify that the person to submit the request to the Charter is a CEOS WGDis activity lead; Increase the data request submission window to more than 10 days; Mention clearly in that the response from the Charter lead should be received within 2 weeks after the submission request; Complete the “procedure for CEOS WGDis to access Charter data” accordingly and have it agreed by the Charter ES], VA provision to the Charter [WGDis activity leads can provide VA products to the Charter Project Manager by contacting them by email (copying the Charter Executive Secretariat). The Charter Project Manager email for a given activation is available on COS-2.that the person to submit the request to the Charter is a CEOS WGDis activity lead; Confirm this with the Charter ES and Complete the “procedure for CEOS WGDis to access Charter data” accordingly and have it agreed by the Charter ES]. | Pierric Ferrier, Dorella Papadopoulou, Jens Danzeglocke, Dave Hodgson, Dave Borges | WGD17 | Open | Now in Charter hands, Dave Hodgson will return to Charter Exucutive to close out.
M16/2 | Develop proposal for addition of CEOS SEO flood mapping tool to International Charter activation pages. Schedule exploratory meeting between CEOS WGDisasters, SEO and International Charter Board. | Brian Killough, Dave Borges, Dave Hodgson, Pierric Ferrier | Update at Telcon 31 | Open | Originally for WGD17. A meeting was held on December 20 to discuss potential SEO contributions to the Charter. The Charter did not think that PM's and users would desire to run Jupyter notebooks or perform their own analyses for disasters. That said, CEOS offered to provide a "service" that includes the development of flood products at the time of the activation and Jupyter notebook tools to monitor flood recovery after the activation period is completed. We are currently working on the release of updated Jupyter notebooks along with tutorials and documentation. Once these resources are completed (estimate April 2022) we would suggest another interaction with the Charter to discuss next-steps and whether these resources could/should be part of the Charter.
M16/3 | Josh Johnston, Peter Moore and Philppe Bally to meet and follow up on further ESA support of Wildfire Pilot activities. | Josh Johnston, Peter Moore, Philippe Bally | WGD17 | Closed | E-mail discussion initiated week of 28 Feb.
M16/4 | Seismic Demonstrator team to develop a next steps and recommendations document to be shared with WGDisasters. | Dorella Papadopoulou, Philippe Bally | WGD17 - delayed to Q2 2022 (end June) | Open
M16/5 | GeoHazards Lab team to send Andrew Eddy their activity's end user tracking spreadsheet. | Michael Foumelis | WGD17 | Closed | Provided 11 March.
M16/6 | Determine if an official Open Geospatial Consortium (OGC) member is already, or could become, a WGDisasters member and liason between WGDisasters/WGISS. | Dave Borges, Rob Woodcock | WGD17 | Closed | Dave Borges will serve as liaison to OGC. There is no "formal" OGC membership in WGISS either, although the OGC is well represented.
M16/7 | WGDisasters to contribute to the GEO Work Programme Mapping Exercise Survey (in the context of GEO EO4DRM Community Activity, which is represented by CEOS WGDisasters). | Pierric Ferrier, Andrew Eddy, Dave Borges, Rui Kotani | WGD17 | Closed | Meeeting has taken place with Ryui Kotani and contribution is initiated.
M16/8 | WGCapD requests brief, specific summary of needs and requirements from the Recovery Observatory Demonstrator Team. | Andrew Eddy, Helene de Boissezon, Nancy Searby | WGD17 | Closed | Action completed with briefing of new UNOOSA chair and initiation of joint activity in Workplan.
M16/9 | Volcano Demonstrator to conduct an internal analysis and develop a review of progress to date, as well as a Next Steps document to be shared with WGDisasters. | Mike Poland, Susi Ebmeier | WGD19 | Open | Initial discussions at leadership level of pilot have taken place.
T29/1 | Distribute latest DCT membership list to review for accuracy and completeness. | Dave Borges | WGD16 | Closed
T29/2 | Request with finite deadline to be distributed to WGDisasters activity leads to determine capability to provision VA data to the Charter and expectation of receiving data from the Charter. | Pierric Ferrier | WGD16 | Closed
T29/3 | Contact Charter and provide offical WGDisasters documentation clearly defining WGDisasters capabilites to support/request Charter data/VA products during activations. | Pierric Ferrier | WGD17 | Closed | Captured in. M16/1.
T29/4 | Flood Pilot leads to follow up with CNES staff interested in joining Flood Pilot, understand interests and potentially secure new EAIL accounts. | Dave Borges, Guy Schumman, Maggi Glasscoe | WGD16 | Closed
M15/1 | Data Coordination Team to create a DCT Role description document. Document written and finalized. | Pierric Ferrier | T29 | Closed
M15/2 | Determine which WGDisasters activites are willing and capable of providing value added products to the International Charter (closed). Collect all relevant example products - still need one agency to provide example of products. Closed and related actions rolled into M16/1. | Pierric Ferrier, Dave Borges | WGD16 | Closed
M15/3 | WGDisasters to work with CEOS MIM Team to address Disasters applications feature concept presented by Ivan Petiteville. | Ivan Petiteville, Pierric Ferrier, Andrew Eddy, Dave Borges | T30 | Closed | Discussed at T30 and WGD concluded best approach is to wait for Symbios to provide an outline of Disasters information requested for MIM and each agency to respond to requests. NO agency volunteered to lead or join a small reflection group on this topic.
M15/4 | Flood Pilot co-leads to coordinate with ASI regarding the potential to add additional SAR data to the Flood Pilot activities. Data provision procedures/requirements received from ASI and shared with Flood Pilot team for awareness. | Guy Schumann, Dave Borges, Mitch Goldberg, Antonio Montuori, Simona Zoffoli | T29 | Closed
M15/5 | Volcano Demonstrator co-leads to follow up with CSA regarding RSAT-2 data request. CSA has been sent prioritized request list for Volcano Demonstrator AOIs. | Susi Ebmeier, Mike Poland, Dave Borges, Yves Crevier | T29 | Closed
M15/6 | If Nicaragua Supersite proposal is accepted, Landslide Pilot team has indicated interest in collaborating with the Supersite team in terms of intersecting hazards and risk. | Dalia Kirschbaum, Stefano Salvi, Dave Borges | T29 | Closed
M15/7 | WGCapD requested the Training Calendar be shared with WGDisasters, along with a request for WGDisasters to contribute relevant content. | Dave Borges, Nancy Searby | T29 | Closed
T28/1 | Volcano Demonstrator Team to make case for International Charter to release SLC complex data when associated data is shared during Charter activations. Remains open, direct contact with Charter in the context of this request still outstanding. | Mike Poland, Susi Ebmeier, Dave Hodgson | WGD17 | Closed | No need to pursue further a tthius time - email S Ebmaier 3 March.
T28/2 | Confirm status of new Nicaragua Supersite Proposal. Supersite proposal approved and notice distributed. | Stefano Salvi | WGD15 | Closed | ASI, DLR and CNES should provide a final decision. All their requests were accepted in the revised proposal. There is still one pending side issue, which is if CONAE intends to support this Supersite (actually also other ones). Given the uncertainty, at present they have not requested SAOCOM images, but if CONAE wants to make them available we can select a site later. -Stefano Salvi, 3/4/21
T28/3 | Provide GEO GSNL instructions and/or good practice documentation to new Supersite communities. In the past, a document was developed, but should be updated to provide instruction regarding licensed data access procedures. | Stefano Salvi | WGD17 | Open | Still pending. -Stefano Salvi, 3/4/21
T28/4 | Wildfire Pilot Co-Leads to work with Marie-Claire Greening (incoming CEO) to identify relevant connections with CEOS WGClimate ECV Inventory and Gap Analysis Team. Connections identified and outreach sent. | Josh Johnston, Marie-Claire Greening | WGD15 | Closed
T28/5 | Amy Parker represents Earth Observation Australia, which encompasses all AU agencies and research sector stakeholders related to Earth observations. Determine appropriate method of engagement with new Wildfire Pilot efforts. Wildfire Pilot in contact with Amy Parker, discussions occuring. | Amy Parker, Josh Johnston | WGD15 | Closed
T28/6 | WGDisasters Data Coordination Team (DCT) Lead Vacancy. Pierric Ferrier will become WGDisasters Chair at CEOS Plenary 2021, and has requested WGDisasters identify a replacement DCT Lead soonest. Pierric Ferrier agreed to maintain DCT Lead Role until Summer 2022. A replacement DCT Lead still needs to be identified by this time. | Pierric Ferrier, Dave Borges, David Green | T29 | Closed
T28/7 | Review current DCT tracking process and methodology and historical data quota tracking process. Determine if new DCT methodology is necessary. | Pierric Ferrier | WGD17 | Closed
M14/1 | WGDisasters Chair Team to reach out to WG Activity Leads and confirm all WGDisasters Deliverables and projected completion dates remain accurate. Update CEOS Deliverables Tracking Tool where necessary. Completed prior to WGD T28. | Dave Borges, WG Activity Leads | T28 | Closed
M14/2 | Flood Pilot Co-Leads to coordinate with DCT and CONAE Flood Pilot Team members to understand and capture SAOCOM data sharing requirements. Flood Pilot Co-Leads to develop Pilot Data Availability spreadsheet. Pilot Data Call developed and distributed. CONAE and CSA data sharing procedures under development. | Guy Schumann, Andrew Molthan, Mitch Goldberg, Pierric Ferrier, Marcelo Quirno, Alvaro Soldano, Ana Medico, Maryse Kalemkarian | WGD17 | Open
M14/3 | Recovery Observatory Demonstrator and WGCapD Chair teams have existing joint WG deliverables that require clarification in terms of specific joint activites and timeline. Dedicated meeting to be scheduled early 2021. WGCapD Deliverable closed (overcome by events). | Helene de Boissezon, Andrew Eddy, Agwilh Collet, Nancy Searby, Christine Mataya (WGCapD Chair Team) | WGD15 | Closed
M14/4 | Regarding the SCO presentation given by Helene de Boissezon during WGD14, all WGDisasters Activity Leads to review SCO presentaiton and respond if any collaboration opportunities exist. Reminder sent to WGDisasters. Action closed. | WGDisasters Activity Leads | WGD15 | Closed
M14/5 | WGDisasters to address and confirm cooperation and data/product sharing procedures proposed by the International Charter. A dedicated meeting between the two groups should be arranged to allow discussion and confirmation of details. Closed and updated actions rolled into action M16/1. | Pierric Ferrier, Dave Borges, David Green, Dave Hodgsen, Dorella Papadopoulou | WGD16 | Closed
M14/6 | Radarsat data availability for GSNL Supersites needs to be clarified and/or confirmed. Yves Crevier confirmed CSA is in a data contribution black out for now due to the following reasons: No access to RSAT 2 data planning other than through commerical approachs, no processing contract for the RSAT 2 data archive, and RCM soley focused on Goernment of Canada needs at this time. CSA is in process of provding data to the Landslide Demonstrator and Flood Pilot teams (these activities include AOIs within Canadian borders). | Stefano Salvi, Yves Crevier | WGD15 | Closed
M14/7 | CEOS WGDisasters to work with UNGGIM WG-Disasters to review specific collaboration areas presented during WGDisasters-14, and distinguish roles and opportunities of both CEOS and GEO DRR WG with UNGGIM. GGIM WG-Disasters Work Plan updated to include collaboration areas with CEOS WGDisasters. | Dave Borges, Simone Lloyd | WGD15 | Closed
M14/8 | WGDisasters Wildfire Pilot Scoping: Invitation to be distributed to WGDisasters for member Agencies and partners to express interest in participating in this new Pilot. Schedule a dedicated meeting to discuss and confirm next steps and request feedback/input to draft Wildfire Pilot proposal. Action completed. Distribute final Wildfire Pilot IP to CEOS community prior to SIT-36. Pilot IP distributed and endorsed at CEOS SIT-36. | Dave Borges, Josh Johnston, other Agency members to be determined | WGD15 | Closed
T27/1 | CNES and ASI to determine ability to support potential new China Supersite, based on new revised proposal. China Supersite approved. Action closed. | Pierric Ferrier, Simona Zoffoli | T28 | Closed
M13/1 | GEO/LEO/SAR Flood Pilot: Confirm Pilot Team participants, based on interest expressed. Pilot Case Study Criteria specifics to be distributed to Pilot Team. Pilot Team has been established. Case Studies are developing. To be presented for approval during SIT TW 2020. | Andrew Molthan, Mitch Goldberg, Guy Schumann | T27 | Closed
M13/2 | GSNL / DCT Dedicated Meeting to address outstanding actions. Decisions required: Renewal of support to Iceland, Southern Andes, Virunga (Quota increase of 100 images was requested after report was delivered) Supersites. Support to the China EQ, Kamchatka/Kuriles Supersites. This meeting was scheduled, took place, and relevant GSNL decisions were made. | Stefano Salvi, Pierric Ferrier, David Green, Dave Borges, DCT | T27 | Closed
M13/3 | Distribute latest CEOS ARD Strategy document and SAR Product Family Specification (PFS) document to Geohazards Lab Co-Leads and the entire WG. Identify if PFS development is relevant to Geohazards Lab activities. Provide feedback to CEOS ARD Strategy Team and CEOS SIT Chair. Dave Borges distributed the above documentaiton to WGDisasters for review, and shared feedback received with SIT Chair Team. | Dave Borges, Dorella Papadopoulou | T27 | Closed
M12/3 | Consolidate WG Activity membership lists, request membership lists from Activities that have not provided these. Create a list of target user communities the WG works with by requesting Activity leads to share top five, or key engagement communities/stakeholders each Activity engages. Share consolidated prodcut at next Telecon. Action completed. | Dave Borges, Activity Leads | T28 | Closed
M12/5 | Report on web statistics at each meeting. Determine methodology to convey website traffic trends over time. Site traffic trend graphics developed and included in meeting minutes. | Andrew Eddy | Recurring | Open
M12/7 | Submit formal proposal to CNES to place Pleiades data on the GEP, and allow online processing services for GSNL. Process to authorize GEP community users to access Pleiades data in the processing environment has been defined, based on authentication and authorization. Future telecon scheduled, and feedback will be provided to the WG. Action completed and closed based on feedback from Dorella Papadopoulou. | Stefano Salvi, Philippe Bally | WGD-14 | Closed
M12/13 | Identify requirements for RSAT-1/2 data and compile. Action closed based on feedback from Andrew Eddy. Request was distributed to WG Activity Leads to identify RSAT-1/2 requirements/value. Feedback was shared with Yves Crevier. | Andrew Eddy (existing requirements from past actions); Activity Leads (new requirements not currently listed in actions); Liaise with Yves Crevier | T27 | Closed
M12/16 | Articulate the open review process (post Santorini, to possibly be reopened) as an activity. Dorella to form small group to address scope. http://esamultimedia.esa.int/docs/EarthObservation/Geohazards/esa-geo-hzrd-2012.pdf Dorella to recirculate final versions of five Google Docs on thematic hazards, requesting feedback on objectives and requirements. Dorella redistributed relevant content during T27. Action closed. | Phillipe Bally, Dorella Papadopoulou | T27 | Closed
M12/18 | Complete EO4DRM Strategy document (Google Doc Link) update based on ToC distributed by Andrew Eddy prior to T26. Complete assignment of writing sections Dave Borges to distribute monthly call schedule where progress will be reviewed. Finalize document and share to CEOS SIT TW website before SIT TW second week of Sept 2020. Document completed and shared for review at SIT TW and endorsement at Plenary 2020 | EO Strategy small reflection team | WGD-14 | Closed
M12/20 | Assess with NASA/USGS/NOAA/CSA the concept of combination of geodetic data and remote sensing data, models and tools for assessing displacements consistent with disaster risks associated with intensive movements including earthquakes and tsunami in the vicinity of exposed and vulnerable communities, lifelines and economies. Evaluate the interest of the participating agencies. Assessment report to be provided. Pierric Ferrier indicates this action should be closed. | Catherine Proy, CNES, NASA, USGS, NOAA, CSA | T27 | Closed
M12/21 | Make presentation on SCO at next meeting in context of developing climate activity within the group – linkages to Coastal change effort within CEOS. Presentation given during WGD14. | Helene de Boissezon | WGD-14 | Closed
M12/22 | Ask GEO-GLAM to brief next meeting on their successful 'Data to Decisions' process vision. GEO-GLAM unavailable at last several WGDisasters meetings. Will continue to try to organize participation, but action is closed. | Dave Borges | T28 | Closed
M11/7 | Circulate a data sheet on the NovaSAR data specs and information on processing tools. Dave Hodgson shared that this action is still on hold, pending more comprehensive decision regarding access to CEOS broadly. Will update WG when materials become available. Noted by Dave Hodgson, NovaSAR data sheet not available at this time, and it is unknown if or when this might change. Action closed. | David Hodgson, Amy Parker | T28 | Closed
M11/9 | Articulate an informal guideline document to explain what each agency is concerned about for proposal drafters Jens shared relevant emails with DCT. Current recommendation TBD. Pierric to distribute three page document detailing useful guidelines and ask for WG comments. Pierric recommended requesting any relevant CSA contributions before closing this action and distributing final documnet version at WGD-14. Dave Borges to send another request to Yves Crevier/CSA for any feedback. Exisiting content to be distributed to the WG as is. | DCT Chair Lead, representative from GSNL, Pilots | T28 | Closed
M10/18 | Pilot and demonstrator leads to review website updates and provides links to further examples/documents, as well as more pictures to illustrate work. Combined with former action M5/19: Inform Chair of relevant outreach, programmatic events, publications and all other activities. | Andrew Eddy, Activity Leads | Recurring | Open
M5/19 | Inform WGD Chair of relevant outreach, programmatic events, publications and all other activities. Merged with recurring action M10/18. | Activity Leads | Recurring | Closed