## StatusSummary
WGISS Action Item Status Summary as of June-29-2006
| Due: Pre-June-2006 | Due: June-2006 | Due: WGISS-22 | CLOSED | Total
WGISS-18 | 1 | 0 | 0 | 1 | 2
WGISS-19 | 2 | 0 | 0 | 3 | 5
WGISS-20 | 3 | 1 | 5 | 19 | 28
WGISS-21 | 1 | 9 | 6 | 7 | 23
Total | 7 | 10 | 11 | 30 | 58
WGISS Action Item Status Summary as of September 15, 2006
| Due: Pre-WGISS-22 | Due: WGISS-22 | Due: Post WGISS-22 | CLOSED | Total
WGISS-18 | 1 | 0 | 0 | 1 | 2
WGISS-19 | 2 | 0 | 0 | 3 | 5
WGISS-20 | 9 | 0 | 0 | 19 | 28
WGISS-21 | 7 | 5 | 0 | 11 | 23
WGISS-22 | 0 | 0 | 27 | 0 | 27
Total | 19 | 5 | 27 | 34 | 85
WGISS Action Item Status Summary as of October 27 2006
| Due: WGISS-22 | Due: Oct-2006 | Due: Post Oct-2006 | CLOSED | Total
WGISS-18 | 1 | 0 | 0 | 1 | 2
WGISS-19 | 2 | 0 | 0 | 3 | 5
WGISS-20 | 6 | 0 | 0 | 22 | 28
WGISS-21 | 7 | 0 | 1 | 15 | 23
WGISS-22 | 0 | 14 | 13 | 8 | 35
Total | 16 | 14 | 14 | 49 | 93

## WGISS-25 Actions
Last Updated 26 September, 2008 by M. Piepgrass
No. | WGISS-25 Action Items Last Updated 26 September 2008 by M. Piepgrass Action | Who | By | Open/CLOSED | Status
25-1 | Martha will support Kengo to fulfill the CEOS IP CL-21 Action | Martha Maiden | 2008-05-01 | Closed | The GCOS ECVs provided by CEOS agencies have been made available on a protal in the CEOS IDN.
25-2 | Determine how to post on WGISS website the WGISS-GEO support information | Ken McDonald & Pakorn | 2008-05-01 | Closed | Incorporated into wgiss 26 action
25-3 | Provide a demonstration of a prototype LSI portal at WGISS-26 | Lyn Oleson | WGISS 26 | Closed
25-4 | Present a plan with milestones for continued enhancement and development of an LSI portal | Lyn Oleson | WGISS 26 | Closed | Ongoing in LSI interest group
25-5 | Contact WGISS all with information with request for interest in LSI Interest Group and LSI Portal Project | Lyn Oleson | 2008-04-02 | Closed
25-6 | Devise a way to capture WGISS lessons learned and best practices. | Karen Moe & Ken McDonald | 2008-05-01 | Closed | Developed a proposal for capturing WGISS lessons learned to present at WGISS-26
25-7 | Report to subgroup chair whether your task team should become an interest group, a project, or an interest group with one or more projects. | Task Team Leaders | 2008-04-02 | Closed | In process of moving to Interest Groups and Projects
25-8 | Get back to Pakorn about GEO action CL-06-02_14. | Ken McDonald | 2008-03-05 | Closed | Climate Diagnostics Portal created by Lola Olsen working with SBA lead Mitch Goldberg. GEO action is closed.
25-9 | Get back to Pakorn about GEO action HE-06-03_02 | Karen Moe | 2008-03-05 | Closed
25-10 | Investigate HE-06-03_3 and get back to Pakorn | Nataliia Kussul | 2008-03-05 | Closed
25-11 | Contact Murielle Lafaye on GEO task HE-07-01_1 and ask specifically what her interest in WGISS participation might be | Paul Kopp | 2008-03-04 | Closed | I had a conversation with Murielle Lafaye about the GEO task HE-07-01_1. She would be happy to get support from WGISS, namely through the IDN, at least as a first step. A second step could be to set up a dedicated IDN portal. 04-Mar-08
25-12 | Get back to Pakorn on GEO task AR-07-02_1 and DA-07-04_1 | Terence vanZyl | 2008-03-05 | Closed
25-13 | Send text to Pakorn for DA-07-03_5 | Lyn Oleson | 2008-03-05 | Closed
25-14 | Contact Doug Nebert concerning DA-06-04 | Pakorn Apaphant & Karen Moe | 2008-03-05 | Closed | Task was revised to coordinate an inventory with task AR-06-05/GEO Clearinghouse and DA-06-07/Web Portal/Registries/Clearinghouse. This will be facilitated through the recommendation of a minimum set of standard interfaces and metadata standards.
25-15 | Send out CEOS Interoperability Handbook version 1.1 in "Track Changes" format. | Paul Kopp | 2008-03-08 | Closed
25-16 | Review issue 1.1 of CEOS Interoperability Handbook and give comments to Paul Kopp | WGISS-all | 2008-05-08 | Closed
25-17 | Provide a process to review and update WGISS website and 5-Year Plan | WGISS Exec and WISP chair | 2008-05-01 | Closed
25-18 | ACC (Hilsenrath) and WGISS (Maiden, Moe) to discuss joint ACC/WGSS areas of interest and expertise to determine specific joint near-term activities. Working to include CEOS member Atmospheric Composition assets into SERVIR is one possibility. Another is WGISS inputs into ACC short-term projects. | Hilsenrath, Maiden, Moe | 2008-04-02 | Closed
25-19 | Review all the presentations from the joint sessions to identify possible activities or topics to explore by WGISS, subgroups, interest groups, or projects. | WGISS exec | 2008-04-02 | Closed

## WGISS-26 Actions
No. | WGISS-26 Action Items Last Updated 26 September 2008 by M. Piepgrass Action | Who | By | Open/ Closed | Status
26-1 | Decide whether to follow the CEOS-style website. | WGISS-All | 2008-09-26 | closed | All agreed.
26-2 | Develop a plan to post Best Practices/Lessons Learned/other items on the WGISS website when it has been redesigned. Establish the requirements for internal and external lessons learned, best practices, and WGISS-GEO support information. | Ken, Karen, Yonsook | 2009-01-15 | Open
26-3 | Develop a plan with milestones to implement the WGISS website. | Ken, SEO | 2008-12-15 | Open
26-4 | Identify and contact the agencies/individuals with which WGISS projects can intercact to provide services during disasters. Use GRID and Wenchuan Earthquake experience and recommendations to outline a clear process. (This is a contribution to DI-06-09). | Lorant (organizer) Nataliia, Guoqing, Pakorn | WGISS-27 | Open
26-5 | Send the WAG Architecture (draft) document to WGISS-All for feedback. | Paul Kopp | 2008-10-15 | Open
26-6 | Send the GEOSS Sensor Web Workshop report to WGISS-All. | Terence | 2008-10-01 | Open
26-7 | Send Technology Infusion report to WGISS-All. | Karen | 2008-10-01 | closed | Sent to WGISS-All October 2
26-8 | Determine milestones for acceptance and publication of new Climate Diagnostics Portal; must be published for CEOS Plenary. | Lola, Dingsheng | 2008-10-05 | Open
26-9 | Send URL for Climate Diagnostics Portal to WGISS-All; include response deadline. | Lola | 2008-10-12 | Open
26-10 | Include a presentation on Quality Metadata Status on WGISS-27 agenda. | WGISS-Exec | 2009-03-01 | Open
26-11 | Review presentation and comment for ISO 19130 and copy Liping. | WGISS-All | 2008-10-31 | Open
26-12 | Include a session on Security on WGISS-27 agenda, with outside experts. | WGISS-Exec | 2009-03-01 | Open
26-13 | Identify liaison candidates for Precipitation Constellation and WGISS. | Satoko, Karen | WGISS-27 | Open
26-14 | Create a new template for project proposals in Applications Subgroup. Include a secion on project closeout. | Karen, Ken, Yonsook | 2009-02-15 | Open
26-15 | Include a session on Data topics on WGISS-27 agenda, with outside experts (refer to Data Services in WGISS-26 minutes). | WGISS-Exec | 2009-03-01 | Open