## Sheet2
Number | Description | Assignee | Due Date | Status | Comments
Action WGISS-44-01 | WISP to update the WGISS organizational chart on the WGISS website. | WISP |  |  | This will be done alongside the development of the WGISS two year work plan.
Action WGISS-44-02 | WGISS to explore the possibility of including the publishing of services related to EO datasets in the IDN. | WGISS |  | In Progress | Andy noted that NASA is working to modify the CMR to handle services, and will provide a date in due time.
Action WGISS-44-03 | WGISS to consider a representative to the OGC Standards Working Group; ask OCG officers to present at WGISS-45. | WGISS |  | Closed | Cristiano Lopes will represent WGISS, and will present at WGISS-45.
Action WGISS-44-04 | Michelle Piepgrass to create a webpage on the CEOS website for CEOS lessons learned and best practices. | Michelle Piepgrass | WGISS-45 | In Progress
Action WGISS-44-05 | WGISS TOR WP Tiger Team to develop and draft a WGISS Work Plan; needs to be developed internally, but input should be fed into the CEOS WP. | Yonsook Enloe, Rob Woodcock, Michelle Piepgrass, Mirko Albani, Richard Moreno, Andy Mitchell | Dec-31-2017
Action WGISS-44-06 | WGISS to revise the WGISS brochure; see notes for details. | WGISS Brochure Team | WGISS-45 |  | Andy will coordinate the WGISS Brochure Team
Action WGISS-44-07 | WGISS Data Access System Level Team to review the ECV inventory for accessibility of datasets. | Data Access SLT | Jan-31-2018 | In Progress | Version 2.0 has been issued. The SLT will provide feedback in January; something formal will need to be delivered to the SIT in April.
Action WGISS-44-08 | Rob Woodcock and Yonsook Enloe to further discuss the possibility to create a Python client to allow ingest of WGISS connected data assets into the CEOS Data Cube. | Robert Woodcock, Yonsook Enloe |  | In Progress | Rob agreed to contact Yonsook and provide status.
Action WGISS-44-09 | WGISS Exec to find the best way to publicize when new missions become available. | Exec |  | In Progress | Mirko and Yolanda will propose something similar to purge alert and provide feedback at December WGISS-Exec meeting.
Action WGISS-44-10 | WGISS Exec to plan a quarterly telecon for raising issues, concerns, and for discussion of topics. | Exec | 2018-02-28 | Ongoing | This would be a virtual meeting and will require some planning; a decision may be made by February.
Action WGISS-44-11 | Mirko Albani and Richard Moreno to take the WGISS EO Data Preservation Maturity Matrix to the LTDP Working Group. | Mirko Albani, Richard Moreno | 2017-12-31 |  | The activity regarding the review of the Maturity Matrix by LTDP WG was completed and the final version was already circulated. As requested during WGISS-44, a final review is under NOAA.
Action WGISS-44-12 | WGISS agencies to consider collaborating on OGC Testbed 14. | Agencies |  |  | Mirko, Iolanda and Cristiano, will circulate the document and collect feedback.
Action WGISS-44-13 | Cristiano Lopes to have a presentation at WGISS-45 on the outcomes of Testbed 13. | Cristiano Lopes | WGISS-45 | In Progress | This will be added to the agenda.
Action WGISS-44-14 | WGISS to consider the areas where WGISS can contribute to ISO TC 211. | Iolanda Maggio, Mirko Albani | WGISS-45 |  | Iolanda and Mirko have started the discussion on cooperation between DSIG and ESIP. A presentation on the possible cooperation will be given during WGISS-45.
Action WGISS-44-15 | WGISS to consider which agency can support WISP. | WGISS-Exec | WGISS-45 | In Progress | Discussion is ongoing; waiting for NOAA to confirm. Plan B is to ask the SEO.
Action WGISS-44-16 | Michelle Piepgrass to publicize the Journal of Global Change Data and Discovery (www.geodoi.ac.cn) on the WGISS website, and Chuang Liu to list WGISS in the publication. | Michelle Piepgrass, Liu Chuang | 2017-11-30 |  | Michelle will follow up with Chuang Liu.