## Sheet1
WGISS-46 Actions, Last Update April 27, 2019
Number | Category | Description | Actionees | Due Date | Status | Comments
WGISS-45-7 |  | Yonsook Enloe, Richard Moreno, Rob Woodcock, Mirko Albani, and Chris Lynnes to identify and submit to Michelle the valid versions of their Best Practice and White Papers. Michelle to display these on the Document Management Table on the WGISS website by end of June 2018. | Yonsook Enloe, Richard Moreno, Rob Woodcock, Mirko Albani, and Chris Lynnes |  | Closed | 05-Dec: DSIG input already provided; Michelle will distribute another email requesting feedback. Something prominent for the IDN and CDA should be included. The page name should be changed to Best Practice and Guidelines. Mirko will advertise to other CEOS groups once WGISS is done. 14-Jan: Iolanda will notify WGISS-Exec that this page is available for maintenance.
WGISS-45-8 |  | Mirko Albani, Iolanda Maggio and Michelle Piepgrass to address Best Practice and White Papers (not lessons learned) Web page (to be put at highest level in CEOS Web Site) population with other WGs material after completion of action on WGISS Interest Groups. Maintain and populate page by September, 2018. | Mirko Albani, Iolanda Maggio and Michelle Piepgrass |  | Closed | 24-July-18: Iolanda is working on it. 05-Sep-18: Kim is working on it and a proposal was submitted. Iolanda has to confirm it. 03-Oct-18: the activity is waiting for the closure of the previous action. 05-Dec: waiting for WGISS-45-7 closure; Ioland will follow up. 13-Feb: the web page has been reviewed and it could be publicized. 18-Mar: The action can be closed.
WGISS-45-13 |  | Michael Morahan to follow up with Greg Stensaas to update the test site information in the IDN by end of June. | Michael Morahan |  | Closed | 24-May-18: Michael will reach out to Greg this week. He would be working with John Faundeen on this. 03-Oct: Michael is expecting some records at end of October or early November. 05-Dec: superseded by WGCV-3-b.
WGISS-45-15 |  | Esther Conway, Andrea Della Vecchia, and Michael Morahan to ensure that UKSA’s data collections are accessible through FedEO. | Esther Conway, Andrea Della Vecchia, and Michael Morahan |  | Closed | 05-Dec: superseded by Action.10 in Carbon Portal (WORKING on ingestion/export tool for automatic population of IDN. Started with DLR, ECV-CMEMS and ECV-CCI)
WGISS-46-1 | WGISS | Mirko Albani to bring to the attention of the SEO and the SIT the need for CEOS-globalized (e. g. VCs and WGs) WISP support; suggest this could be provided through the SEO. | Mirko Albani | End November 2018 | In progress | 13-Feb: In progress 18-Apr: During the WGISS-47 meeting a dedicated presentation of all activities covered by WISP will trigger the discussion.
WGISS-46-2 | WGISS | Mirko Albani to inform the SIT Chair that CSIRO has confirmed nomination of Robert Woodcock as WGISS representative in the GEOSS Expert Advisory Group. Mirko Albani and Andrew Mitchell will support Robert as needed. WGISS suggests that a letter be sent by the SIT Chair to the GEO Secretariat. | Mirko Albani | End October 2018 | Closed
WGISS-46-3 | WGISS | Michelle Piepgrass to send Terms of Reference (ToR) to Robert Woodcock and Mirko Albani. WGISS-Exec to update the WGISS ToR to reflect FDA activities assigned to WGISS and recommendations from the CEOS SIT and Plenary. | Michelle Piepgrass | End January 2019 | Closed | 13-Feb: ToR circulated and after an internal analysis the proposal is to not update the ToR but include FDA dedicated session in the CEOS Workplan assigned to WGISS and to update the WGISS internal organization accordingly. 18-Mar: The action can be closed
WGISS-46-4 | WGISS | WGISS interest group leads to provide information for the ‘CEOS Agencies Participation/Contribution to WGISS’ table (a table showing the different WGISS groups, their scope, CEOS agency interest/benefits, and skills of representatives), and to finalize, distribute and post. | Interest Group Leads | End November 2018 | In progress | 14-Jan: Preservation and Stewardship and Technology interest Group draft contribution circulated. Reminder sent to FDA and Interoperability. 13-Feb: The FDA provided input but we need to understand how change the Interoperability and use IG. Dedicated discussion during this WGISS-exec meeting. 18-Mar: To be discussed. 18-Apr: the new version of the WGISS organization will be discussed during the exec meeting (point 3) and the report updated consequently.
WGISS-46-5 | WGISS | WGISS-Exec to identify potential WGISS Vice-chair candidates for period 2019-21 (to become Chair in 2021-23) and determine availability. | WGISS-Exec | End January 2019 | In progress | 14-Jan: Conversing with USGS 13-Feb: Rob Woodcock contacted USGS. Awaiting confirmation of interest. Additional options to be investigated.
WGISS-46-6 | WGISS | Interest Group leads to send final comments on the WGISS brochure to Michelle Piepgrass and Iolanda Maggio. | Interest Group Leads | End October 2018 | Closed | Dec-05: No comments received yet. 07-Jan: the brochures confirmed
WGISS-46-7 | Cooperation | WGISS-Exec (Mirko Albani, Robert Woodcock, Andrea Della Vecchia, Yonsook Enloe, Liping Di) to explore the possibility of a Carbon Portal case study built around the VAST-VNSC Chair Initiative. After confirmation, WGISS-Exec will get in touch with the SEO and VNSC as needed. | WGISS-Exec (Mirko Albani, Robert Woodcock, Andrea Della Vecchia, Yonsook Enloe, Liping Di) | End November 2018 | In progress | 05-Dec: Stephen Plummer provided a list of requests and observations from the carbon team. Liping Di responded to the CEOS Plenary task email. A telecon is scheduled this month. 13-Feb: Awaiting feedback from NOAA 18-Mar: first telco held with VNSC. Further details will be discussed in the upcoming week.
WGISS-46-8 | Cooperation | WGISS-Exec (Richard Woodcock, Iolanda Maggio) to further explore possible areas of cooperation with WGDisasters, specifically with regards to the generic Recovery Observatory and FDA/CDA. | WGISS-Exec (Richard Woodcock, Iolanda Maggio) | End February 2019 | In progress | 13-Feb: In progress 18-Apr: A dedicated presentation on first of May could address this topic.
WGISS-46-9 | Cooperation | Mirko Albani, Richard Moreno, Ge Peng, Iolanda Maggio to further elaborate possible collaboration with the WMO International Expert Group on Climate Data Modernisation (IEG-CDM), WIS and WIGOS, and possibly organize a joint session at WGISS-47. | Mirko Albani, Richard Moreno, Ge Peng, Iolanda Maggio | End February 2019 | Closed | 13-Feb: In progress 18-Mar: A dedicated presentation during the WGISS-47. The action can be closed
WGISS-46-10 | Cooperation | Rosemarie Leone and Ge Peng to exchange information and further elaborate on use cases to be included in a CCSDS Green Book. Rosemarie to drive input for CCSDS. | Rosemarie Leone, Ge Peng | Date TBD | On Hold | 05-Dec: will be reported at the next WGISS Exec. 07-Jan: Few Use cases on Data Curator are going to be finalized. Ge Peng will be contacted in a second step 13-Feb: an analysis on this activity is ongoing and for the moment it could be put in waiting
WGISS-46-11 | Cooperation | Robert Woodcock to follow up on a SAR training/meeting in Vietnam with WGCapD/CSIRO. | Robert Woodcock | End November 2018 | Closed | 14-Jan: Matt Paget joined the WGCapD telecon on VNSC SAR training in 2019. It was decided that SAR ARD (for experts) would go ahead as planned on 19-20 Feb 2019. Following will be a SAR training course for general users focused on rice and forestry applications on 21-23 Feb 2019 (largely CNES/CESBIO run). A second SAR training course will be held later in 2019 to focus on other topics such as water extent and land subsidence (possibly DLR run). CSIRO EASI ODC training environment running well. Open Datacube is being installed on laptops. Need to work on data pipelines from providers; CNES provided for SAR. One problem is not enough metadata. So some lessons learned from that.
WGISS-46-12 | Cooperation | Iolanda Maggio to communicate with NextGEOSS, AmeriGEOSS, AfriGEOSS and EuroGEOSS about joining the WGISS inventories (FDA and/or SW/Tools). | Iolanda Maggio | End November 2018 | Closed | 05-Dec: Iolanda has contacted each, and AmeriGEO agreed. 07-Jan: EuroGEOSS also expressed interest on this activity in terms of advertising of the WGISS inventories. 18-Mar: The action can be closex
WGISS-46-13 | Cooperation | Chris Lynnes, Mirko Albani and Robert Woodcock to put together one page on recommendations for cooperation between GEO and WGISS based on the outcomes of the WGISS-46 joint workshop. | Chris Lynnes, Mirko Albani, Robert Woodcock | End November 2018 | In progress | 14-Jan: Will proved update next week. 13-Feb: WGISS contributions to GEOSS knowledge Hub implementation will be included in the new GEO work plan. WGISS will continue contributing to the GEO EVOLVE initiative for CEOS agencies Data Access and DMP IG 18-Mar: A dedicated presentation during the WGISS-47. Action can be closed
WGISS-46-14 | Cooperation | WGISS-Exec to investigate the Research Data Alliance (RDA) working groups and identify those that may have relevance to the work of WGISS. Identify next steps. | WGISS-Exec | End of January 2019 | Closed | 13-Feb: The report has been produced and a specific session will be organized in WGISS-47. 18-Mar: The action can be closed
WGISS-46-15 | Connected Data Assets | WGISS members to provide comments on the User Metrics Best Practice. | WGISS members | Mid-November 2018 | Closed | 05-Dec: Inputs have been received from DLR. The document should be issued and placed on the BP page. 07-Jan: the action can be closed the final version of the best practices has been delivered and loaded in the WGISS web site 13-Feb: To be closed
WGISS-46-16 | Connected Data Assets | WGISS members to perform an analysis of status of implementation of User Metrics at respective organizations and provide input (status check) to Iolanda Maggio. | WGISS members | End March 2019 | In progress | 05-Dec: Analysis should follow issue of document. 07-Jan: The final version has been circulated. 14-Apr: no input received yet. The action can be postponed.
WGISS-46-17 | Connected Data Assets | WGISS CDA System Level Team (SLT) to consider/assess feasibility to implement the defined user metrics. | WGISS CDA SLT | End March 2019 | In progress | 05-Dec: Currently the SLT is manually maintaining a list of the status of each FedEO and CWIC data partner. An automatic method is being considered. 13-Feb: Andrea confirms that no metrics on the data usage are implemented yet. 18-Mar: To be discussed during the WGISS-47. Define a slot for this topic.
WGISS-46-18 | Connected Data Assets | Mirko Albani to liaise with the CEO to trigger update of the inventory of Virtual Constellations datasets and then assess discoverability/accessibility through the WGISS Connected Data Assets infrastructure. | Mirko Albani | End February 2019 | In progress | 13-Feb: In progress 18-Apr: Finalise inventory of Virtual Constellations datasets/sensors will be done by WGISS.
WGISS-46-19 | Connected Data Assets | WGISS CDA SLT to discuss way forward to implement a single front-end/portal within the IDN to access the WGISS CDA for data discovery and access (see proposal by Andrea Della Vecchia). | WGISS CDA SLT | End November 2018 | In progress | 05-Dec: Will be discussed at next SLT telecon. Mirko emphasized that searches should have CEOS branding at the IDN portal to motivate IDN registration by data providers, and that the portal should share a look and feel with the CEOS website, while at the same time displaying the identity of the data partner. 13-Feb: Decision needs to be taken following the Andrea proposal 18-Mar: To be discussed during the WGISS-47.
WGISS-46-20 | Connected Data Assets | Michael Morahan to provide a one page description of IDN entries (i. e. DIF-10 Writer Page points with fields/sub-fields and reference to external sources) and a DIF-10 metadata validator. | Michael Morahan | End December 2018 | Closed | 05-Dec: The IDN site has been updated with the information, and with links to documents.
WGISS-46-21 | Connected Data Assets | WGISS-Exec to consider organizing a session at the next WGISS-47 on EO ontologies as part of the DSIG. | WGISS-Exec | WGISS-47 | Closed | 13-Feb: ESA can present the internal new ontology. The session is confirmed and the participation will be requested to the WGISS agencies. Action to be closed 18-Mar: The action can be closed
WGISS-46-22 | Connected Data Assets | Michael Morahan, Andrea Della Vecchia, Liping Di to organize a meeting to discuss a metadata model for services description to be circulated and approved by WGISS Model will be used to describe services which will then be discoverable through the IDN SERF interface. | Michael Morahan, Andrea Della Vecchia, Liping Di | End December 2018 | In progress | 05-Dec: Valerie Dixon is organizing a meeting on metadata model. The FedEO tag (INT.ESA.FedEO) for CMR searches has been created. 13-Feb: Andrea will send a proposal for service metadata management.
WGISS-46-23 | Connected Data Assets | Marco Leonardi to trigger a request for information on an SSO White Paper to different partners including NEXT-GEOSS (Bente Bye). | Marco Leonardi | End November 2018 | In progress | 07-Jan: ESA is preparing a common understanding plan in order to identify use case scenarios in collaboration with the WGISS agencies 13-Feb: The table of contents will be circulated and a session on the topic is being organized.
WGISS-46-24 | Open Source | WGISS-Exec to evolve the OSS inventory target from an inventory sheet to a mechanism for ongoing CEOS publishing and discovery of open source tools important to CEOS agencies. Assess for sustainability and commitment from CEOS agencies prior to development. [OSSW inventory should focus on tools/SW that CEOS wants to make visible for wider use. When published on WGISS web site they should be classified by: 1) Thematic area (problem they solve), datasets usable, targeted users, category (e. g. visualization, etc.) High relevant tools should be highlighted. Second steps will be to approve at WGISS level a service/tools metadata (see WGISS-46-22) and ensure that CEOS agencies register services/tools in IDN using it. Discovery will then be possible via IDN “CEOS branded” entry point] | WGISS-Exec |  | Closed | 05-Dec: Awaiting delivery of database. 07-Jan: a feedback on the OSS inventory tool has been requested. 11-Jan: A call with the team has been held. The WGISS-46 feedback was communicated and use cases produced to explain the needs. The updated file has been sent for the first development. They are verifying the possibility to implement a functionality to be more independent when new OSS are collected in the future. The team will inform about the effort and new timeline. 13-Feb: Some technical discussions on the topic. The OSS inventory is under development and it will be presented at WGISS-47 18-Mar: The action can be closed
WGISS-46-25 | Open Source | Andrew Mitchell to notify WGISS when the CEOS Open Source Conformance Test Document is approved for Open Source. | Andrew Mitchell | Upon approval | In progress | 05-Dec: Not yet approved.
WGISS-46-26 | Preservation, Sterwardship | Iolanda Maggio to prepare a proposal for GEO DMP improvement/update based on the work done by WGISS (e. g. Maturity Matrix). | Iolanda Maggio | End January 2019 | In progress | 07-Jan: In progress 13-Feb: The proposal has been defined. A specific session during WGISS-47 meeting will be considered. 18-Mar: The action can be closed
WGISS-46-27 | Preservation, Sterwardship | DSIG to consider organizing a discussion/session/workshop regarding long term archival tapes and storage media This could be part of PV2020; consider including vendors. | DSIG | End January 2019 | Closed | 13-Feb: The CERN has been contacted to verify their interest on this topic. CERN agrees on this. 18-Mar: The action can be closed
WGISS-46-28 | FDA | WGISS-Exec (Robert Woodcock, Andrea Della Vecchia) to prepare one to two slides for the SEO on what WGISS is doing for Data Cubes and propose a way forward for cooperation between WGISS and SEO on the FDA Data Cube topic. | WGISS-Exec (Robert Woodcock, Andrea Della Vecchia) | End November 2018 | In progress | 13-Feb: Andrea will circulate a proposal by the end of February to be reviewed. 13-Feb: Rob briefed Brian verbally. The primary activity is automating the data pipelines through ARD data holdings. A key issue is how to streamline the discovery and access where there are multiple copies of datasets; Rob will write this up.
WGISS-46-29 | FDA | Mirko Albani and WGISS-Exec to prepare an updated set of actions for the CEOS 2019-21 Work Plan to address the mandate on FDA (see FDA AHT recommendations) and other WGISS related activities. | Mirko Albani | End November 2018 | Closed | 07-Jan: The draft version has been circulated (including to CEO) and collecting input. No feedback yet so can still make comments additions, request from Exec. 13-Feb: new actions sent to CEO, awaiting feedback. Specific presentation during WGISS-47 18-Mar: The action can be closed
WGISS-46-30 | FDA | Andrea Della Vecchia, Robert Woodcock, WGCV (Medhavy, Philippe Goryl, Cindy Ong) to discuss way forward on ongoing activities on data cube support to WGCV. | Andrea Della Vecchia, Robert Woodcock, WGCV (Medhavy Thankappan, Philippe Goryl, Cindy Ong) | End November 2018 | In progress | 13--Feb: A dedicated session/presentation in WGISS-47 18-Mar: To be discussed during the WGISS-47. Action can be closed during the meeting.
WGISS-46-31 | FDA | Mirko Albani, Robert Woodcock, Iolanda Maggio, and Richard Moreno to organize an FDA workshop during the next WGISS meeting to demonstrate FDA elements capabilities (subset selected from FDA inventory) and practically address interoperability aspects to make the ecosystem more manageable for users. | Mirko Albani, Robert Woodcock, Iolanda Maggio, Richard Moreno | WGISS-47 | Closed | 13-Feb: In progress 18-Mar: As soon as the right date of FDA workshop the identified speakers will be contacted. Rob should communicate how many free slots are available. 18-Apr: The FDA workshop is finalized and the action can be closed.
WGISS-46-32 | FDA | Chris Lynnes to investigate and write an information model in FDA (knowledge). | Chris Lynnes |  | In progress | Dec-05: Chris has written the section on Information Model (Information Viewpoint) in the FDA white paper.
WGISS-46-33 | Technology | WGISS (Doug Newman, Andre’ Twele, Michael Morahan, Andrea Della Vecchia) to draft a short summary analysis on Google Data Search Tool capabilities with respect to CEOS agency’s data and differences/complementarity with respect to WGISS CDA Infrastructure Include recommended actions, if any, to be carried out on WGISS side (e. g. in IDN). | WGISS (Doug Newman, Andre’ Twele, Michael Morahan, Andrea Della Vecchia) | End January 2019 | Closed | 13-Feb: Doug is preparing a white paper on this topic. 18-Mar: A reminder has been sent 18-Apr: Doug is waiting for Raytheon Corporate authorization.
WGISS-46-34 | Technology | WGISS-Exec to consider having a special session on cloud services at WGISS-47. | WGISS-Exec | WGISS-47 | Closed | 05-Dec: In discussion. 13-Feb: The session has been foreseen and the action can be closed. 18-Mar: The action can be closed.