## Sheet1
WGISS-47 Actions, Last Update October 11, 2019
Number | Description | Actionees | Due Date | Status | Comments
WGISS-47-01 | Michelle Piepgrass to finalise and post the WGISS organizational structure chart | Michelle Piepgrass | 2019-05-20 | Closed
WGISS-47-02 | Iolanda Maggio to update the WGISS Work Plan based on the CEOS Work Plan 2019-2021 | Iolanda Maggio | 2019-06-15 | Closed | July 17: The file has been circulated
WGISS-47-03 | Michelle Piepgrass to contact Cindy Ong to obtain the BP and Guidelines for WGCV | Michelle Piepgrass | 2019-05-31 | Closed
WGISS-47-04 | Mirko Albani to request SIT Chair Team to include a WGISS representative to the CEOS Study Team on WGs | Mirko Albani | 2019-05-20 | Closed
WGISS-47-05 | Mirko Albani and Robert Woodcock to provide SIT Chair Team with the name of WGISS representative for the GEO Implementation Task Force to be proposed to GEO Secretariat | Mirko Albani | 2019-05-20 | Closed
WGISS-47-06 | Iolanda Maggio to complete the Google Dataset Search Tool CEOS report using input from NASA/ESA/DLR/NOAA | Iolanda Maggio | 2019-06-30 | Closed | June 6: Iolanda is finalizing the document and will see if USGS has anything to add. July 17: the document has been circulated and input requested to NOAA and USGS August 20: New input received from STFC. The white paper will be updated also adding the agencies report as annexes. September 24: The white paper was finalized and circulated to WGISS all.
WGISS-47-07 | WGISS-Exec to follow-up GEO Work Plan preparation and identify where WGISS can contribute with • Data Management Principles (DSIG) • WGISS Connected Data Access • Future Data Architectures | WGISS-Exec | 2019-06-30 | Closed | July 17: DMP WG will be merged with Data Sharing WG and included in Foundational Task “GEOSS Data, Information and Knowledge”. Review of latest version and definition of possible contribution from WGISS is ongoing (WGISS Chair). August 20: still ongoing September 18: WGISS will contribute with DMP. Ad-hoc calls are being followed by DSIG team. They have accepted to change the wording such that we can contribute.
WGISS-47-08 | Robert Woodcock to define next steps and schedule for FDA-08 White paper | Robert Woodcock | 2019-05-20 | Closed | June 6: Iolanda is finalizing the document and will see if USGS has anything to add. July 17: the document has been circulated and input requested to NOAA and USGS August 20: New input received from STFC. The white paper will be updated also adding the agencies report as annexes. September 18: The white paper will be finalized and circulated to WGISS all by the end of next week. Oct. 11: Superseded by new action WGISS-48.
WGISS-47-09 | Mirko Albani and Iolanda Maggio to complete FDA-09 Inventory deliverable | Mirko Albani | 2019-07-31 | Closed | June 6: the team is investigating different platforms. Final document will be issued by end of July. August 20: still ongoing September 18: dedicated presentation during WGISS-48 meeting.
WGISS-47-10 | ESA to present progress of DCFS Data Cube at next WGISS | ESA | WGISS-48 | Closed
WGISS-47-11 | Ad-hoc team led by Valerie Dixon (Michael Morahan, Andrea Della Vecchia, Chris Lynnes, Cristiano Lopes, Richard Moreno) to define proposal for metadata model for services addressing a set of high priority use cases. Proposed model to be circulated to WGISS-all for review and approval | Ad-hoc team | 2019-07-31 | Closed | June 6: Valerie noted a good deal of analysis and a path forward to a back-end integrated service model, and further work needed for the front-end model. The team is on track to have an updated UMM out for review by end of June. July 17: SLT start reviewing UMM-S and Yves Coene shared OGC TB-15 report
WGISS-47-12 | Michael Morahan to register services/tools from inventory tables (FDA elements and SW/tools) into IDN starting from the ones presented at WGISS-47 | Michael Morahan | WGISS-50 | In Progress | June 6: Iolanda will send the last version to Michael Morahan soon. July 17: The files have been sent Oct 9: Waiting until the UMMT
WGISS-47-13 | Andrea Della Vecchia and Robert Woodcock to define with SEO a roadmap and short term activities on interoperability between ODC / HMDC / DCFS Data Cubes (e.g. Jupyter notebooks with XArray API and WCS / WPS) | Andrea Della |  | Closed | June 6: Rob will reach out to Andrea to begin this task. Aug 20: Rob reached out to Andrea to begin this task. Oct. 11: Roadmap defined during WGISS-48.
WGISS-47-14 | Cristiano Lopes to inform WGISS-Exec about outcomes of ongoing OGC standardisation activities (including OGC test-beds) and ask for any additional support as needed | Cristiano Lopes | WGISS-48 | Closed | June 6: Cristiano will have more information after the OGC meeting. Need to ponder how to make this more collaborative and engage more audiences, perhaps incorporating into Tech Expo. Oct 11: presentation at WGISS-48.
WGISS-47-15 | Andrea Della Vecchia and Robert Woodcock to define with WGCV colleagues (Medhavy Thankappan, Phillipe Goryl, and Cindy Ong) coordinated roadmap and short term activities on WGISS-WGCV Data Cubes (ESA and ODC DEA) and possibly demo to be shown at SIT TW in September 2019 |  | 2019-06-30 | Closed | June 6: Rob will follow up with Cindy and Medhavy. Aug 20: Rob met with Medhavy, who suggests revising one of the actions. This will be discussed with Mirko and Cindy.
WGISS-47-16 | Robert Woodcock to liaise with AquaWatch representatives to gather their requirements/needs and further define how WGISS could support | Robert Woodcock | 2019-06-30 | In progress | Oct 11: Rob will discuss with the leads of CARD4L.
WGISS-47-17 | WGISS CDA System Level Team (SLT) to | CDA-SLT
WGISS-47-17a | Identify the best approach to implement a single map-based front-end/portal within the IDN to discover and access CEOS agencies data through WGISS CDA back-end. Agree on way-forward with WGISS-Exec. Due by June 30, 2019. |  | 2019-06-30 | Closed | July 17: Discussion on this topic during the SLT meeting.
WGISS-47-17b | Start Actions as agreed (e.g. implement CEOS branding on IDN portal and underlying FedEO and CWIC when appearing for second step searches, etc.) Due by December 31, 2019. |  | 2019-12-31 | In Progress | July 17: CWIC has been branded with CEOS, and the same has been requested from FedEO. Michael will demonstrate this at WGISS-48.
WGISS-47-17c | Assess advantages and feasibility to implement (part of) CEOS Data Usage Metrics in the IDN portal / WGISS Connected Data Assets. Due by December 31, 2019. |  | 2019-12-31 | In Progress | July 17: The NASA EarthData Search Tool will be used. Searches will be the same, but the interface will be quite different.
WGISS-47-18 | Chris Lynnes, Yousuke Ikehata and Kent Ross to organise a webinar in September focusing on existing (pre)operational Exploitation and Application Platforms targeting the academic community. Following webinars should target the new developing countries on the same topics | Chris Lynnes | 2019-09-30 | Closed | June 6: Chris is looking to Rob to lead one or two webinars and proposes first week in September and Rob agreed. Chris will begin the planning. Sept 9: Webinar occurred.
WGISS-47-19 | Iolanda Maggio and Andrew Cherry finalise SW Inventory database tool, present to WGISS-Exec and publish on CEOS website | Iolanda Maggio | 2019-07-31 | In Progress | Have link presented, collecting comments. Idea is to use the same format to load the fda-09 elements. July 17: the teams are in contact to finalise it and to implement a prototype for the FDA element as well August 20: meeting scheduled in this week. September 18: Dedicated presentation and final demo at WGISS-48 meeting (the technical decision seems to be to have one server for both inventories to reduce the impact of security internal audit) Oct 11: Mirko and Iolanda will contact to Brian Killough.
WGISS-47-20 | Liping Di and Kenneth Casey to confirm EXEC of closure of Action CARB-15 (i.e. when next version of Carbon portal is available online) | Liping Di |  | Closed | Aug 20: The new version is online
WGISS-47-21 | Marco Leonardi to circulate first version of SSO White Paper to WGISS-all for review and comments | Marco Leonardi | 2019-05-31 | Closed | June 6: Document circulated to WGISS-All June 2, 2019. July: Feedback from DLR received.
WGISS-47-22 | David Borges to share with WGISS the WGDisasters Generic RO white paper when it becomes available, to identify any integration opportunities where WGISS could support WGDisasters Generic RO technical requirements | David Borges |  | Closed | July 17: paper being finalized. Aug 28: WGDisasters Generic Recovery Observatory White Paper distributed.
WGISS-47-23 | Chris Lynnes to provide a more nuanced version of the “Entities and Connections” for the GEO Knowledge Hub by July 31, 2019 | Chris Lynnes | 2019-07-31 | Closed | June 6: Rob will determine where GEO is in connection to this action, and see if Simon Cox is interested.
WGISS-47-24 | Mirko Albani to distribute to WGISS the draft version of the GEO Work Plan by May 20, 2019 | Mirko Albani | 2019-05-20 | Closed
WGISS-47-25 | Andrea Della Vecchia to put together a guide (e.g. video, short doc, demo) on the use of SKOS interface and tool by July 31, 2019 | Andrea Della Vecchia | 2019-07-31 | Closed | July 17: The guide has been circulated
WGISS-47-26a | Iolanda Maggio to liaise with Ge Peng to find out when the WMO documents on stewardship are approved by October 31, 2019 | Iolanda Maggio | 2019-10-31 | In progress | July 17: This effort is ongoing. August 20: still ongoing September 18: ongoing
WGISS-47-26b | Iolanda Maggio to liaise with WGCV to collect comments on WGISS and WMO maturity matrices (once the WMO documents are approved) by December 31, 2019 | Iolanda Maggio | 2019-12-31 | In Progress | July 17: Awaiting feedback from WGCV. August 20: still ongoing September 18: first meeting held with ESA quality team and a dedicated presentation at WGISS#48 meeting
WGISS-47-27 | Iolanda Maggio to define way forward for finalization of WGISS Maturity Matrix using WMO matrix and RDA-FAIR WG results; finalise input for DMP by June 30, 2019 | Iolanda Maggio | 2019-06-30 | Closed | July 17: The proposal has been finalized and it will be presented at WGISS-48. Oct 11: Superseded by new action (WGISS-48).
WGISS-47-28 | Mirko Albani to send to Liping Di a packet of slides describing CEOS/WGISS for presentation at the ISO 48th Plenary by May 31, 2019 | Mirko Albani | 2019-05-31 | Closed
WGISS-47-29 | CDA SLT to analyse what kind of effort and solution can be accomplished by WGISS to automate future ECV Inventory updates [last slide of presentation] | CDA SLT | Q3 2020 | In Progress
WGISS-47-30 | CDA SLT to send to WGClimate the list of elements in the inventory that should be made mandatory so they can be registered automatically | CDA SLT | 2019-06-30 | In Progress | June 6: The SLT is organizing with WGClimate to determine which activities can be done by the ESA team. July 17: ECV Team notified with email sent on 28/05/2019 16:00 (Iolanda and Mirko in cc). No answer yet. June 6: The NASA updates have been done, and Andrea is progressing with ESA’s. July 17: Michael Morahan and Yves discussed the remaining issues with respect to FedEO collection records, particularly the ECV records. In the ECV records, geographical extent needs to be machine readable and the organization responsible for collection needs to be identified in a consistent way. ESA will indicate which ECV records to put into IDN.
WGISS-47-31 | Mirko Albani and Yonsook Enloe to contact the KMA and JMA to get their assets connected | Mirko Albani | 2019-09-30 | In Progress
WGISS-47-32 | Mirko Albani to send information to Joerg Schultz about the Purge Alert procedure | Mirko Albani | 2019-06-30 | Closed | Sept 18: information sent.
WGISS-47-33 | WGISS to give a demonstration of the Carbon Portal at the WGClimate meeting in September | WGISS |  | Closed | July 17: Mirko plans to contact Joerg on the feasibility of this.
WGISS-47-34 | Mirko Albani to liaise with Marc Paganini on discovery and access of data and platforms identified in the SDG slides | Mirko Albani | 2019-07-31 | Closed | August 20: discussion started. New feedback ready on September after a scheduled meeting. September 18: Waiting for meeting scheduling
WGISS-47-35 | CDA SLT and Ad-hoc team led by Valerie Dixon (Michael Morahan, Andrea Della Vecchia, Chris Lynnes, Cristiano Lopes, Richard Moreno) to look into OGC Testbed 14 results and assess possible use and application within WGISS FDA interoperability activities | CDA SLT | 2019-07-31 | Closed
WGISS-47-36 | Technology Exploration IG to define a template suitable for gathering inputs from agencies (domain, use case, datasets, labels, dataset accessible accessibility) in the areas of Machine Learning and Artificial Intelligence | Technology Exploration IG | 2019-08-31 | In Progress | June 6: Chris noted that he has someone in NASA to involve and Esther added that she is reaching out to some people in the UK, specifically from organizations in involved in the British Antarctica Survey.

## Sheet2
Action WGISS-47-01 | Michelle Piepgrass to finalise and post the WGISS organizational structure chart | Due by May 20, 2019
Action WGISS-47-02 | Iolanda Maggio to update the WGISS Work Plan based on the CEOS Work Plan 2019-2021 | Due by June 15, 2019
Action WGISS-47-03 | Michelle Piepgrass to contact Cindy Ong to obtain the BP and Guidelines for WGCV | Due by May 31, 2019
Action WGISS-47-04 | Mirko Albani to request SIT Chair Team to include a WGISS representative to the CEOS Study Team on WGs | Due by May 20, 2019
Action WGISS-47-05 | Mirko Albani and Robert Woodcock to provide SIT Chair Team with the name of WGISS representative for the GEO Implementation Task Force to be proposed to GEO Secretariat | Due by May 20, 2019
Action WGISS-47-06 | Iolanda Maggio to complete the Google Dataset Search Tool CEOS report using input from NASA/ESA/DLR/NOAA | Due by June 30, 2019
Action WGISS-47-07 | WGISS-Exec to follow-up GEO Work Plan preparation and identify where WGISS can contribute with | by June 30, 2019
Action WGISS-47-08 | Robert Woodcock to define next steps and schedule for FDA-08 White paper | Due by May 20, 2019
Action WGISS-47-09 | Mirko Albani and Iolanda Maggio to complete FDA-09 Inventory deliverable | Due by July 31, 2019
Action WGISS-47-10 | ESA to present progress of DCFS Data Cube at next WGISS | Due by WGISS-48
Action WGISS-47-11 | Ad-hoc team led by Valerie Dixon (Michael Morahan, Andrea Della Vecchia, Chris Lynnes, Cristiano Lopes, Richard Moreno) to define proposal for metadata model for services addressing a set of high priority use cases | Proposed model to be circulated to WGISS-all for review and approval | Due by July 31, 2019
Action WGISS-47-12 | Michael Morahan to register services/tools from inventory tables (FDA elements and SW/tools) into IDN starting from the ones presented at WGISS-47 | Due by WGISS-48
Action WGISS-47-13 | Andrea Della Vecchia and Robert Woodcock to define with SEO a roadmap and short term activities on interoperability between ODC / HMDC / DCFS Data Cubes (e | g | Jupyter notebooks with XArray API and WCS / WPS) | Due by June 30, 2019
Action WGISS-47-14 | Cristiano Lopes to inform WGISS-Exec about outcomes of ongoing OGC standardisation activities (including OGC test-beds) and ask for any additional support as needed | Due by WGISS-48
Action WGISS-47-15 | Andrea Della Vecchia and Robert Woodcock to define with WGCV colleagues (Medhavy Thankappan, Phillipe Goryl, and Cindy Ong) coordinated roadmap and short term activities on WGISS-WGCV Data Cubes (ESA and ODC DEA) and possibly demo to be shown at SIT TW in September 2019 | Due by June 30, 2019
Action WGISS-47-16 | Robert Woodcock to liaise with AquaWatch representatives to gather their requirements/needs and further define how WGISS could support | Due by June 30, 2019
Action WGISS-47-17 | WGISS CDA System Level Team (SLT) to
Action WGISS-47-18 | Chris Lynnes, Yousuke Ikehata and Kent Ross to organise a webinar in September focusing on existing (pre)operational Exploitation and Application Platforms targeting the academic community | Following webinars should target the new developing countries on the same topics | Due by September 30, 2019
Action WGISS-47-19 | Iolanda Maggio and Andrew Cherry finalise SW Inventory database tool, present to WGISS-Exec and publish on CEOS website | Due by July 31, 2019
Action WGISS-47-20 | Liping Di and Kenneth Casey to confirm EXEC of closure of Action CARB-15 (i | e | when next version of Carbon portal is available online) | Mirko will then inform CEOS SEC about closure and that activities will in any case continue | Due by June 30, 2019
Action WGISS-47-21 | Marco Leonardi to circulate first version of SSO White Paper to WGISS-all for review and comments | Due date by May 31, 2019
Action WGISS-47-22 | David Borges to share with WGISS the WGDisasters Generic RO white paper when it becomes available, to identify any integration opportunities where WGISS could support WGDisasters Generic RO technical requirements
Action WGISS-47-23 | Chris Lynnes to provide a more nuanced version of the “Entities and Connections” for the GEO Knowledge Hub by July 31, 2019
Action WGISS-47-24 | Mirko Albani to distribute to WGISS the draft version of the GEO Work Plan by May 20, 2019
Action WGISS-47-25 | Andrea Della Vecchia to put together a guide (e | g | video, short doc, demo) on the use of SKOS interface and tool by July 31, 2019
Action WGISS-47-26a | Iolanda Maggio to liaise with Ge Peng to find out when the WMO documents on stewardship are approved by October 31, 2019
Action WGISS-47-26b | Iolanda Maggio to liaise with WGCV to collect comments on WGISS and WMO maturity matrices (once the WMO documents are approved) by December 31, 2019
Action WGISS-47-27 | Iolanda Maggio to define way forward for finalization of WGISS Maturity Matrix using WMO matrix and RDA-FAIR WG results; finalise input for DMP by June 30, 2019
Action WGISS-47-28 | Mirko Albani to send to Liping Di a packet of slides describing CEOS/WGISS for presentation at the ISO 48th Plenary by May 31, 2019
Action WGISS-47-29 | CDA SLT to analyse what kind of effort and solution can be accomplished by WGISS to automate future ECV Inventory updates [last slide of presentation]
Action WGISS-47-30 | CDA SLT to send to WGClimate the list of elements in the inventory that should be made mandatory so they can be registered automatically | By June 30, 2019
Action WGISS-47-31 | Mirko Albani and Yonsook Enloe to contact the KMA, JAXA and JMA to get their assets connected | Due by September 30, 2019
Action WGISS-47-32 | Mirko Albani to send information to Joerg Schultz about the Purge Alert procedure | Due by June 30, 2019
Action WGISS-47-33 | WGISS to give a demonstration of the Carbon Portal at the WGClimate meeting in September
Action WGISS-47-34 | Mirko Albani to liaise with Marc Paganini on discovery and access of data and platforms identified in the SDG slides | Due by July 31, 2019
Action WGISS-47-35 | CDA SLT and Ad-hoc team led by Valerie Dixon (Michael Morahan, Andrea Della Vecchia, Chris Lynnes, Cristiano Lopes, Richard Moreno) to look into OGC Testbed 14 results and assess possible use and application within WGISS FDA interoperability activities | Due by July 31, 2019
Action WGISS-47-36 | Technology Exploration IG to define a template suitable for gathering inputs from agencies (domain, use case, datasets, labels, dataset accessible accessibility) in the areas of Machine Learning and Artificial Intelligence | Due by August 31, 2019