## Sheet1
WGISS-48 Actions, Last Update October 29, 2019
Number | Category | Description | Actionees | Due Date | Status | Comments
WGISS-48-01 | General | WGISS Exec to consider creation of a subgroup under the Data Interoperability and Use Interest Group to focus on “Services and Tools: discovery, access and interoperability”. Due by end 2019. | WGISS Exec | Dec 31 2019
WGISS-48-02 | General | WGISS Exec to await GEOSEC announcement and submit nomination of WGISS point of contact in GEO WP Foundational Tasks. Due by end 2019. | WGISS Exec | Dec 31 2019
WGISS-48-03 | General | WGISS Exec to review and comment potential Actions on WGISS in the new CEOS Work Plan 2020-22 in relation to ARD Strategy. Due by February 2020. | WGISS Exec | 2020-02-01
WGISS-48-04 | Data Discovery and Access | Michelle Piepgrass to discuss with Brian Killough the possibility of restoring the URL wgiss.ceos.org since it is referenced in several brochures. Due by November 2019. | Michelle Piepgrass | 2019-11-30
WGISS-48-05 | Data Discovery and Access | WGISS CDA-SLT to organize a session at WGISS-49 on services discovery and access with the goal to align the approaches of OGC, CDA, and GEO. Due by WGISS-49. | WGISS CDA-SLT | WGISS-49
WGISS-48-06 | Data Discovery and Access | WGISS CDA-SLT to review VC data collection inventories spreadsheet and confirm if/what information is missing to generate DIF-10 metadata for the datasets therein included. Due by December 2019. | WGISS CDA-SLT | 2019-12-31
WGISS-48-07 | Data Discovery and Access | WGISS CDA-SLT to prepare a template for VC Leads to gather information for IDN registration. Ask for specific needs (e.g. One-stop-shop data discovery and access for relevant data sets and tools? Community portals?). Due by December 2019. | WGISS CDA-SLT | 2019-12-31
WGISS-48-08 | Data Interoperability and Use | WGISS Interoperability Tiger Team to follow-up interoperability activities between data cubes as defined in the roadmap outlined in the WGISS#48 session (including definition of relevant milestones). The team will include Rob Woodcock (Lead), Andrea Della Vecchia, Brian Killough, Philippe Mougnaud, Chris Lynnes, Damiano Guerrucci, Valerie Dixon, and Michael Morahan. | WGISS Interoperability Tiger Team
WGISS-48-09 | Data Interoperability and Use | WGISS Exec (Rob Woodcock and Chris Lynnes) to reformulate FDA-08 with a short umbrella clarifying the FDA business case and high level picture plus a set of underlying papers on specific topics (e.g. cloud-native formats, OGC-API evolutions, data cubes interoperability, and STAC). Due by December 2019. | WGISS Exec (Rob Woodcock and Chris Lynnes) | 2019-12-31
WGISS-48-10 | Data Interoperability and Use | WGISS Exec (Mirko Albani and Iolanda Maggio) to define a governance process to update and maintain the OSS and FDA Elements Inventory. Due by February 2020. | WGISS Exec (Mirko Albani and Iolanda Maggio) | 2020-02-01
WGISS-48-11 | Data Interoperability and Use | WGISS Exec (Iolanda Maggio) to ensure coordination of inventory activities with ongoing SLT work on UMM-S/UMM-T and with discovery/access through WGISS CDA. Due by February 2020. | WGISS Exec (Iolanda Maggio) | 2020-02-01
WGISS-48-12 | Data Preservation and Stewardship | Iolanda Maggio to update the Persistent Identifiers Best Practice and circulate it to WGISS by December 31, 2019. | Iolanda Maggio | 2019-12-31
WGISS-48-13 | Data Preservation and Stewardship | Iolanda Maggio to organize a session at WGISS-49 to discuss persistent identifiers, including use cases of DOI (i.e. software). Due by WGISS-49. | Iolanda Maggio | WGISS-49
WGISS-48-14 | Data Preservation and Stewardship | Ken Casey to make a presentation at WGISS-49 to demonstrate the NOAA CoMET tool and the Maturity Matrix Self-Assessment tool. Due by WGISS-49. | Ken Casey | WGISS-49
WGISS-48-15 | Data Preservation and Stewardship | Mirko Albani and Iolanda Maggio to organize a teleconference/meeting with WGCV representatives to review the Maturity Matrix. Due by November 2019. | Mirko Albani and Iolanda Maggio | 2019-11-01
WGISS-48-16 | Data Preservation and Stewardship | Iolanda Maggio to issue the Maturity Matrix to WGISS for review by February 2020 and to request approval to finalize at WGISS-49. Due by WGISS-49. | Iolanda Maggio | WGISS-49
WGISS-48-17 | Technology Exploration | WGISS Exec to assess Blockchain as a potential topic for the Technology Exploration Interest Groups and see if there is interest in WGISS to proceed with it further. Due by February 2020. | WGISS Exec | 2020-02-01
WGISS-48-18 | Technology Exploration | WGISS Exec to develop a plan/solicit volunteers to write sections of the Future Data Architecture Whitepaper as it applies to STAC/OGC-API/Datacube interoperability), now that IDN (through CMR) has a STAC API (OGC WFS 3.0-compliant). Due by January 2020. | WGISS Exec | 2020-01-01
WGISS-48-19 T | Technology Exploration | Technology Interest Group to explore the possibility to organize a dedicated session on ARD products SW and tools at WGISS-49. Due by WGISS-49. | Technology Interest Group | WGISS-49
WGISS-48-20 | Working Groups Cooperation | WGISS Exec to consider having a joint workshop with GEOSS at WGISS-49. Due by WGISS-49. | WGISS Exec | WGISS-49
WGISS-48-21 | Working Groups Cooperation | Andrea Della Vecchia and Michael Morahan to analyse feedback from WGClimate for IDN registration (see Joerg Schultz slides) and check if registration can be completed or we need additional feedback or to wait ECV inventory update V4. Due by November 2019. | Andrea Della Vecchia and Michael Morahan | 2019-11-30
WGISS-48-22 | Working Groups Cooperation | Liping Di and Ken Casey to check with Joerg Schultz if an additional Carbon Portal Demo / Presentation is needed at WGClimate-12 in Q1-2020. Due by January 2020. | Liping Di and Ken Casey | 2020-01-01
WGISS-48-23 | Working Groups Cooperation | DSIG to consider updating the WGISS Glossary of Terms to add ECV definitions and other interoperability-related terms to help in communicating with external entities: cooperation with WGClimate/LSI-VC/WGCV. Due by January 2020. | DSIG | 2020-01-01

## Sheet2
WGISS-48 Actions Last updated Nov 24, 2019
Category | Number | Description | Actionee | Due Date | Comments
General | WGISS-48-01 | WGISS Exec to consider creation of a subgroup under the Data Interoperability and Use Interest Group to focus on “Services and Tools: discovery, access and interoperability”. Due by end 2019. | WGISS Exec | Dec 31 2019 | Nov 12: Mirko recommended making the Services/Tools activity explicit under Discovery and Access and the data cubes activity under the Interoperability. Michelle will included this on the WGISS website.
General | WGISS-48-02 | WGISS Exec to await GEOSEC announcement and submit nomination of WGISS point of contact in GEO WP Foundational Tasks. Due by end 2019. | WGISS Exec | Dec 31 2019
General | WGISS-48-03 | WGISS Exec to review and comment potential Actions on WGISS in the new CEOS Work Plan 2020-22 in relation to ARD Strategy. Due by February 2020. | WGISS Exec | 2020-02-01 | Nov 12: Ongoing.
Data Discovery and Access | WGISS-48-04 | Michelle Piepgrass to discuss with Brian Killough the possibility of restoring the URL wgiss.ceos.org since it is referenced in several brochures. Due by November 2019. | Michelle Piepgrass | 2019-11-30
Data Discovery and Access | WGISS-48-05 | WGISS CDA-SLT to organize a session at WGISS-49 on services discovery and access with the goal to align the approaches of OGC, CDA, and GEO. Due by WGISS-49. | WGISS CDA-SLT (Yonsook Enloe) | WGISS-49 | Nov 12: To be added to the WGISS-49 agenda.
Data Discovery and Access | WGISS-48-06 | WGISS CDA-SLT to review VC data collection inventories spreadsheet and confirm if/what information is missing to generate DIF-10 metadata for the datasets therein included. Due by December 2019. | WGISS CDA-SLT (Michael, Mirko, Andrea) | 2019-12-31 | Nov 12: An analysis similar to one done with WGClimate of VC datasets registered in the IDN. Michael will resend the response from a few months ago.
Data Discovery and Access | WGISS-48-07 | WGISS CDA-SLT to prepare a template for VC Leads to gather information for IDN registration. Ask for specific needs (e.g. One-stop-shop data discovery and access for relevant data sets and tools? Community portals?). Due by December 2019. | WGISS CDA-SLT | 2019-12-31 | Nov 12: The VC leads needs to be identified.
Data Interoperability and Use | WGISS-48-08 | WGISS Interoperability Tiger Team to follow-up interoperability activities between data cubes as defined in the roadmap outlined in the WGISS#48 session (including definition of relevant milestones). The team will include Rob Woodcock (Lead), Andrea Della Vecchia, Brian Killough, Philippe Mougnaud, Chris Lynnes, Damiano Guerrucci, Valerie Dixon, and Michael Morahan. | WGISS Interoperability Tiger Team | 2019-12-31 | Nov 12: LSI has a draft, and Rob will circulate his updates. Rob will organize a meeting of the Tiger Team in December.
Data Interoperability and Use | WGISS-48-09 | WGISS Exec (Rob Woodcock and Chris Lynnes) to reformulate FDA-08 with a short umbrella clarifying the FDA business case and high level picture plus a set of underlying papers on specific topics (e.g. cloud-native formats, OGC-API evolutions, data cubes interoperability, and STAC). Due by December 2019. | WGISS Exec (Rob Woodcock and Chris Lynnes) | 2019-12-31 | Nov 12: In progress.
Data Interoperability and Use | WGISS-48-10 | WGISS Exec (Mirko Albani and Iolanda Maggio) to define a governance process to update and maintain the OSS and FDA Elements Inventory. Due by February 2020. | WGISS Exec (Mirko Albani and Iolanda Maggio) | 2020-02-01 | Nov 12: Work to be started.
Data Interoperability and Use | WGISS-48-11 | WGISS Exec (Iolanda Maggio) to ensure coordination of inventory activities with ongoing SLT work on UMM-S/UMM-T and with discovery/access through WGISS CDA. Due by February 2020. | WGISS Exec (Iolanda Maggio) | 2020-02-01 | Nov 12: Work to be started.
Data Preservation and Stewardship | WGISS-48-12 | Iolanda Maggio to update the Persistent Identifiers Best Practice and circulate it to WGISS by December 31, 2019. | Iolanda Maggio | 2019-12-31 | Nov 12: New version of BP will be circulated by end of November.
Data Preservation and Stewardship | WGISS-48-13 | Iolanda Maggio to organize a session at WGISS-49 to discuss persistent identifiers, including use cases of DOI (i.e. software). Due by WGISS-49. | Iolanda Maggio | WGISS-49 | Nov 12: To be added to the WGISS-49 agenda.
Data Preservation and Stewardship | WGISS-48-14 | Ken Casey to make a presentation at WGISS-49 to demonstrate the NOAA CoMET tool and the Maturity Matrix Self-Assessment tool. Due by WGISS-49. | Ken Casey | WGISS-49 | Nov 12: To be added to the WGISS-49 agenda.
Data Preservation and Stewardship | WGISS-48-15 | Mirko Albani and Iolanda Maggio to organize a teleconference/meeting with WGCV representatives to review the Maturity Matrix. Due by November 2019. | Mirko Albani and Iolanda Maggio | 2019-11-01 | Nov 12: Iolanda meeting with WGCV end of November. Working in parallel with WGISS-47-26b.
Data Preservation and Stewardship | WGISS-48-16 | Iolanda Maggio to issue the Maturity Matrix to WGISS for review by February 2020 and to request approval to finalize at WGISS-49. Due by WGISS-49. | Iolanda Maggio | WGISS-49 | Nov 12: To be added to the WGISS-49 agenda.
Technology Exploration | WGISS-48-17 | WGISS Exec to assess Blockchain as a potential topic for the Technology Exploration Interest Groups and see if there is interest in WGISS to proceed with it further. Due by February 2020. | WGISS Exec | 2020-02-01
Technology Exploration | WGISS-48-18 | WGISS Exec to develop a plan/solicit volunteers to write sections of the Future Data Architecture Whitepaper as it applies to STAC/OGC-API/Datacube interoperability), now that IDN (through CMR) has a STAC API (OGC WFS 3.0-compliant). Due by January 2020. | WGISS Exec | 2020-01-01
Technology Exploration | WGISS-48-19 T | Technology Interest Group to explore the possibility to organize a dedicated session on ARD products SW and tools at WGISS-49. Due by WGISS-49. | Technology Interest Group | WGISS-49 | Nov 12: To be added to the WGISS-49 agenda.
Working Groups Cooperation | WGISS-48-20 | WGISS Exec to consider having a joint workshop with GEOSS at WGISS-49. Due by WGISS-49. | WGISS Exec, Rob/Mirko | WGISS-49 | Nov 12: To be added to the WGISS-49 agenda.
Working Groups Cooperation | WGISS-48-21 | Andrea Della Vecchia and Michael Morahan to analyse feedback from WGClimate for IDN registration (see Joerg Schultz slides) and check if registration can be completed or we need additional feedback or to wait ECV inventory update V4. Due by November 2019. | Andrea Della Vecchia and Michael Morahan | 2019-11-30 | Nov 12: In progress
Working Groups Cooperation | WGISS-48-22 | Liping Di and Ken Casey to check with Joerg Schultz if an additional Carbon Portal Demo / Presentation is needed at WGClimate-12 in Q1-2020. Due by January 2020. | Liping Di and Ken Casey | 2020-01-01 | Nov 12: Michelle will follow up with Ken.
Working Groups Cooperation | WGISS-48-23 | DSIG to consider updating the WGISS Glossary of Terms to add ECV definitions and other interoperability-related terms to help in communicating with external entities: cooperation with WGClimate/LSI-VC/WGCV. Due by January 2020. | DSIG, Mirko will monitor | 2020-01-01 | Nov 12: Document circulated by LSI on definitions around ARD; suggest including with WGISS glossary of terms. Mirko contacted them, but no one took the lead. He will follow up with Matt Stevenson.