## Slide 1: WGISS-55 Meeting Summary: Actions and Feedback

## Slide 2: Action Items: Day 1
General
  Action: Michelle Piepgrass to find out number of downloads from CEOS website (Best Practice, White Papers, presentations) and provide the results to WGISS Exec.
CEOS Interoperability Framework
  Action: Each factor Lead of the CEOS Interoperability Framework to finalize the factor name, coordinator (lead), collaborator(s), description (1-2 paragraphs), scope (included and excluded).
  Action: Doug Newman to brief the CEOS Interoperability Framework team on STAC.
  Action: WGISS to work with Thomas Huang to consider the digital twins as a use case in the CEOS Interoperability Framework.
Technology Exploration
  Action: Esther Conway to schedule two Jupyter Notebooks workshops (July, September): One on access metadata, and one on technical dependencies.

## Slide 3: Action Items: Day 2
Data Discovery and Access
  Action: DSIG/SLT to confirm that content of the Open Source Software page on the CEOS website has been correctly ingested in the FedEO operational system that is accessible to end users.
  Action: DSIG to ask SEO to remove from the CEOS website the Open Source Software page, upon completion of previous action.
  Action: SLT to define a procedure for registration of services/tools into IDN/FedEO (direct registration by users or through circulation of Open Source Software spreadsheet). SLT to inform WGISS-All on how to register their services and tools.
  Action: SLT to examine the emerging needs and possible solutions for user authentication and authorisation in the new scenario for data access. Provide a status report at WGISS-56.

## Slide 4: Action Items: Day 3
Data Preservation and Stewardship
  Action: DSIG to prepare a white paper on in-situ data based on the study conducted, and submit it to WGCV for review. Review of the content should be completed by the end of May, and the document should be circulated by end of June if no updates are needed.
  Action: DSIG to prepare a white paper on software preservation based on the study conducted. Complete the review of the content by end of May, and circulate by end of June if no updates are needed.
  Action: DSIG to circulate the package of WGISS updated White Papers and Reports to WGISS-All to decide if they should be updated or retired by the end of April. The WGISS website should be updated accordingly by the end of May. DSIG should also clearly state the issue date, suggested retirement date, and the type of document (White Paper, technical note, Best Practice). The list should be submitted to the VC leads for their consideration.

## Slide 5: Action Items: Day 3 continued
Data Preservation and Stewardship, continued
  Action: Makoto Natsuisaka to ask the SEO and CEO to provide a method of governance on the process for submission and “publication” of CEOS documents (White Papers, Best Practices, Technical Documents, and deliverables from the Work Plan).
  Action: DSIG to organize a session on AVHRR at WGISS-56.

## Slide 6: Lessons Learned: Positive Feedback
Logistics: A tremendous thank you to CONAE! The facilities were great, as were the audio/visual, the breaks and hosted events, and the transportation to and from the venue. The agency tour was superb, and very interesting. The meeting was a great opportunity for CONAE to show their activities and facilities, and to exchange information.
Joint session: The joint session was interesting and well planned, and the resulting cross collaboration is very valuable.
Content: It was obvious that the agenda contained expanded time for discussion, leading to good planning for the coming year. The results can be seen already in the actions and future planning.
In-person participation: The meeting provided some with opportunity for reflection based on what was learned. Side conversations were helpful, allowing participants to see where their work is going, and to identify collaborations and sharing of resources. One participant felt that by having presentation each day, it was easier to remain engaged. Others were pleased to have the opportunity to establish old and new friendships and collaborations.
Remote participation: Great job in accommodating remote participants. The remote participants remained engaged throughout, which is hard to do for three days. Their dedication made it feel that they were truly part of the meeting.
Objectives met: More discussion time and improved communication to CEOS of WGISS technical expertise.

## Slide 7: Lessons Learned: Areas for Improvement
Audio: Try to solve the technical challenges of the hybrid meeting by exploring audio devices, closed captioning, and taking personal responsibility for being heard and understood.
Meeting scheduling: Consider having one in person meeting per year, and one or more remote meetings. Consider meeting in person every nine months
Content:
  Reinstitute the session on announcing newly released datasets and products.
  In the technology session have a presentation and discussion about the technologies coming up and those that are obsolete.
  During each session, focus and go in depth on specific topics, and avoid presentations less than 10 minutes, or cutting presentations short.