## Slide 1: Work Plan for Data Interoperability and Use Interest Group (DIIG) Deliverables for 2024-2026 Work Plan
Nitant Dube, ISRO
Agenda Item 5.1
WGISS-57
4-7 March 2023
Sydney, Australia

## Slide 2: Status: Work Plan 2023-2025
Year | 2023 | 2024 | 2025
Interoperability Framework | Roadmap | Handbook v2.0 | Maturity Matrix
 | Completed | Initiated | To be Initiated
Handbook V2.0: Emails circulated to all WG/IG/VC lead for identification of Factor Champions
Waiting for response for formation of Team
Possible Contributors
Factor | Vocabulary (Semantics) | Architecture | Interface (Accessibility) | Quality | Policy
WGISS | TEIG, DIIG | DSIG, DIIG | DAIG, DIIG | DIIG | DIIG
Other WG | WGCapD, WGCV, CEOS-ARD, LSI-VC | WGCapD, WGCV, CEOS-ARD, LSI-VC, SEO | CEOS-ARD, LSI-VC | CEOS-COAST WGCV, NSTT, GEO (QA4EO) | NSTT, CEOS/Agencies

## Slide 3: Work Plan 2024-2026
Year | 2024 | 2025 | 2026
Interoperability Framework | Handbook V2.0 | Handbook V2.0 + Maturity Matrix | Interoperability Demonstration : Development of Earth Observation Plug and Play (EOPnP) modules
Year-2024 | Q1 | Q2 | Q3 | Q4
Handbook V2.0 | E-mails sent, with request for identification of Champions | Discussions with Champions/ leads and Draft Sketch of HB 2.0 | Detailed discussions on each Factors | Presentation of Draft HB2.0 during WGISS-58
Year-2025 | Q1 | Q2 | Q3 | Q4
Handbook V2.0 + Maturity Matrix | Presentation of Final version of HB2.0 during WGISS-59 Maturity Matrix Discussions during WGISS-59 | Release of HB 2.0 for comments Development of Maturity Matrix | Incorporation of Comments Development of Maturity Matrix | Endorsement during CEOS Plenary Presentation of Maturity Matrix during WGISS-60

## Slide 4: Interoperability Demonstration
Earth Observation Plug and Play (EOPnP)
  Development of Plug and Play modules to demonstrate interoperability best practices
    Discovery and access of Earth observation data
    Data Analytics
  Possible collaboration with CEOS Analytics Lab (CAL)

## Slide 5
Thanks
nitant@sac.isro.gov.in