## General
6 | LIST OF ACTIONS
6.1 | General, cross-cutting, actions
# | Title | Action | Benefit | Time frame | Who | Performance indicator | Annual cost | Adressed in SARGIP 2017 | Comment
Action G1: | Guidance and best practice for adaptation observations | Produce guidance and best practice for climate observations for adaptation. This would include advice on using the global and regional requirements at a national and local level, and guidance and best practice on prioritization of observations, implementation, data stewardship and reporting. Promote the use of this guidance by parties and donors. Review the use of this guidance and requirements and revise as needed. | Encourage high-quality, consistent and comparable observations. | Version one available in 2018, thereafter review and refine, as needed. | GCOS in association with users and other stakeholders | Availability and use of specifications | US$ 10 000–100 000 | Y | May update info from SARGIP 2017
Action G2: | Specification of high-resolution data | Specify the high resolution climate data requirements: In response to user needs for climate adaptation planning, develop high-resolution observational requirements and guidance and distribute widely; Promote coordination among climate observation systems at different scales from subnational to global, particularly through relevant focal points, national coordinators and regional climate centres and alliances; Ensure that this work responds to other work streams under UNFCCC’s Research and Systematic Observation agenda item and the SDGs; Ensure these data are openly accessible to all users. | Develops a broad understanding of climate observational needs. Ensures consistency of climate observations and thus enables their wide use. | 2018 and ongoing thereafter | GCOS in association with users and other stakeholders | Availability and use of specifications | US$ 10 000–100 000 | Y | May update info from SARGIP 2017
Action G3: | Development of indicators of climate change | Devise a list of climate indicators that describe the ongoing impacts of climate change in a holistic way. Consider the work of WMO, IPCC and others. Indicators may include: heating of the ocean, rising sea level, increasing ocean acidity, melting glaciers and decreasing snow, changes in Arctic sea ice, changes in vegetation characteristics and distributions and land-cover changes. | Communicate better the full range of ongoing climate change in the Earth system | 2017 | GCOS in association with other relevant parties, including WMO and IPCC | Agreed list of indicators (for example, 6 in number) | US$10 000–100 000 | Y | May update info from SARGIP 2017
Action G4: | Indicators for adaptation and risk | Promote definition of, and research supporting, the development of indicators linking physical and social drivers relating to exposure, vulnerability and improved resilience, in line with national requirements | Tracking of progress of climate change and adaptation, improved capacity to respond and avoid loss. | 2017 | GCOS with relevant agencies and national bodies | Definition and development of relevant risk assessments | US$ 10 000–100 000 | Y | May update info from SARGIP 2017
Action G5: | Identification of global climate observation synergies with other multilateral environmental agreements | Ensure a scientifically rigorous assessment of the exact requirements of common variables and identify a common set of specifications between GCOS and CBD and UNCCD; ensure that maximum benefit is taken from GCOS ECVs in implementing the SDG process, including addressing multiple-benefits across SDG goals, fulfilling the climate specific goal (SDG-13) and providing support to transparent global development and climate finance prioritization (SDG-17); explore how ECV data can contribute to: (a) The Ramsar Convention; (b) the Sendai Framework for Disaster Risk Reduction; (c) other MEAs. | Improved information exchange between Conventions, cost savings, shared capacity-building and outreach, and coordinated approaches to observation providers | Ongoing (2017 for Rio conventions, 2018 for Ramsar and Sendai) | GCOS, CBD Secretariat, UNCCD Secretariat and the Global Mechanism, GEO Secretariat and GEO Biodiversity Observation Network; GCOS and sponsors + Parties (through national statistics offices) and GEO (GEO initiative on the SDGs (GI-18)); GCOS, Ramsar Convention, Open-ended Intergovernmental Expert Working Group on Indicators and Terminology Relating to Disaster Risk Reduction, ICSU-ISSC-UNISDR programme IRDR, Secretariats of other MEAs | Climate service components optimized for disaster risk reduction | US$ 10 000–100 000 | N
Action G6: | Assisting developing countries to maintain or renovate climate observation systems and to improve climate observations networks | Provide financial support to GCM through its trust fund; cooperate between donors to provide targeted support to countries to improve their observational systems; propose suitable projects for support | Targeted expert assistance to improve key monitoring networks | Continuous | Developed countries, developing country aid banks, WMO VCP, GEF and other funds for UNFCCC, the United Nations Development Programme (UNDP), national aid agencies; project proposals coordinated by GCOS panels, GCM Board and potential donor countries | Funds received by the trust sund; Increasing number of projects supporting countries | US$ 1–10 million | N
Action G7: | GCOS coordinator | Activate national coordinators | Coordinated planning and implementation of systematic climate observing systems across the many national departments and agencies involved with their provision | Ongoing | Relevant division at national governmental level responsible for the coordination of climate observation | Annual reports describing and assessing progress made in national coordination in compliance with the coordinator’s responsibilities; establishing a national climate observations inventory and publication of annual reports | US$ 10 000–100 000/year/national government | N
Action G8: | Regional workshops | Hold regional workshops to identify needs and regional cooperation, starting with Africa | Improve key monitoring networks to fill gaps in regions | 2018–2020 | GCOS secretariat in coordination with the UNFCCC Secretariat and national coordinators and the involvement and coordination with existing capacity-building activities, for example WCRP programmes such as CLIVAR or CORDEX) | Workshop outputs describing regional plans and priority national needs. | US$ 1–10 million (total for six workshops) | N
Action G9: | Communication strategy | Develop and implement a GCOS communication strategy | Targeted expert assistance to improve key monitoring networks | Develop strategy/plan in 2017; implement in subsequent years | GCOS Secretariat. | Increased monitoring and use of GCMP and monitoring of ECVs; increased donations to GCM; climate monitoring included in national plans and/or reporting to UNFCCC; production of material and improved website; participation in international meetings | US$ 100 000–1 million | N
Action G10: | Maintain ECV requirements | Routinely maintain, review and revise list of ECV requirements. The GCOS secretariat will ensure that there is a consistent approach between panels. | Clear, consistent and complete list of ECV requirements as a basis for national and international climate observations ensures consistency between observations. | GCOS Panels, GCOS secretariat | Develop a systematic approach in 2017 and review every five years | Annually updated list of ECV requirements. | US$ 1 000–10 000 for experts | N | This action needs clarification: are there really annual updates? How / where are they published? Any comment on the consistency?
Action G11: | Review of availability of climate data records | Provide a structured, comprehensive and accessible view as to what CDRs are currently available, and what are planned to exist, together with an assessment of the degree of compliance of such records with the GCOS requirements for the ECV products indicated in Annex A | Improve planning of satellite-derived climate data acquisition | CEOS/CGMS Working Group on Climate for records contributing to the ECV products that are indicated in Annex A. | End 2016 and updated every two years thereafter. | Online availability of an inventory of current and future CDRs, together with an assessment of compliance with GCOS requirements | Covered by CEOS and CGMS agencies | Y | ECV Inventory + GCOs-cmpliance assessment
Action G12: | Gap-analysis of climate data records | Establish a gap analysis process and associated actions, to: (a) address gaps/deficiencies in the current available set of CDRs; and (b) ensure continuity of records, and address gaps through the appropriate planning of future satellite missions for the ECV products indicated in Annex A | Increase the utility of the CDRs | CEOS/CGMS Working Group on Climate for records contributing to the ECV indicated in Annex A | End 2017, and updated every two years thereafter. | Availability of gap analysis and associated action plan | Covered by CEOS and CGMS agencies | Y | Gap Analysis + Coordinated Action Plan
Action G13: | Review of ECV observation networks | For all ECV products not covered by a review following actions G11 and G12: develop and implement a process to regularly review ECV observation networks, comparing their products with the ECV product requirements; identify gaps between the observations and the requirements; identify any deficiencies and develop remediation plans with relevant organizations; and ensure the data is discoverable and accessible. This action may also contribute to the definition of reference-grade observing network and standards. The GCOS science panels should identify stakeholders who will perform this review and regularly check all ECV products are being reviewed. | Increase quality and availability of climate observations | Organizations listed in Annex A. GCOS panels to maintain oversight. | Develop and demonstrate review process in 2017. Review each ECV’s observing systems at least every four years. | Reports of results of ECV reviews produced by panels each year. | US$ 100 000–1 million also part of the work of panels | N
Action G14: | Maintain and improve coordination | Maintain and improve coordination with other global observing systems (such as GOOS and FluxNet), satellite agencies (especially through CGMS and CEOS), those providing climate services (such as GFCS, Copernicus and NMHS climate departments), GEO flagships (such as GEO Carbon, GFOI, Blue Planet: Oceans and Society), Regional Climate Centres and WMO technical commissions and other users such as UNFCCC and IPCC | Improved and more efficient observation systems. | GCOS Secretariat and Science Panels | On going | Reports to GCOS Steering Committee and science panels | Part of ongoing tasks of GCOS | N
Action G15: | Open data policies | Ensure free and unrestricted data access by encouraging that data policies facilitating the open exchange and archiving of all ECVs are followed; encouraging national parties to develop new data policies where appropriate, assessing and regularly reporting of status of data access | Access to data by all users in all countries at minimum cost | Parties and international agencies, appropriate technical commissions and international programmes; GCOS Secretariat. | Continuing, of high priority. | Number of countries adhering to data policies favouring free and open exchange of ECV data. | US$ 100 000–1 million | Y | We can generate an indicator, based on the ECV Inventory 'Accessibility' information.
Action G16: | Metadata | 1. GCOS to work with WMO to ensure that the WIGOS metadata standard meets GCOS requirements for metadata, where relevant; 2. Develop metadata standards for those observing systems where they do not exist. | Improved access and discoverability of datasets | Operators of GCOS.related systems, including data centres | Continuous | Number of ECV-related datasets accessible through standard mechanisms | US$ 100 000–1 million (US$ 20 000 per data centre) (10% in non-Annex-I Parties) | N | Standard mechanisms? Can we actually provide any feedback here, for the space-observable ECVs?
Action G17: | Support to national data centres | Ensure national data centres are supported to enable timely, efficient and quality-controlled flow of observations to international data centres where they exist; ensure timely flow of feedback from monitoring centres to observing network operators | Long-term, sustainable, provision of timely data and improved data quality | Parties with coordination by appropriate technical commissions and international programmes | Continuing, of high priority | Data receipt at centres and archives | US$ 10–30 million (70% in non-Annex-I Parties) | N
Action G18: | Long-term accessibility of data | Ensure that data centres follow best practice in data stewardship to ensure long-term preservation of data according to guidance to be developed by WMO | Preservation of data for future generations | Funding agencies for data centre | Ongoing | Data held in compliant data centres and holdings and accessible to users | US$ 1–10 million | N
Action G19: | Data access and discoverability | Identify and develop means of discovering and accessing all relevant CDRs and other relevant products. Ensure there is access to metadata that clearly distinguishes each data product and describes its adherence to the GCMP | Increase access to CDRs | GCOS, GEO, US National Oceanographic and Atmospheric Administration (NOAA) | Develop plans in 2017 | Reports of results of ECV reviews produced by panels each year | US$10 000–100 000 | N
Action G20: | Use of digital object identifiers for data records | GCOS to encourage international data centres to introduce DOIs for their data records of ECV and recommend datasets producers to follow this practice | Help researchers to discover relevant data more easily | GCOS panels | Ongoing | Number of data records having an assigned DOI | Should be part of network planning and implementation. | Y | Observe number for satellite data records in ECV Inventory
Action G21: | Collaboration with WMO CCl on climate data management | GCOS secretariat to engage with WMO CCl on development of regulatory and guidance on climate data management | Users to climate data will have easier access to data. | GCOS secretariat and WMO CCl | Ongoing until 2019 | Guidance material publication | None | N
Action G22: | Implementation of new production streams in global reanalysis | Continue comprehensive global reanalyses and implement planned new production streams using improved data-assimilation systems and better collections of observations; provide information on the uncertainty of products and feedback on data usage by the assimilation systems | Improved reanalysis datasets | Global reanalysis production centres | Ongoing | Number and specifications of global reanalyses in production; improved results from evaluations of performance; user uptake of uncertainty information; extent to which observational archives are enhanced with feedback from reanalyses | US$ 10–30 million | N
Action G23: | Develop coupled reanalysis | Further develop coupled reanalysis and improve the coupled modelling and data assimilation methodology | Provide coupled reanalysis data sets | Global reanalysis production centres and other centres undertaking research in data assimilation | Ongoing | Number, specification and demonstrated benefits of coupled reanalyses | US$ 1–10 million | N
Action G24: | Improve capability of long-range reanalysis | Improve the capability of long-scale reanalysis using sparse observations datasets | Provide longer reanalysis datasets | Global reanalysis production centres and other centres undertaking research in data assimilation | Ongoing | Demonstrated improvements in the representation of long-term variability and change in century-scale reanalyses | US$ 1–10 million | N
Action G25: | Implementation of regional reanalysis | Develop and implement regional reanalysis and other approaches to downscaling the information from global data products | Capability to capture climate variability on a regional scale | Dataset producers | Ongoing | Number and evaluated performance of regional reanalyses and other downscaled datasets | US$ 1–10 million | N
Action G26: | Preservation of early satellite data | Ensure long-term data preservation of early satellite raw and level 1 data, including metadata | Extend CDRs back in time | Space agencies | Ongoing | Data archive statistics at space agencies for old satellite data | US$ 1–10 million | Y | Can provide feedback, from comparison of Inventory #2 and #3 on instrument data usage, but could also collate information from agencies in WGClimate on data rescue activities. Have a nice example of EUM NSIDC collaboration.
Action G27: | Recovery of instrumental climate data | Continue the recovery of instrumental climate data that are not held in a modern digital format and encourage more imaging and digitization | Improve access to historical observations datasets | Agencies holding significant volumes of unrecovered data; specific projects focused on data recovery | Ongoing | Data Increases in archive-centre holdings and data used in product generation; register entries recording data-recovery activities (see following action) | US$ 1–10 million | N
Action G28: | Register of data-recovery activities | Populate and maintain a register or registers of data-recovery activities | Facilitate planning of data rescue | WMO CCl and other international bodies with related responsibilities; institutions hosting registers | Ongoing | Existence and degree of population of register(s). | US$ 1 000–10 000 | N | Action should be extended to satellite data or its mayby G26
Action G29: | Scanned records | Lodge scans with an appropriate international data centre if digitization does not follow scanning; assemble classes of scanned record suitable for digitization, for example by crowdsourcing | Facilitate planning of data rescue | Institutions that have scanned data but not undertaken digitization; receiving data centres for assembly of records | Ongoing | Statistics on holdings and organization of scanned records by data centres | US$ 10 000–100 000 | N | Action should be extended to satellite data or its mayby G26
Action G30: | Sharing historical data records | Share recovered historical data records | Improved access to historical datasets to all users | Institutions that have recovered data records but not made them widely available. | Ongoing | Number of released data records as reported in registers | US$ 10 000–100 000 | N
Action G31: | Improve gravimetric measurements from space | Prepare for satellite missions to provide continuity and consider improved performance to meet the observational requirements in Table 2 | Improved monitoring of water transport and distribution. | Space agencies. | For 2023 | Published plans and agreed missions | US$100 000–1million | Y | May update info from SARGIP 2017
Action G32: | Improved bathymetry | Support increased level of multibeam seabed mapping both synchronously with ocean observation initiatives and separately as dedicated basin-scale mapping initiatives | Better representation of ocean volume, improved ability to model ocean currents and mixing | Institutions that fund vessel-based science studies and programmes and/or have access to survey platforms with existing multibeam survey infrastructure. | For 2023 | Availability of improved bathymetry data | US$ 30–100 million | Y | May update info from SARGIP 2017

## Atmosphere
6 | LIST OF ACTIONS
6.2 | Atmospheric Domain Actions
# | Title | Action | Benefit | Time frame | Who | Performance indicator | Annual cost | Adressed in SARGIP 2017 | ECV | Comment
Action A1: | Near-real-time and historical GCOS Surface Network availability | Improve the availability of near-real-time and historical GSN data especially over Africa and the tropical Pacific | Improved access for users to near-real-time GSN data | National Meteorological Services, regional centres in coordination/cooperation with WMO CBS, and with advice from AOPC | Continuous for monitoring GSN performance and receipt of data at archive centre | AOPC review of data archive statistics at the World Data Center for Meteorology at Asheville, NC, USA, annually and national communications to UNFCCC | US$ 10–15 million | N
Action A2: | Land database | Set up a framework for an integrated land database which includes all the atmospheric and surface ECVs and across all reporting timescales | Centralized archive for all parameters. Facilitates QC among elements, identifying gaps in the data, efficient gathering and provision of rescued historical data, integrated analysis and monitoring of ECVs. Supports climate assessments, extremes, etc. Standardized formats and metadata. | NCEI and contributing centres | Framework agreed by 2018 | Report progress annually to AOPC | US$ 100 00–1million | N
Action A3: | International exchange of SYNOP and CLIMAT reports | Obtain further progress in the systematic international exchange of both hourly SYNOP reports and daily and monthly CLIMAT reports from all stations | Enhanced holdings data archives | NMHSs, regional centres in coordination/cooperation with WMO CBS, and with advice from AOPC | Continuous, with significant improvement in receipt of RBSN synoptic and CLIMAT data by 2019 | Data archive statistics at data centres | US$ 100 000–1 million | N
Action A4: | Surface observing stations: transition from manual to automatic | Follow guidelines and procedures for the transition from manual to automatic surface observing stations | More stable time series | Parties operating GSN stations for implementation. WMO CCl, in cooperation with WMO CIMO, WMO CBS for review | Ongoing | Implementation noted in national communications and relevant information provided | US$ 30–100 million | N
Action A5: | Transition to BUFR | Encourage dual transmission of TAC and BUFR for at least 6 months and longer if inconsistencies are seen (to compare the two data streams for accuracy). | Transition to BUFR does not introduce discontinuities in the datasets. BUFR allows metadata to be stored with data. | Parties operating GSN stations for implementation | Ongoing for implementation; review by 2018 | Proven capability to store BUFR messages giving same quality or better as TAC data | US$ 100 000–1 million | N
Action A6: | Air temperature measurements | Enhance air temperature measurements networks in remote or sparsely populated areas and over the ocean | Improved coverage for better depiction of climate system | National Parties and international coordination structures such as the Global Cryosphere Watch (GCW) | Ongoing | Coverage of air-temperature measurements | US$ 10–30 million | N
Action A7: | Atmospheric pressure sensors on drifting buoys | Enhance to 100% the percentage of drifting buoys incorporating atmospheric pressure sensors, in particular by benefiting from barometer-upgrade programmes | Measurements over oceans of surface pressure will improve coverage. | Parties deploying drifting buoys and buoy-operating organizations, coordinated through JCOMM, with advice from OOPC and AOPC | Ongoing | Percentage of buoys with sea-level pressure (SLP) sensors in tropics and sub-tropics | US$ 10 000–100 000 | N
Action A8: | Provide precipitation data to the Global Precipitation Climatology Centre | Submit all precipitation data from national networks to the Global Precipitation Climatology Centre at the Deutscher Wetterdienst | Improved estimates of extremes and trends, enhanced spatial and temporal detail that address mitigation and adaptation requirements | National Meteorological and Water-resource Services, with coordination through the WMO CCl and the GFCS. | Ongoing | Percentage of nations providing all their holdings of precipitation data to international data centres. | US$ 100 000–1 million | N
Action A9: | Submit water-vapour data | Submit water-vapour (humidity) data from national networks and marine platforms to the international data centres | Improved coverage of surface water-vapour measurements | NMHSs, through WMO CBS and international data centres, with input from AOPC | Ongoing | Data availability in analysis centres and archive and scientific reports on the use of these data | US$ 100 000–1 million | N
Action A10: | Incorporating national sunshine records into data centres | National sunshine records should be incorporated into International Data Centres. | Better description of surface radiation fields | NMHSs | Implement in next 2 years | Sunshine record archive established in international data centres in analysis centres by 2018 | US$ 1–10 million | N
Action A11: | Operation of the the GCOS Baseline Network for Surface Radiation | Ensure continued long-term operation of the BSRN and expand the network to obtain globally more representative coverage and improve communications between station operators and the archive centre | Continuing baseline surface radiation climate record at BSRN sites | Parties’ national services and research programmes operating BSRN sites in cooperation with AOPC and the WCRP GEWEX Radiation Panel | Ongoing | The number of BSRN stations regularly submitting valid data to international data centres | US$ 100 000–1million | Y |  | ECV Inventory may contains information on usage of BSRN for validation of satellite records-
Action A12: | Surface radiation data to the World Radiaiton Data Centre | Submit surface radiation data with quality indicators from national networks to the WRDC; expand deployment of surface radiation measurements over ocean | Expand central archive; data crucial to constrain global radiation budgets and for satellite product validation; more data over ocean would fill an existing gap. | NMHSs and others, in collaboration with WRDC | Ongoing | Data availability in WRDC | US$ 1–10 million | N
Action A13: | Implement vision for future of GCOS Upper-Air Network operation | Show demonstrable steps towards implementing the vision articulated in the GCOS Networks Meeting in 2014[1] relating to the future of GUAN operation | Improved data quality, better integrated with GRUAN and more closely aligned with WIGOS framework | Task team of AOPC with GCOS Secretariat in collaboration with relevant WMO commissions and WIGOS | 2019 for adoption at Nineteenth World Meteorological Congress | Annual reporting in progress at AOPC of task team | US$ 100 000–1 million | N
Action A14: | Evaluation of benefits for the GCOS Upper-Air Network | Quantify the benefits of aspects of GUAN operation including attaining 30 hPa or 10 hPa, twice-daily as opposed to daily ascents and the value of remote island GUAN sites | Better guidance to GUAN management, improved scientific rationale for decision-making | NWP and reanalysis centres | Completed by 2018 | Published analysis (in peer reviewed literature plus longer report) | US$ 10 000–100 000 | N
Action A15: | Implementation of Reference Upper-Air Network | Continue implementation of GRUAN metrologically traceable observations, including operational requirements and data management, archiving and analysis and give priority to implementation of sites in the tropics, South America and Africa | Reference-quality measurements for other networks, in particular GUAN, process understanding and satellite cal/val. | Working Group on GRUAN, NMHSs and research agencies, in cooperation with AOPC, WMO CBS and the Lead Centre for GRUAN | Implementation largely completed by 2025 | Number of sites contributing reference-quality data streams for archival and analysis and number of data streams with metrological traceability and uncertainty characterization; better integration with WMO activities and inclusion in the WIGOS manual. | US$ 10–30 million | Y |  | ECV Inventory may contains information on usage of BSRN for validation of satellite records-
Action A16: | Implementation of satellite calibration missions | Implement a sustained satellite climate calibration mission or missions | Improved quality of satellite radiance data for climate monitoring | Space agencies | Ongoing | Commitment to implement by the next status report in 2020; proof-of-concept proven on ISS pathfinder | US$ 100–300 million | Y |  | May update info from SARGIP 2017
Action A17: | Retain original measured values for radiosonde data | For radiosonde data and any other data that require substantive processing from the original measurement (e.g. digital counts) to the final estimate of the measurand (e.g. T and q profiles through the lower stratosphere); the original measured values should be retained to allow subsequent reprocessing. | Possibility to reprocess data as required, improved data provenance | HMEI (manufacturers), NMHSs, archival centres. | Ongoing. | Original measurement raw data and metadata available at recognized repositories | US$ 100 000–1million | N
Action A18: | Hyperspectral radiances reprocessing | Undertake a programme of consistent reprocessing of the satellite hyperspectral sounder radiances | Consistent time series of hyperspectral radiances for monitoring and reanalyses, improved CDRs computed from the FCDRs | Space agencies | Ongoing | Reprocessed FCDRs available for hyperspectral sounders | US$ 100 000–1million | Y |  | Some information on the existence of FCDRs could be inferred from the ECV Inventory
Action A19: | Reprocessing of atmospheric motion vectors | Continue reprocessing of AMVs derived from geostationary satellite imagery in a coordinated manner across agencies | Consistent time series of AMVs for monitoring and reanalyses, improved CDRs computed from the FCDRs | Space agencies | Ongoing | Reprocessed FCDRs available for upper-air winds | US$ 100 000–1 million | Y | Upper-air winds | Some information on the existence of FCDRs could be inferred from the ECV Inventory
Action A20: | Increase the coverage of aircraft observations | Further expand the coverage provided by AMDAR, especially over poorly observed regions such as Africa and South America | Improved coverage of upper-air wind for monitoring and reanalysis | NMHSs, WIGOS, RAs I and III. | Ongoing | Data available in recognized archives | US$ 1–10 million | N
Action A21: | Implementation of space-based wind-profiling system | Assuming the success of ADM/Aeolus, implement an operational space-based wind profiling system with global coverage | Improved depiction of upper-air windfields: improved reanalyses, 3D aerosol measurements as a byproduct | Space agencies | Implement once ADM/Aeolus concept is proven to provide benefit | Commitment to launch ADM follow-on mission | US$ 100–300 million | Y |  | May update info from SARGIP 2017
Action A22: | Develop a repository of water vapour climate data records | Develop and populate a globally recognized repository of GNSS zenith total delay and total column water data and metadata | Reanalyses, water vapour CDRs | AOPC to identify the appropriate responsible body | By 2018 | Number of sites providing historical data to the repository | US$ 100 000–1 million | Y |  | ECV Inventory and gapanaylsis provides information. Action is very fuzzy, KPI indicates only ground based is thpugth of which doesn't fit with reanalysis.
Action A23: | Measure of water vapour in the upper troposphere/lower stratosphere | Promote the development of more economical and environmentally friendly instrumentation for measuring accurate in situ water-vapour concentrations in the UT/LS | Improved UT/LS water vapour characterization, water-vapour CDRs | NMHSs, National measurements institutes, HMEI and GRUAN | Ongoing | Number of sites providing higher-quality data to archives | US$ 10–30 million | N
Action A24: | Implementation of archive for radar reflectivities | To implement a global historical archive of radar reflectivities (or products of reflectivities are not available) and associated metadata in a commonly agreed format | Better validation of reanalyses, improved hydrological cycle understanding | NMHSs, data centres, WIGOS | Ongoing | Data available in recognized archive, agreed data policy | US$ 1–10 million | N
Action A25: | Continuity of global satellite precipitation products | Ensure continuity of global satellite precipitation products similar to GPM | Precipitation estimates over oceans for global assessment of water-cycle elements and their trends | Space agencies | Ongoing | Long-term homogeneous satellite-based global precipitation products | US$ 30–100 million | Y | Precipitation | Gap Analysis
Action A26: | Development of methodology for consolidated precipitation estimates | Develop methods of blending raingauge, radar and satellite precipitation | Better precipitation estimates | WMO technical commissions. | By 2020 | Availability of consolidated precipitation estimates | US$ 10 000–100 000 | Y |  | Maybe gap analysis if we have blended products.
Action A27: | Dedicated satellite Earth Radiation Budget mission | Ensure sustained incident total and spectral solar irradiances and ERB observations, with at least one dedicated satellite instrument operating at any one time | Seasonal forecasting, reanalyses, model validation. | Space agencies | Ongoing | Long-term data availability at archives | US$ 30–100 million | Y | Earth Radiation Budget | Feedback based on contents of the ECV Inventory
Action A28: | In situ profile and radiation | To understand the vertical profile of radiation requires development and deployment of technologies to measure in-situ profiles. | Understanding of 3D radiation field, model validation, better understanding of radiosondes | NMHSs, National measurements institutes, HMEI | Ongoing | Data availability in NMS archives | US$ 1–10 million | N
Action A29: | Lightning | To define the requirement for lightning measurements, including data exchange, for climate monitoring and to encourage space agencies and operators of ground-based systems to provide global coverage and reprocessing of existing datasets | Ability to monitor trends in severe storms | GCOS AOPC and space agencies | Requirements to be defined by 2017 | Update to Annex A for lightning and commitments by space agencies to include lightning imagers on all geostationary platforms. Reprocessed satellite datasets of lightning produced | US$ 10–30 million | Y | Lightning | Feedback based on contents of the ECV Inventory
Action A30: | Water vapour and ozone measurement in upper troposphere and lower and upper stratosphere | Re-establish sustained limb-scanning satellite measurement of profiles of water vapour, ozone and other important species from UT/LS up to 50 km | Ensured continuity of global coverage of vertical profiles of UT/LS constituents | Space agencies | Ongoing, with urgency in initial planning to minimize data gap | Continuity of UT/LS and upper stratospheric data records | US$ 30–100 million | Y | Water Vapour; Ozone | Feedback based on contents of the ECV Inventory
Action A31: | Validation of satellite remote-sensing | Engage existing networks of ground-based, remote sensing stations (e.g. NDACC, TCCON, GRUAN) to ensure adequate, sustained delivery of data from MAXDOAS, charge coupled device (CCD) spectrometers, lidar, and FTIR instruments for validating satellite remote-sensing of the atmosphere | Validation, correction and improvement of satellite retrievals | Space agencies, working with existing networks and environmental protection agencies | Ongoing, with urgency in initial planning to minimize data gap | Availability of comprehensive validation reports and near-real-time monitoring based on data from the networks | US$ 1–10 million | Y |  | Feedback from ECV Inventory if used for validation.
Action A32: | Fundamental Climate Data Records and Climate Data Records for greenhouse gas and aerosols ECVs | Extend and refine the satellite data records (FCDRs and CDRs) for GHG and aerosol ECVs | Improved record of GHG concentrations | Space agencies | Ongoing | Availability of updated FCDRs and CDRs for GHGs and aerosols | US$ 1–10 million | Y | GHG, Aerosols | Direct feedback for TCDRs, indirect for FCDRs
Action A33: | Maintain WMO GAW CO2 and CH4 monitoring networks | Maintain and enhance the WMO GAW Global Atmospheric CO2 and CH4 monitoring networks as major contributions to the GCOS Comprehensive Networks for CO2 and CH4. Advance the measurement of isotopic forms of CO2 and CH4 and of appropriate tracers to separate human from natural influences on the CO2 and CH4 budgets | A well-maintained, ground-based and in situ network provides the basis for understanding trends and distributions of GHGs. | National Environmental Services, NMHSs, research agencies, and space agencies under the guidance of WMO GAW and its Scientific Advisory Group on Greenhouse Gases | Ongoing | Data flow to archive and analysis centres | US$ 1–10 million | N
Action A34: | Requirements for in situ column composition measurements | Define the requirements for providing vertical profiles of CO2, CH4 and other GHGs, using recently emerging technology, such as balloon capture technique[2] | Ability to provide widespread, accurate, in situ vertical profiles economically; an excellent tool for validating satellite retrievals and improving transport models | GCOS AOPC and space agencies | Requirements to be defined by 2018 | Update to Annex A to include vertical profiles and XCO2 (the dry-air column-averaged mole fraction of CO2) | US$ <5 million | N
Action A35: | Space-based measurements of CO2 and CH4 implementation | Assess the value of the data provided by current space-based measurements of CO2 and CH4, and develop and implement proposals for follow-on missions accordingly | Provision of global records of principal greenhouse gases; informing decision-makers in urgent efforts to manage GHG emissions | Research institutions and space agencies | Assessments are ongoing and jointly pursued by research institutions | Approval of subsequent missions to measure GHGs | US$ 30–100 million | Y | GHG | ECV Inventory may contains information on usage of data+A40:K40 for validation of satellite records-
Action A36: | N2O, halocarbon and SF6 networks/measurements | Maintain networks for N2O, halocarbon and SF6 measurements | Informs the parties to the Montreal Protocol, provides records of long-lived, non-CO2 GHGs and offers potential tracers for attribution of CO2 emissions. | National research agencies, national environmental services, NMHSs, through WMO GAW | Ongoing | Data flow to archive and analysis centres | US$ 30–100 million | Y
Action A37: | Ozone network coverage | Urgently restore the coverage the extent possible and maintain the quality and continuity of the GCOS Global Baseline (profile, total and surface level) Ozone Networks coordinated by WMO GAW. | Provides validation of satellite retrievals and information on global trends and distributions of ozone. | Parties’ national research agencies and NMHSs, through WMO GAW and network partners, in consultation with AOPC | Ongoin. | Improved and sustained network coverage and data quality | US$ 1–10 million | Y |  | May from ECV Inventory if used for validation of existing data records
Action A38: | Submission and dissemination of ozone data | Improve timeliness and completeness of submission and dissemination of surface ozone, ozone column and profile data to users, WDCGG and WOUDC | Improves timeliness of satellite retrieval validation and availability of information for determining global trends and distributions of ozone. | Parties’ national research agencies and services that submit data to WDCGG and WOUDC, through WMO GAW and network partners. | Ongoing | Network coverage, operating statistics and timeliness of delivery. | US$ 100 000–1 million | N
Action A39: | Monitoring of aerosol properties | Provide more accurate measurement-based estimates of global and regional direct aerosol radiative forcing (DARF) at the top of the atmosphere and its uncertainties, and determine aerosol forcing at the surface and in the atmosphere through accurate monitoring of the 3D distribution of aerosols and aerosol properties. Ensure continuity of monitoring programs based on in situ ground-based measurement of aerosol properties. | Reducing uncertainties in DARF and the anthropogenic contributions to DARF, and the uncertainty in climate sensitivity and future predictions of surface temperature. Better constraints on aerosol type needed for atmospheric correction and more accurate ocean property retrieval than currently available. | Parties’ national services, research agencies and space agencies, with guidance from AOPC and in cooperation with WMO GAW and AERONET | Ongoing, baseline in situ components and satellite strategy is currently defined. | Availability of the necessary measurements, appropriate plans for future | US$ 10–30 million | Y | Aerosols | Info on data records in Gap Analysis report.
Action A40: | Continuity of products of precursors of ozone and secondary aerosols | Ensure continuity of products based on space-based, ground-based and in situ measurements of the precursors (NO2, SO2, HCHO, NH3 and CO) of ozone and secondary aerosol and derive consistent emission databases, seeking to improve spatial resolution to about 1 x 1 km2 for air quality | Improved understanding of how air pollution influences climate forcing and how climate change influences air quality. | Space agencies, in collaboration with national environmental agencies and NMHSs | Ongoing | Availability of the necessary measurements, appropriate plans for future missions, and derived emission databases | US$ 100–300 million | Y | Precursors | Info on data records in Gap Analysis report.

## Ocean
6 | LIST OF ACTIONS
6.3 | Ocean Domain Actions
# | Title | Action | Benefit | Time frame | Who | Performance indicator | Annual cost | Adresses in SARGIP 2017 | ECV | Comment
Action O1: | Coordination of enhanced shelf and coastal observations for climate | Assess existing international, national and regional plans that address the needs to monitor and predict the climate of coastal regions and develop plans were they do not exist. | Detailed specific observational requirements in the coastal regions for improved understanding, assessment and prediction of the impact of climate on the coastal environment | 2026, with interim assessment of progress by 2021 | GOOS, GRAs, JCOMM OCG | An internationally recognized coordination activity | US$ 10–30 million | N
Action O2: | Integration and data access | Improve discoverability and interoperability, comparability and traceability of ocean observations among ocean observing networks for all ECVs (including ECVs of other domains). | Improved access to data, ease of integration across data sources | Continuous | Parties’ national research programmes and data-management infrastructure, OOPC, International Ocean Carbon Coordination Project (IOCCP), the WCRP Data Advisory Council (WDAC), JCOMM Data Management Programme Area (DMPA), GEO Blue Planet | Timely and open access to quality-controlled observational data | US$ 1–10 million | N
Action O3: | Data quality | Sustain and increase efforts for quality control and reprocessing of current and historical data records | Improved quality of ocean climate data | Continuous. | Parties’ national ocean research agencies and data-management infrastructure, supported by JCOMM DMPA, IODE, WCRP CLIVAR Project | Improved record of uniform quality control | US$ 1–10 million | N
Action O4: | Development of climatologies and reanalysis products | Maintained research and institutional support for the production of ocean gridded data products and reanalysis products, and coordinated intercomparison actrivities | Improved quality and availability of integrated ocean products for climate change detection and validation of climate projections and initialization of weather- and marine-forecasting models | Continuous | Parties’ national research programmes and operational agencies, WCRP-CLIVAR GSOP, GODAE OceanView and the JCOMM Expert Team on Operational Ocean Forecasting (ETOOFS), IOCCP | Regular updates of global ocean synthesis products | US$1–10 million | N
Action O5: | Sustained support for ocean observations | Strengthen funding of the ocean observing system to move towards a more sustained long-term funding structure and broaden support by engaging more agencies and nations in sustained ocean observing through capacity building | A more resilient observing system that is less exposed to changes in national research priorities. | 2026 | Parties’ national research programmes, funding streams and operational agencies, capacity building through the Partnership for Observations of the Global Ocean (POGO). | Observing system performance indicators continuously at or above 90%, increasing number of agencies and nations contributing to sustained observing. | US$30–100 million | N
Action O6: | Technology development | Continued support for development of satellite capabilities, autonomous platforms and climate-quality sensors, from pilot phase to mature stage | Continued improvements to the sustained observing system to fill gaps, take new measurements, at lower cost per observation. | Continuous | National research programmes supported by the GOOS expert panels, CEOS Constellations Teams, JCOMM OCG and user groups. | Amount of climate-quality data provided in near-real time to internationally agreed data centres | US$ 10–30 million | N
Action O7: | Observing system development and evaluation | Support and engage in systems-based observing system development projects established through GOOS as detailed in this Plan and efforts for the ongoing evaluation of the observing system | Continued improvements to the sustained observing system ensure it is robust, integrated and meets future needs. | Continuous | National research programmes supported by GOOS expert panels and regional alliances | Periodic evaluation of observing system against requirements and expansion of support for sustained observations | US$ 100 000–1million (mainly to Annex I Parties). | N
Action O8: | Satellite sea-surface temperature product development | Continue the provision of best possible SST fields based on a continuous coverage mix of polar orbiting (including dual view) and geostationary IR measurements, combined with passive MW coverage, and appropriate linkage with the comprehensive in situ networks | Global routine calibrated mapping of SST for climate monitoring and weather and subseasonal to seasonal prediction systems | Continuous | Space agencies, coordinated through Global High Resolution Sea Surface Temperature Project (GHRSST), CEOS, CGMS and WMO Space Programme | Agreement of plans for maintaining a CEOS Virtual Constellation for SST, ongoing satellite operation, routine delivery of SST products | US$ 1–10 million | Y | SST | Gap Analysis shows what is missing.
Action O9: | Upper-ocean temperature observing system | Maintain a global upper ocean (0-2 000 m) temperature observing system for the assessment of ocean temperature and heat content change and its contribution to sea-level rise | High-quality ocean temperature time series for accurate estimates of annual ocean heat storage as a function of depth and its spatial distribution to assess the role on the ocean in the Earth’s energy balance and ocean warming contribution to sea-level change | Continuous | Parties’ national agencies working with GOOS observational networks (Drifters, CEOS, Argo, SOOP, OceanSITES), in cooperation with the Observations Coordination Group of JCOMM. | Spatial coverage, interoperability of observations platforms, annually updated global upper-ocean temperature records | US$ 30–100 million | Y | SST | Maybe if the surface is included in this Action.
Action O10: | Full-depth temperature observing system | Develop and begin implementation of a full-depth ocean temperature observing system to support the decadal global assessment of the total ocean heat content and thermosteric sea-level rise | High-quality, deep-ocean temperature time series for accurate estimates of biennial to decadal ocean heat storage below 2 000 m and its spatial distribution to assess the role of the ocean in the Earths energy balance and ocean-warming contribution to sea-level change | Observational system in place by 2026 | Parties, national agencies working with GOOS observational networks (Argo, GO-SHIP, OceanSITES), in cooperation with the JCOMM Observations Coordination Group | Design study completed and targeted implementation begun; spatial coverage, interoperability of observations platforms | US$ 30–100 million | N
Action O11: | Ocean salinity observing system | Maintain and grow a global ocean salinity observing system for the assessment of ocean salinity and freshwater content change and its contribution to global hydrological cycle | High-quality ocean salinity time-series for accurate estimates of annual (0-2 000 m) to decadal (below 2 000 m) ocean freshwater changes and its spatial distribution to assess the role on the ocean in the Earths hydrological cycle and contribution to sea-level change. Improved initialisation of weather- and climate-forecasting systems | Continuous. | Parties’ national agencies working with GOOS observational networks (CEOS, SOOP, Argo, GO-SHIP, OceanSITES), in cooperation with DOOS and the JCOMM Observations Coordination Group | Spatial coverage, interoperability of observations platforms’ annually updated global ocean salinity records | US$ 30–100 million (10% in non-Annex I Parties) | Y |  | Sapace Segment consideration from gapa analysis.
Action O12: | Ocean current gridded products | Maintain gridded ocean-surface and subsurface current products based on satellite, drifting-buoy and Argo programsme, other observations and data-assimilating models | High-quality ocean-current observations for climate services and marine operational systems | Continuous | Parties’ national agencies working with CEOS, GOOS observational networks (SOOP, Argo, GO-SHIP, OceanSITES, Drifters) in cooperation with the JCOMM Observations Coordination Group, Godea OceanView and reanalysis projects | Spatial coverage, interoperability of observation platforms | US$ 1–10 million (10% in non-Annex I Parties) | Y | Ocean surface currents | Gap analysis
Action O13: | Sea-level observations | Maintain and develop a global sea-surface-height observing system from observational and satellite networks for annual assessment of sea level and sea-level rise | Quality control and accurate global sea level and regional sea-level variability dataset | Continuous | Parties’ national agencies working with CEOS, GOOS observational networks (e.g. GLOSS), in cooperation with the JCOMM Observations Coordination Group | Spatial coverage, interoperability of observations platforms, annually updated global sea-level data | US$ 30–100 million | Y | Sea Level | Gap Analysis
Action O14: | Contributing to sea-state climatologies | Maintain and improve the global sea-state observing system from the observational networks to inform wave models/climatologies for assessment of wave climate, its trend and variability and contribution to extremes of sea level; expand observations on surface-reference moorings and drifters | Routine observations of wave climate and extremes in support of marine/climate services | Continuous | Parties’ national agencies coordinated through GOOS, OOPC, GRAs, OceanSITES, DBCP, guidance from the JCOMM Expert Team on Waves and Coastal Hazard Forecasting Systems (ETWCH) | Number of global wave observations available routinely at International Data Centres. | US$ 1–10 million | N
Action O15: | In situ sea-ice observations | Plan, establish and sustain systematic in situ observations from sea ice, buoys, visual surveys (SOOP and aircraft) and in-water upward-looking Sonar (ULS) | Long time series for validations of satellite data and model fields; short- and long-term forecasting of sea-ice conditions; ocean-atmosphere-sea ice interaction and process studies | Integrated Arctic Observing System design and demonstration project funded by EU for | 2017–2020 | National and international services and research programmes, Copernicus; coordination through Arctic Council, EU-PolarNET, Arctic-ROOS (in EuroGOOS), CLIVAR, CLIC, JCOMM, OOPC | Establishment of agreement and frameworks for coordination and implementation of sustained Arctic (EU-PolarNet and Arctic-ROOS, which will be extended with the new funded project (see time frame)) and Southern Ocean observations (SOOS) | N |  | US$ 30–100 million
Action O16: +A20:K20 | Ocean-surface stress observations | Develop requirements and review system design (satellite and in situ) for observing OSS ECV and commence implementation | Agreed plan for design of surface-stress observing system to improve ocean-surface-stress products | Internationally agreed plans published and establish GDACs by 2019 | CEOS and in situ networks | Publication of internationally agreed plans, establishment of agreements/frameworks for coordination according to plan | US$ 100 000–1 million | Y | Ocean surface stress
Action O17: | Ocean-surface heat-flux observing system | Develop requirements and system design for observing Ocean surface heat flux ECV (utilizing indirect and direct methods) and commence implementation | Agreed plan for high-quality heat-flux data required to improve surface flux products | Complete programme design and begin implementation of observational system by 2019 | GOOS observational networks (CEOS, OceanSITES, SOOP), in cooperation with the JCOMM Observations Coordination Group | Publication of observing network plan; spatial coverage, interoperability of observation platforms | US$ 10–30 million | Y
Action O18: | Surface ocean partial pressure of CO2,moorings | Sustain the surface reference mooring pCO2 network and increase the number of sites to cover all major biogeochemical regions to resolve seasonal cycle | Increased information on seasonal and longer variability in key ocean areas | Continuous | IOCCP, in consultation with OOPC; implementation through national services and research programmes | Flow of data of adequate quality into SOCAT | US$ 1–10 million | N
Action O19: | Building multidisciplinary time series | Add inorganic carbon and basic physical measurements to existing biological timeseries, considering particularly spatial gaps in current observing system, aiming for balanced representation of the full range of natural variability | Improved understanding of the regional effects of ocean acidification | Continuous | Parties’ national research programmes supported by GOA-ON, GOOS Biogeochemistry and Biology and Ecosystems expert panels. | Flow of data of adequate quality to data centres | US$ 1–10 million | N
Action O20: | Nutrient observation standards and best practices | Increase the use of nutrient CRMs on ship-based hydrographic programmes | Increased accuracy of nutrient measurements | Continuous | IOCCP, in consultation with OOPC; implementation through national services and research programmes; SCOR working group 147 “Towards comparability of global oceanic nutrient data" | Increased consistency of nutrient data | US$ 1–10 million | N
Action O21: | Sustaining tracer observations | Maintain capacity to measure transient tracers on the GO-SHIP network. Encourage technological development to encompass additional tracers that provide additional information on ventilation. | Information on ocean ventilation and variability in ventilation | Continuous | IOCCP, in consultation with OOPC; implementation through national services and research programmes | Number of high-quality transient tracer measurements on the repeat hydrography programme | US$ 1–10 million | N
Action O22: | Develop sustained N2O observations | Develop an observing network for ocean N2O observations, with particular emphasis on regions with known high oceanic N2O production/emission rates | Improved estimate of oceanic emissions by improved spatial and temporal coverage; detecting seasonal and interannual variability | Continuous | IOCCP, in consultation with OOPC; implementation through national services and research programmes, SCOR WG 143 Dissolved N2O and CH4 measurements: working towards a global network of ocean time series measurements of N2O and CH4 | Flow of data of adequate quality into MEMENTO | US$ 1–10 million | N
Action O23: : | In situ ocean colour radiometry data | Continue support for generation and maintenance of climate-quality in situ OCR data, including: developing new high-resolution sensors of high radiometric quality; for improving satellite algorithms; validating products and for establishing product uncertainties characterization, with global coverage and validity, including coastal (Case-2) waters, and capable of dealing with user requirements for products at a variety of time and space scales | Monitoring of changes and variability in ocean colour and derived products | Implement plan beyond 2017 after completion of ESA’s OC-CCI activities | CEOS space agencies, in consultation with IOCCG and GEO through INSITU OCR initiative of IOCCG, and in accordance with the recommendations contained in the IOCCG INSITU-OCR White Paper (see http://www.ioccg.org/groups/INSITU-OCR_White-Paper.pdf). | Free and open access to up-to-date, multi-sensor global products for climate research; flow of data into agreed archives | US$ 30–100 million | Y | Ocean colour | Action Title doesn't fit to the rest of description, is this really purely in-situ, why space agencies then. ECV Inventory provides info on Ocean Colour data sets.
Action O24: | Ocean colour algorithm development | Support continued research and technology development to ensure that the best and the most up-to-date algorithms are used for processing the ocean-colour time-series data in a consistent manner for climate research; to develop product suites suitable for application across wide ranges of water types, including coastal water types; to study inter-sensor differences and minimize them before multi-sensor data are merged; to provide quality assurance and uncertainty characterization of products | Improved quality of ocean colour products, particularly in coastal waters and complex water types | Implement plan as accepted by CEOS agencies in 2009 | CEOS space agencies, in consultation with IOCCG and GEO | Improved algorithms for a range of water-property types | <missing> | Y | Ocean colour | maybe
Action O25: | Satellite-based phytoplankton biomass estimates | Establish a plan to improve and test regional algorithms to convert satellite observations to water-column integrated phytoplankton biomass through implementing an in situ phytoplankton monitoring programme. Estimates of uncertainty should be a standard output associated with improved algorithms. Wherever possible, a time series of phytoplankton should be collected simultaneously with the measurement of other important physical and biogeochemical variables. | Baseline information on plankton | Implementation build-up to 2020 | CEOS space agencies, in consultation with IOCCG, including Satellite PFT Intercomparison Project, parties’ national research agencies, working with SCOR and GOOS | Publication of internationally agreed plans; establishment of agreements/frameworks for coordination of a sustained global phytoplankton observing system with consistent sensors and a focused global program of in situ calibration implementation according to plan, flow of data into agreed archives, summary interpreted data products available as well as original data. | US$ 100 000–1 million | Y | Ocean Colour | ???
Action O26: | Expand Continuous Plankton Recorder and supporting observations | Establish plan for, and implement, global CPR surveys, including extension to (sub) tropical areas and integration of data from supporting observation programmes | Information on variability and trends in plankton | Internationally agreed plans published by end 2019; implementation build-up to 2024 | Parties’ national research agencies, working with SCOR and GOOS Biology and Ecoystems Panel, IGMETS, Global Alliance of CPR Surveys, OceanSITES | Publication of internationally agreed plans; establishment of agreements/frameworks for coordination of sustained global CPR surveys supported by repeated surveys at fixed locations; implementation according to plan; flow of data into agreed archives, summary of interpreted data products available | US$ 10–30 million | N
Action O27: | Strengthened network of coral reef observation sites | Strengthen the global network of long-term observation sites covering all major coral-reef habitats within interconnected regional hubs, encourage collection of physical, biogeochemical, biological and ecological measurements, following common and intercalibrated protocols and designs, and implement capacity-building workshops | Accurate global monitoring of changes in coral-reef cover, health and pressures | 2016–2020 | Parties’ national research and operational agencies, supported by GCRMN, GOOS Biology and Ecosystems Panel, GRAs and other partners | Reporting on implementation status of network | US$ 30–100 million | N
Action O28: | Global networks of observation sites for mangroves, seagrasses, macroalgae | Advance the establishment of global networks of long-term observation sites for seagrass beds, mangrove forests and macroalgal communities (including kelp forests) and encourage collection of physical, biogeochemical, biological and ecological measurements, following common and intercalibrated protocols and designs and implement capacity-building workshops | Accurate global monitoring of changes in mangroves, seaglasses and macroalgae cover | 2016–2020. | Parties’ national research and operational agencies, supported by GOOS Biology and Ecosystems Panel, GRAs and other partners in consultation with CBD and Ramsar Convention on Wetlands | Reporting on implementation status of network. | US$ 30–100 million | N
Action O29: | In situ data for satellite calibration and validation | Maintain in situ observations of surface ECV measurements from existing observations networks (including surface drifting buoys, SOOP ships, tropical moorings, reference moorings, Argo drifting floats, and research ships) for calibration and validation of satellite data; undertake a review of requirements of observations | Comprehensive in situ observations for calibration and validation of satellite data | Continuous, review by 2020 | Parties’ national services and ocean research programmes, through GOOS, IODE and JCOMM, in collaboration with WRCP/CLIVAR and CEOSS | Data availability at international data centres | US$ 1–10 million | Y | Ocean ECVs | Can we provide any feedback here on the ground-based networks used for calibration?
ActionA34:K34 O30: : | Satellite sea-surface temperature | Secure future passive microwave missions capable of SST measurements | Ensure SST coverage in regions of high cloud coverage | Continuous | Space agencies, coordinated through CEOS, CGMS, and WMO Space Programme in consultation with the Global High Resolution Sea Surface Temperature Project (GHRSST) | Agreement of plans for maintaining required microwave SST missions | US$ 100–300 million (for securing needed missions) | N | SST | Gap analysis
Action O31: | Satellite sea-surface height | Ensure continuous coverage from one higher-precision, medium-inclination altimeter and two medium-precision, higher-inclination altimeters, including a satellite altimetry reference mission with no gap between each satellite to ensure that each mission following another has a recovery period (6–9 months) to intercalibrate onean other (example of TOPEX/Poseidon and Jason missions) | Global routine calibrated mapping of SSH; intercalibration period between difference satellite missions | Continuous | Space agencies, with coordination through the OSTST, CEOS Constellation for Ocean Surface Topography, CGMS and the WMO Space Programme. | Satellites operating; provision of data to analysis centres | US$ 30–100 million | Y | Sea Level | ??? Information from OSCAR? (A bit far-fetched…, as this is specifically for the reference missions (TOPEX, Jason-1/2/3/CS)
Action O32: | Satellite sea-surface salinity | Ensure the continuity of space-based SSS measurements | Continue satellite SSS record to facilitate research (ocean circulation, climate variability, water cycle, and marine biogeochemistry), operation (seasonal climate forecast, short-term ocean forecast, ecological forecast) and linkages with the water cycle | Continuous | Space agencies, coordinated through OSSST, CEOS, CGMS and WMO Space Programme and in situ network | Agreement of plans for maintaining a CEOS virtual constellation for SSS, ongoing satellite operation, routine delivery of SSS products | US$ 30–100 million (for securing needed missions) | Y | SSS | Feedback from ECV Inventory contents
Action O33: | Satellite sea state | Continue to improve the delivery and quality of sea-state fields, based on satellite missions with in situ networks | Global routine calibrated mapping of sea state | Continuous | Space agencies, coordinated through CEOS, CGMS, and WMO Space Programme and in situ network | Agreement of plans for maintaining a CEOS virtual constellation for sea state | US$ 1–10 million (for generation of datasets) | Y | Sea State | Feedback from ECV Inventory contents
Action O34: | Satellite ocean surface stress | Continue to improve the delivery and quality of ocean-surface stress fields based on satellite missions with the comprehensive in situ networks (e.g. metocean moorings); improve resolution with the benefit of near coastal data; improved coverage of the diurnal and semi-diurnal cycles. | Global routine calibrated mapping of ocean-surface stress | Continuous | Space agencies, coordinated through OVSST, CEOS, CGMS and WMO Space Programme and in situ network | Agreement of plans for maintaining a CEOS virtual constellation for ocean-surface stress | <empty> | Y | Ocean Surface Stress | Feedback from ECV Inventory contents
Action O35: | Satellite sea ice | Ensure sustained satellite-based (microwave radiometry, SAR, altimetry, visible and IR) sea-ice products; high-inclination altimetry (e.g. Cryosat follow-on) also desired | Global, routine, calibrated mapping of sea ice | Continuous | Parties’ national services, research programmes and space agencies, coordinated through the WMO Space Programme and Global Cryosphere Watch, CGMS and CEOS; national services for in situ systems, coordinated through WCRP CliC and JCOMM | Sea-ice data in international data centres | US$ 1 -10 million (for generation of datasets) | Y | Sea Ice | Feedback from ECV Inventory contents
Action O36: | Satellite ocean colour | Support generation of long-term multi-sensor climate-quality OCR time series that are corrected for inter-sensor bias as needed and that have quantitative uncertainty characterization, with global coverage and validity, including coastal (Case-2) waters, and capable of dealing with user requirements for products at a variety of space and timescales. | Global routine calibrated mapping of ocean colour, including coastal (Case-2) regions | Implement plan beyond 2017 | CEOS space agencies, in consultation with IOCCG and GEO; agencies responsible for operational Earth observations, such as NOAA in the USA and Copernicus in the European Union | Free and open access to up-to-date, multi-sensor global products for climate research; flow of data into agreed archives | US$ 1–10 million (for generation of datasets) | Y | Ocean Colour | Feedback from ECV Inventory contents
Action O37: | Argo array | Sustain and expand the Argo profiling float network of at least one float every 3° x 3° in the ocean, including regional seas and the seasonal ice zone (approximately 3 800 floats) | Global climate-quality observations of the broadscale subsurface global ocean temperature and salinity down to 2 000 m | Continuous | Parties participating in the Argo programme and in cooperation with the JCOMM Observations Coordination Group | Spatial coverage and number of active floats | US$ 30 million | N
Action O38: | Development of a biogeochemical Argo array | Deploy a global array of 1 000 profiling floats (~6°x ~6°) equipped with pH, oxygen, nitrate, chlorophyll fluorescence, backscatter and downwelling irradiance sensors, consistent with the Biogeochemical Argo Science and Implementation Plan | Global observations of the broadscale subsurface global ocean biogeochemistry down to 2 000 m | In place by 2026; review progress in 2021 | Parties, in cooperation with the Argo Project and the JCOMM Observations Coordination Group | Number of floats reporting oxygen and biogeochemical variables | US$ 25 million | N
Action O39: | Development of a deep Argo array | Deploy a global array of approximately 1 230 deep Argo floats at 5° x 5° spacing, covering all ocean regions deeper than 2 000 m | Global climate-quality observations of the broad-scale subsurface global ocean temperature and salinity below 2 000 m | Array in place and maintained by 2026; review progress in 2021 | Parties participating in the Argo programme and in cooperation with the JCOMM Observations Coordination Group | Spatial coverage and number of active deep floats | US$ 20 million | N
Action O40: | GO-SHIP | Maintain a high-quality, full-depth, multi-disciplinary ship-based decadal survey of the global ocean (approximately 60 sections) and provide a platform to deploy autonomous components of the ocean-observing system and test new technology | Global, comprehensive, full-depth, decadal ocean inventory of ECVs | Continuous | National research programmes supported by the GO-SHIP project, JCOMM Ocean Coordination Group and GOOS | Percentage coverage of the sections and completion of Level-1 measurements | US$ 10–30 million | N
Action O41: | Develop fixed-point time series | Build and maintain a globally distributed network of multi-disciplinary, fixed-point surface and subsurface time series, using mooring, ship and other fixed instruments | Comprehensive high temporal resolution time series characterizing trends and variability in key ocean regimes | Continuous | Parties’ national services and ocean research agencies responding to the OceanSITES plan working with GOOS panels and GRAs | Moorings operational and reporting to archives | US$ 30–100 million | N
Action O42: | Maintain the Tropical Moored Buoy system | Maintain the Tropical Moored Buoy system | Contributes to observing state of the tropical ocean climate, particularly focused on coupled air–sea processes and high frequency variability and for prediction of ENSO events | Continuous | Parties’ national agencies, coordinated through the JCOMM Tropical Moored Buoy Implementation Panel, following guidance from scientific development projects (e.g. TPOS 2020, IIOE-II, AtlantOS) | Data acquisition at international data centres and robust design requirements articulated | US$ 30–100 million | N
Action O43: | Develop time-series-based biogeochemical data | Establish a coordinated network of ship-based multidisciplinary time series that is geographically representative; initiate a global data product of time-series-based biogeochemical data | Provision of comprehensive regular observations of ocean biogeochemistry, complementary to the GO-SHIP decadal survey | Internationally agreed plans published by end 2018; implementation build-up to 2020 | Parties’ national research agencies, working with IOCCP and user groups, such as IGMETS | Publication of internationally agreed plans; timely availability of data in internationally agreed on data centres | US$ 10–30 million | N
Action O44: | Meteorological moorings | Maintain measurements on surface moored buoys of meteorological parameters (air temperature, humidity, SST, wind speed and direction) and expand range of parameters measured (surface pressure, waves, precipitation and radiation); ensure observational metadata are available for all moored buoy observations, both for current data and for the historical archive | Comprehensive marine meteorological observation delivery | Continuous | Parties’ national services and ocean research agencies, DBCP, OceanSITES | Moorings operational and reporting to archives | US$ 30–100 million | N
Action O45: | Wave measurements on moorings | Develop a strategy and implement a wave measurement component as part of the Surface Reference Mooring Network (DBCP and OceanSITES) | Comprehensive in situ reference observations of wave parameters. | Complete plan and begin implementation by 2020 | Parties operating moorings, DBCP, OceanSITES, coordinated through the JCOMM Expert Team on Waves and Coastal Hazards | Sea-state measurement at the international data centres | US$ 1–10 million | N
Action O46: | Observations of sea ice from buoys and visual survey | Establish and sustain systematic in situ observations from sea-ice buoys, visual surveys (SOOP and Aircraft) and ULS in the Arctic and Antarctic | Enables tracking of variability in ice thickness and extent | Continuous | Arctic Party research agencies, supported by the Arctic Council; Party research agencies, supported by CLIVAR Southern Ocean Panel; JCOMM, working with CliC and OOPC | Establishment of agreements/frameworks for coordination of sustained Arctic and Southern Ocean observations, implementation according to plan | Plan and agreement of frameworks: US$ 100 000–1 million. Implementation: US$ 10–30 million | N
Action O47: | Sustain drifter array | Sustain global coverage of the drifting buoy array (at least 1 300 drifting buoys to cover oceans in the latitudes between 60S and 60N, excluding marginal seas, plus additional coverage for these areas) with ocean temperature sensors and atmospheric pressure sensors on all drifting buoys | Routine broad-scale observations of surface temperature and sea-level pressure in support of NWP; climate-data products (e.g. SST) and VOSClim for climate-quality flux estimates | Continuous | Parties’ national services and research programmes through JCOMM, DBCP and the Ship Observations Team (SOT) | Data submitted to analysis centres and archives | US$ 1–10 million | N
Action O48: | Underway observations from research and servicing vessels | Ensure where possible that ancillary underway observations are collected during research voyages and routine mooring servicing cruises | Improved coverage of underway observations, particularly in data-sparse, open oceans, and complementary to moored buoy arrays | Continuous. | National research agencies in consultation with the JCOMM Ship Observations Team and GO-SHIP | Improved observations from research vessels | US$ 1–10 million | N
Action O49: | Improve measurements from Voluntary Observing Ships | Improve the quality and spatial coverage of VOS observations, by working collaboratively with stakeholders having interests in the maritime transportation industry; continue efforts to validate utility of VOS observations for a range of applications, including NWP, marine climate, reanalysis and validation of remotely sensed observations. Improve metadata acquisition and management for as many VOS as possible through VOSClim, together with improved measurement systems | Improved coverage of routine marine meteorology observations in support of NWP | Continuous | National meteorological agencies and climate services, with commercial shipping companies in consultation with the JCOMM Ship Observations Team | Increased quantity and quality of VOS reports | US$1–10 million | N
Action O50: | Improve measurements of underway thermosalinograph data | Improve the quality and spatial coverage of underway temperature and salinity data; ensure observations are archived and quality-controlled when collected complementary to other observing programmes | Improved coverage of surface temperature and salinity observations | Continuous | National meteorological agencies and climate services, research agencies with the commercial shipping companies in consultation with the JCOMM Ship Observations Team | Increased quantity and quality of VOS reports | US$ 1–10 million | N
Action O51: | Sustain ship-of-opportunity expendable bathyghermograph/expendable conductivity temperature depth | Sustain the existing, multi-decadal, ship-of-opportunity XBT/XCTD transoceanic network in areas of significant scientific value | Eddy-resolving transects of major ocean basins, enabling basin-scale heat fluxes to be estimated and forming a global underpinning boundary- current observing system | Continuous | Parties' national agencies, coordinated through JCOMM-SOT | Data submitted to archive; percentage coverage of the sections | US$ 1–10 million | N
Action O52: | Coordination of underway pCO2 observations and agreed best practices | Improve coordination, outreach and tracking of implementation and measurements of a global surface water CO2 observing system; implement an internationally agreed strategy for measuring surface pCO2 on ships and autonomous platforms and improve coordination of network, timely data submission to the SOCAT data portal | Delivery of a high-quality global dataset of surface-ocean pCO2, enabling accurate estimates of ocean fluxes of carbon dioxide | Establishment of global monitoring group by 2018; continuous, coordinated network by 2020 | IOCCP in coordination with OOPC, JCOMM OCG and JCOMMOPS; implementation through Parties’ national services and research agencies | Tracking assets within 3 months of completion of voyage; data delivery to SOCAT. | US$ 10–30 million | N
Action O53: | Underway biogeochemistry observations | Sustain current trans-basin sampling lines of pCO2 and extend the coverage to priority areas by starting new lines (see GCOS-195, page 137); implement routine pCO2 measurements on research vessels; develop and deploy a global ship-based reference network of robust autonomous in situ instrumentation for Ocean biogeochemical ECVs | Enables routine observations of multiple surface Ocean biogeochemical ECVs, leading to improved coverage | Plan and implement a global network of SOOP vessels equipped with instrumentation by 2020 | Parties’ national ocean research agencies in association with the GOOS Biogeochemistry Panel, IOCCP, in consultation with JCOMM OCG. | Improved flow of data to SOCAT; pilot project implemented; progress towards global coverage with consistent measurements as determined by number of ships with calibrated sensors providing quality data | US$ 10–30 million | N
Action O54: | Continuous plankton recorder surveys | Implement, global CPR surveys | Towards global transects of surface zooplankton, plankton species diversity and variability, plus an indicator of phytoplankton productivity | 2026, review progress by 2021 | Parties’ national research agencies, through GACS and the GOOS Biology and Ecosystems Panel | Continuation and of sustained global CPR according to plan | US$ 10–30 million | N
Action O55: | Maintain tide gauges | Implement and maintain a set of gauges based on the GLOSS Core Network (approximately 300 tide gauges) with geocentrically located, high-accuracy gauges; ensure continuous acquisition, real-time exchange and archiving of high-frequency data; build a consistent time series, including historical sea-level records, with all regional and local tide-gauge measurements referenced to the same global geodetic reference system | The GLOSS Core Network is the backbone serving the multiple missions that GLOSS is called on to serve. Not all core stations serve every mission and not all stations for a given mission are part of the core. The Core Network serves to set standards and is intended to serve as the example for the development of regional networks. The GLOSS climate set serves to put the short altimetry record into a proper context, serves as the ground truth for the developing satellite dataset, and also provides continuity if climate capable altimetry missions have interruptions in the future. | Continuous. | Parties’ national agencies, coordinated through JCOMM-GLOSS of | Data availability at international data centres, global coverage, number of capacity-building projects | US$ 1–10 million | N
Action O56: | Developing a global glider observing system | Design and begin implementation of a globally distributed network of multi-disciplinary glider missions across the continental shelf seas to the open ocean as part of a glider reference coastal–open ocean observation network | Multi-disciplinary, high-frequency observations enabling the linkage of open ocean and coastal environments and cross-shelf exchange of properties | Framework and plan developed by 2020 | National research programmes coordinated by the global glider programme and GOOS | Published, internationally agreed plan and implementation of sustained coastal boundary–open ocean sections | US$ 10–30 million | N
Action O57: | Developing a global animal-tagging observing system | Move towards global coordinatinon of pinniped tagging for ecosystem and climate applications, including the coordination of deployment locations/species and QA/QC of resultant data | High-frequency T/S profile data in polar regions and in the ice zone, filling a critical gap in the observing system; high-frequency T/S profile data in other regions providing complementary data to other observing systems and likely high-frequency sampling of physical features of interest to foraging animals such as fronts and eddies | Framework and plan developed by 2020 | National research programmes coordinated through SOOS, SAEON GOOS | An internationally recognized coordination activity, and observing plan. | US$ 10–30 million | N

## Land
6 | LIST OF ACTIONS
6.4 | Terrestrial Domain Actions
# | Title | Action | Benefit | Time frame | Who | Performance indicator | Annual cost | Addressed in SARGIP 2017 | ECV | Comment
Action T1: | Improve coordination of terrestrial observations | Establish mechanism to coordinate terrestrial observations: this will be particularly important for climate change impacts and adaptation where local information will be critical and will not be provided through GCOS directly. It includes biodiversity and natural resources information and could also incorporate socio-economic components (e.g. health) so as to become fine-tuned with post-2015 frameworks. This would be based on discussions with stakeholders and could include a formal framework or regular meetings to exchange ideas and coordinate observational requirements. | Efficient observing systems with minimal duplication, delivering consistent and comparable data to a range of different users | 2017: Hold workshops to discuss way forward; 2019: Mechanism in place. | All involved in terrestrial observations. Initially TOPC, GEO, ICSU, GOFC-GOLD, FluxNet, NEON | Presence of active mechanism | US$ 100 000–1 million | Y
Action T2: | Develop joint plans for coastal zones | Jointly consider observations of coastal zones (including sea ice, mangroves and sea grass, river and groundwater flows, nutrients, etc.) to ensure the seamless coverage of ECVs and the global cycles in these areas | Consistent, accurate and complete monitoring of coastal zones | 2017: joint meetings; 2019: agreed plans | All involved in coastal observations. Initially TOPC, OOPC | Plan completed | US$ 1 000–10 000k | Y
Action T3: | Terrestrial monitoring sites | Review the need for establishing a public database of sites that aim to record climate-relevant data and their data. Consider the usefulness of establishing a set of GCOS terrestrial monitoring sites that aim to monitor at least one ECV according to the GCMP. | Improved access to monitoring and increased use of the data | One year for review | GCOS | Report on GCOS terrestrial monitoring sites | US$10 000–100 000 | Y
Action T4: | Review of monitoring guidance | Review existing monitoring standards/guidance/best practice for each ECV and maintain database of this guidance for terrestrial ECVs | Improved consistency and accuracy of results to meet user needs | Review: 2017–2018, maintain database as of 2019 | TOPC | Presence of maintained database | US$ 1 000 –10 000 | Y
Action T5: | Develop metadata | Provide guidance on metadata for terrestrial ECVs and encourage its use by data producers and data holdings | Provide users with a clear understanding of each dataset and the differences and applicability of different products for each ECV | 2018 | TOPC in association with appropriate data producers | Availability of metadata guidance | US$ 1 000 –10 000 | Y
Action T6: | Identify capacity development needs | Identify capacity-development needs to inform GCM and other capacity-building initiatives; identify specific improvements that could be supported by GCM | Improved monitoring in recipient countries | Ongoing | TOPC and GCM | Project proposals and Implemented projects | US$ 10 000–100 000 | Y
Action T7: | Exchange of hydrological data | In line with WMO Resolutions 25 (Cg-XIII) and 40 (Cg-XII), improve the exchange hydrological data and delivery to data centres of all networks encompassed by GTN-H, in particular the GCOS baseline networks, and facilitate the development of integrated hydrological products to demonstrate the value of these coordinated and sustained global hydrological networks. | Improved reporting filling large geographic gaps in datasets | Continuing; 2018 (demonstration products) | GTN-H partners in cooperation with WMO and GCOS | Number of datasets available in international data centres; number of available demonstration products | US$ 100 000–1 milion | N
Action T8: | Lakes and reservoirs: compare satellite and in situ observations | Assess accuracy of satellite water-level measurements by a comparative analysis of in situ and satellite observations for selected lakes and reservoirs | Improved accuracy | 2017–2020 | Legos/CNES, HYDROLARE | Improving accuracy of satellite water-level measurements | US$ 10 000–100 000 | Y | Lakes | We don't think we can do much here, as there is no data in #2
Action T9: | Submit historical and current monthly lake-level data | Continue submitting to HYDROLARE historical and current monthly lake-level data for GTN-L lakes and other lakes weekly/monthly water-temperature and ice-thickness data for GTN-L | Maintain data record | Continuous | National Hydrological Services through WMO CHy and other institutions and agencies providing and holding data | Completeness of database | US$ 100 000–1 million (40% in non-Annex-1 Parties) | N
Action T10: | Establish sustained production and improvement for the Lake ECV products | Establish satellite-based ECV data records for Lake-surface water temperature, Lake ice coverage and Lake water-leaving reflectance (Lake colour); Implement and sustain routine production of these new satellite based products; Sustain efforts on improving algorithms, processing chains and uncertainty assessments for these new ECV products, including systematic in situ data sharing and collection in support of ECV validation; Develop additional products derived from Lake water-leaving reflectance for turbidity, chlorophyll and coloured dissolved organic matter | Add additional Lake ECV products for extended data records; provide a more comprehensive assessment of climate variability and change in lake systems | Continuous. | Space agencies and CEOS, Copernicus Global Land Service, GloboLakes and ESA CCI | Completeness of database | 1–10M US$ (40% in non-Annex-1 Parties) | Y | Lakes | Feedback from ECV Inventory contents? Performance indicator is unclear.
Action T11: | Confirm Global Terrestrial Network for River Discharge sites | Confirm locations of GTN-R sites; determine operational status of gauges at all GTN-R sites; ensure that GRDC receives daily river discharge data from all priority reference sites within one year of observation (including measurement and data transmission technology used) | Up-to-date data for all areas | 2019 | National Hydrological Services, through WMO CHy in cooperation with TOPC, GCOS and GRDC | Reports (made In cooperation with GTN-H partners) to TOPC, GCOS and WMO CHy on the completeness of the GTN-R record held in GRDC, including the number of stations and nations submitting data to GRDC, National Communication to UNFCCC | US$ 1–10 million (60% in non-Annex I Parties) | N
Action T12: | National needs for river gauges | Assess national needs for river gauges in support of impact assessments and adaptation and consider the adequacy of those networks | Prepare for improvement proposals | 2019 | National Hydrological Services, in collaboration with WMO CHy and TOPC | National needs identified; options for implementation explored | US$ 10–30 million (80% in non-Annex I Parties) | N
Action T13: | Establish a full-scale Global Groundwater Monitoring Information System (GGMS) | Complete the establishment of a full-scale GGMS as a web portal for all GTN-GW datasets; continue existing observations and deliver readily available data and products to the information system | Global, consistent and verified datasets available to users | 2019 | IGRAC, in cooperation with GTN-H and TOPC | Reports to UNESCO IHP and WMO CHy on the completeness of the GTN-GW record held in GGMS, including the number of records in, and nations submitting data to, GGMS; web-based delivery of products to the community | US$ 1–10 million | N
Action T14: | Operational groundwater monitoring from gravity measurements | Develop an operational groundwater product, based on satellite observations | Global, consistent and verified datasets available to users | 2019 | Satellite agencies, CEOS, CGMS | Reports to UNESCO IHP and WMO CHy on the completeness of the GTN-GW record held in GGMS, including the number of records in, and nations submitting data to, GGMS; web-based delivery of products to the community. | US$ 1–10 million | Y | Groundwater | Feedback from ECV Inventory contents. Performance indicator is unclear.
Action T15: | Satellite soil-moisture data records | Regularly update individual microwave sensor (SMOS, SMAP, ASCAT, AMSR-E …) soil-moisture data records, including the subsidiary variables (freeze/thaw, surface inundation, vegetation optical depth, root-zone soil moisture) | Time series of data to identify trends over time | Continuing | Space agencies (ESA, EUMETSAT, NASA, NOAA, JAXA …) and Earth observation service providers | Availability of free and open global soil-moisture data records for individual microwave missions | US$ 10–30 million | Y | Soil Moisture | Feedback from ECV Inventory contents
Action T16: | Multi-satellite, soil-moisture data services | Regularly update of merged multi-sensor, soil-moisture data records, including the subsidiary variables (freeze/thaw, surface inundation, vegetation optical depth, root-zone soil moisture) | High-quality, soil moisture CDR for users | Continuing | Copernicus, NOAA, Earth observation data providers | Availability of free and open merged multi-sensor data records (merged passive, merged active and merged active-passive data) | US$ 1–10 million | Y | Soil Moisture | Feedback from ECV Inventory contents
Action T17: | International soil-moisture network | Operate, provide user services and expand the International Soil Moisture Network (ISMN), which is part of the GTN-H. | Coordinated in situ soil moisture data for users and calibration/validation | Continuing | Vienna Technical University, supported by national data providers, ESA, GEWEX, CEOS and GEO | Availability of harmonized and quality-controlled in situ soil-moisture data provided by network operators to ISMN | US$ 100 000–1 million (includes only central services of the ISMN data centre) | N
Action T18: | Regional high-resolution soil-moisture data record | Develop high-resolution soil-moisture data records for climate change adaptation and mitigation by exploiting microwave and thermal remote-sensing data | Availability of data suitable for adaptation | 2017–2020 | NASA Soil Moisture Active-Passive Programme, ESA Climate Change Initiative, Copernicus Evolution Activities in cooperation with identified universities and research organizations | Public releases of experimental multi-year (> 10 years) high-resolution, soil-moisture data records | US$ 10–30 million | Y | Soil Moisture | Feedback from ECV Inventory contents. Microwave and high resolution doesn't fit.
Action T19: | Maintain and extend the in situ mass balance network | Maintain and extend the in situ mass balance network, especially within developing countries and High Mountain Asia (Himalaya, Karakorum, Pamir) (e.g. using capacity-building and twinning programmes) | Maintain a critical climate record | Ongoing | Research community, national institutions and agencies | Number of observation series submitted to WGMS | US$ 100 000–1 million | N
Action T20: | Improve the funding situation for international glacier data centres | Improve the funding situation for international glacier data centres and services as well as for long-term glacier-monitoring programmes. Integrated and international availability of funding for sustaining programme, expecting also private sector contributions | Secure long-term monitoring and data availability | 2020 | National and international funding agencies | Resources dedicated to glacier-database management at WGMS and NSIDC; number of reference glaciers with more than 30 years of continued observations | US$ 1–10 million | N
Action T21: | Encourage and enforce research projects to make their ECV-relevant observations available through the dedicated international data centres | Encourage and enforce research projects to make their ECV-relevant observations available through the dedicated international data centres (e.g. through dedicated budget lines and the use of digital object identifiers for datasets). | Open and long-term availability of data for users | Ongoing | National funding agencies | Number of datasets submitted to dedicated international data centres | US$ 100 000–1 million | Y | Terrestrial ECVs | ??? Can we actually provide any feedback here, for space=based products? Not clear…
Action T22: | Global glacier inventory | Finalize the completion of a global reference inventory for glaciers and increase its data quality (e.g. outline, time stamp) and data richness (e.g. attribute fields, hypsometry) | Improved data quality on glaciers | 2020 | NSIDC and WGMS with GLIMS research community and space agencies | Data coverage in GLIMS database | US$ 100 000–1 million | Y
Action T23: | Multi-decadal glacier inventories | Continue to produce and compile repeat inventories at multi-decadal timescale | Extend the time series of glacier information | Ongoing | NSIDC and WGMS with GLIMS research community and space agencies. | Data coverage in GLIMS database | US$ 1–10 million | Y
Action T24: | Allocate additional resources to extend the geodetic dataset | Allocate additional resources to extend the geodetic dataset at national, regional and global levels: decadal elevation change can potentially be computed for thousands of glaciers from air- and spaceborne sensors | Improved accuracy of glacier change | Ongoing | WGMS with research community and space agencies | Data coverage in WGMS database | US$ 30–100 million | Y
Action T25: | Extend the glacier-front variation dataset both in space and in time | Extend the glacier-front variation dataset both in space and back in time, using remote-sensing, in situ observations and reconstruction methods | Understanding long-term trends in glacier extent (mass trends need additional information) | Ongoing | WGMS with research community and space agencies | Data coverage in WGMS database | US$ 10 000–100 000 | Y
Action T26: | Glacier observing sites | Maintain current glacier-observing sites and add additional sites and infrastructure in data-sparse regions, including South America, Africa, the Himalayas, the Karakoram and Pamir mountain ranges, and New Zealand; attribute quality levels to long-term mass-balance measurements; improve satellite-based glacier inventories in key areas | Sustained global monitoring to understand global trends | Continuing, new sites by 2017 | Parties’ national services and agencies coordinated by GTN-G partners, WGMS, GLIMS and NSIDC | Completeness of database held at NSIDC from WGMS and GLIMS | US$ 10–30 million | Y
Action T27: | Observations of glacier velocities | Encourage observations and reporting of glacier velocities | Improve understanding of glacier dynamics and mass loss | Starting 2017 | GTN-G partners, WGMS, GLIMS and NSIDC | Completeness of database held at NSIDC from WGMS and GLIMS | US$ 100 000–1 million | Y
Action T28: | Snow-cover and snowfall observing sites | Strengthen and maintain existing snow-cover and snowfall observing sites, provide clear and unambiguous instructons; ensure that sites exchange snow data internationally; establish global monitoring of those data over the GTS; and recover historical data; ensure reporting includes reports of zero cover. | Improved understanding of changes in global snow | Continuing; receipt of 90% of snow measurements at international data centres | NMHSs and research agencies, in cooperation with WMO-GCW and WCRP and with advice from TOPC, AOPC and tGTN-H | Data submission to national centres such as NSIDC and world data services | US$ 1–10 million | N
Action T29: | Integrated analyses of snow | Obtain integrated analyses of snow over both hemispheres | Improved understanding of changes in global snow | Continuous | Space and research agencies in cooperation with WMO-GCW and WCRP-CliC with advice from TOPC, AOPC and IACS | Availability of snow-cover products for both hemispheres | US$ 1–10 million | Y | Snow | Feedback from ECV Inventory contents?
Action T30: | Ice-sheet measurements | Ensure continuity of in situ ice-sheet measurements and field experiments for improved understanding of processes and for the better assessment of mass-loss changes | Robust data on trends in ice-sheet changes | Ongoing | Parties, working with WCRP-CliC, IACS and SCAR | Integrated assessment of ice sheet change supported by verifying observations. | US$ 10–30 million | N
Action T31: | Ice-sheet model improvement | Research into ice-sheet model improvement to assess future sea-level rise; improving knowledge and modelling of ice–ocean interaction, calving ice-mass discharge | Improved sea-level rise forecasting | International initiative to assess local and global sea-level rise and variability | WCRP-CliC sea-level cross-cut, IACS and SCAR | Reduction of sea-level rise uncertainty in future climate prediction from ice-sheet contributions | US$ 1–10 million (mainly by Annex-I Parties) | N
Action T32: | Continuity of laser, altimetry and gravity satellite missions | Ensure continuity of laser, altimetry and gravity satellite missions adequate to monitor ice masses over decadal timeframes | Sustain ice-sheet monitoring into the future | New sensors to be launched in 10-30 years | Space agencies, in cooperation with WCRP-CliC and TOPC | Appropriate follow-on missions agreed | US$ 30–100 million | Y | Ice-sheets and ice shelves | feedback from "planned" TCDRs + OSCAR?
Action T33: | Standards and practices for permafrost | Refine and implement international observing standards and practices for permafrost and combine with environmental variable measurements; establish national data centres | Consistent and comparable global observations | Complete by 2018 | Parties’ national services/research institutions and IPA | Implementation of guidelines and establishment of national centres | US$ 100 000–1 million | N
Action T34: | Mapping of seasonal soil freeze/thaw | Implement operational mapping of seasonal soil freeze/thaw through an international initiative for monitoring seasonally frozen ground in non-permafrost regions and active layer freeze/thaw in permafrost regions | Improved understanding of changes in biosphere and carbon cycle | Complete by 2020 | Parties, space agencies, national services and NSIDC, with guidance from IPA, the IGOS Cryosphere Theme team, and WMO-GCW | Number and quality of mapping products published. | US$ 1–10 million | N | Soil Moisture, Permafrost | Feedback from ECV Inventory contents?
Action T35: | Ensure the consistency of the various radiant energy fluxes | The the various radiant energy fluxes (e.g. surface albedo and FAPAR) derived from remote-sensing observation, and their compatibility with the specific requirements of the models, especially in the context of climate change studies; fire and surface albedo, especially in the context of climate change studies | Improved data leading to improved model predictions and understanding of changes in biosphere | 2020 | CEOS WG Cal/Val, TOPC observers, CEOS/CGMS WG Climate | Documented system to ensure consistency; reports demonstrating consistency | U US$ 100 000–1 million | Y | Albedo, FAPAR, Fire… | WGClimate is an actionee, but Action too broad and not specific.
Action T36: | Climate change indicators for adaptation | Establish climate change indicators for adaptation issues using land ECVs at high resolution | Inputs into adaptation planning, damage limitation and risk assessments | Initial products by 2018; ongoing development and improvement | GCOS, GCOS Science panels, WCRP, GFCS | Availability of indicators | US$ 100 000–1 million | N
Action T37: | Quality of ground-based reference sites for FAPAR and LAI | Improve the quality and number of ground-based reference sites for FAPAR and LAI; agree minimum measurement standards and protocols; conduct systematic and comprehensive evaluation of ground-based measurements for building a reference sites network | Ensure quality assurance of LAI and FAPAR products | Network operational by 2020 | Parties’ national and regional research centres, in cooperation with space agencies and Copernicus coordinated by CEOS WGCV, GCOS and TOPC | Data available | US$ 1–10 million | Y | FAPAR, LAI | Can we provide any feedback here, based on the information about ground-based networks used for calibration?
Action T38: | Improve snow and ice albedo products | Improve quality of snow (ice and sea ice) albedo products | Improve consistency of datasets | 2018 | Space agencies and Copernicus coordinated through CEOS WGCV LPV, WMO Space Pprogramme, with advice from GCOS and TOPC | Product available | US$ 100 000–1 million | Y | Snow, Ice Sheets and Ice Shelves, Sea-ice | Feedback from ECV Inventory contents?
Action T39: | Improve in situ albedo measurements | Improve quality of available in situ validation measurements and collocated albedo products, as well as BHR factors and measures of surface anisotropy from all space agencies generating such products; promote benchmarking activities to assess the reliability of albedo products | Improved calibration and validation | Full benchmarking/intercomparison by 2012 | BSRN and spatially representative FLUXNET sites, space agencies in cooperation with CEOS WGCV LPV | Data available to analysis centres | US$ 1–10 million | Y
Action T40: | Production of climate data records for LAI, FAPAR and Albedo | Operationalize the generation of: 10-day and monthly FAPAR and LAI products as gridded global products at 5 km spatial resolution over time periods as long as possible; 10-day FAPAR and LAI products at 50 m spatial resolution; Daily (for full characterization of rapidly greening and senescing vegetation, particularly over higher latitudes with the rapid changes due to snowfall and snowmelt), 10-day and monthly surface albedo products from a range of sensors using both archived and current Earth observation systems as gridded global products at 1 km to 5 km spatial resolution of over time periods as long as possible. | Provide longer time records for climate monitoring | 2020 | Space agencies, Copernicus and SCOPE-CM coordinated through CEOS WGCV LPV | Operational data providers accept the charge of generating, maintaining and distributing global physically consistent ECV products | US$ 100 000–1 million | Y | LAI, FAPAR, Albedo | Feedback from ECV Inventory contents
Action T41: | Evaluate LAI, FAPAR and Albedo | Promote benchmarking activities to assess reliability of FAPAR and LAI products, taking into account their intrinsic definition and accuracy assessment against fiducial ground references and evaluate the Albedo products with high-quality tower data from spatially representative sites | Improved accuracy of data | Evaluation by 2019 | Space agencies and Copernicus in relation with CEOS WGCV, GCOS/TOPC | Publish results. Recommendations after gap analysis on further actions for improving algorithms | US$ 10 000–100 000 | Y | LAI, FAPAR, Albedo | Gap Analysis results?
Action T42: | Land-surface temperature: in situ protocols | Promote standardized data protocols for in situ LST and support the CEOS-LPV group in development of a consistent approach to data validation, taking its LST Validation Protocol as a baseline | LST datasets will be more accessible to users, encouraging user uptake of more than one LST dataset. This will lead to better characterisation of uncertainties and inter-dataset variability. | Network concept and approach by 2017; implementation by 2018 | Parties’ national services and research agencies, space data providers, GOFC-GOLD, NASA LCLUC, TOPC, CEOS WGCV/LPV | Availability of protocols and evidence of their use. | US$ 1 000 –10 000 | Y
Action T43: | Production of land-surface temperature datasets | Continue the production of global LST datasets, ensuring consistency between products produced from different sensors and by different groups | Make available long time series of LST datasets in consistent formats, enabling more widespread use of LST for climate applications | Continual | Space agencies | Up-to-date production of global LST datasets | US$ 10 000 –100 000 | Y | LST | Feedback from ECV Inventory contents
Action T44: | Reprocessing land-surface temperature | Reprocess existing datasets of LST to generate a consistent long-term time series of global LST; in particular, reprocess archives of low Earth orbit and geostationary LST observations in a consistent manner and to community-agreed data formats | Make available long time series | Network concept and approach by 2017; implementation by 2018 | Parties’ national services and research agencies, space data providers, GOFC-GOLD, NASA LCLUC, TOPC, CEOS WGCV/LPV | Availability of long time series of LST datasets | US$ 100 000–1 million | Y | LST | Feedback from ECV Inventory contents
Action T45: | Land-surface temperature in situ network expansion | Expand the in situ network of permanent, high-quality IR radiometers for dedicated LST validation | LST datasets better validated and over more land-surface types; independent validation of stated accuracies providing credibility to satellite LST products | Network concept and approach by 2017; implementation by 2018 | Parties’ national services and research agencies, space data providers, GOFC-GOLD, NASA LCLUC, TOPC, CEOS WGCV/LPV, ILSTE | Establishment of a comprehensive network of ground sites with high-quality in situ measurements suitable for validating the different sensors; results from in situ radiometer intercomparison exercises | US$ 1–10 million (10-20 sites at US$ 100 000 per site) | Y
Action T46: | Land-surface temperature radiometric calibration | Radiometric calibration intercomparisons and uncertainties for LST sensors | LST datasets better calibrated and over all land-surface types for different satellite sensors; independent calibration providing credibility and traceability of data and uncertainties | Network concept and approach by 2017; implementation by 2018 | Coordinated by CEOS WGCV Infrared and Visible Optical Sensors subgroup/GSICS and supported by space agencies | ECV generators taking into account radiometric calibration uncertainties, ideally with calibrations being referenced to a common framework | US$ 1–10 million | Y | LST | ??? Here a feedback would only be possible after deep digging into documentation…
Action T47: | Land-cover experts | Maintain and strengthen a global network of land-cover/land-use experts to: develop and update an independent, very high spatial-resolution reference dataset for global land-cover map accuracy assessment;and facilitate access to land-use and management information to support the development of global-scale land-use products | For GLC map developers, GLC map users | Network concept and approach by 2017; implementation by 2018 | GOFC-GOLD, CEOS WGCV/LPV, Parties’ national services and research agencies, space data providers, NASA LCLUC, TOPC | Global LC map developers using the reference data developed by the operational network | US$ 100 000–1 million | Y
Action T48: | Annual land-cover products | Generate annual land-cover products over key regions that allow change assessment across time (including for the six IPCC AFOLU land categories) at 10 m–30 m spatial resolutions, according to internationally agreed standards and accompanied by statistical descriptions of their accuracy | For mitigation and adaptation communities | 2017 and beyond | Space agencies, GOFC-GOLD, Copernicus Land Service, USGS, University of Maryland (UMD)-GoogleEarth | Product delivered and used by a large community; use of standard approaches for validation and uncertainty metrics | US$ 1–10 million | Y | Land cover | Feedback from ECV Inventory contents?
Action T49: | Land-cover change | Generate global-scale land-cover products with an annual frequency and long-term records that allow change assessment across time (including as much as possible for the six IPCC AFOLU land categories), at resolutions between 250 m and 1 km, according to internationally agreed standards and accompanied by statistical descriptions of their accuracy | To climate change modellers, others | 2017 and beyond | Space agencies, research institutes, GOFC-GOLD, Copernicus Land Service | Product delivered and used; use of standard approaches for validation and uncertainty metrics | US$ 1–10 million | Y | Land cover | Feedback from ECV Inventory contents?
Action T50: | Land-cover community consensus | Develop a community consensus strategy and priorities for monitoring to include information on land management in current land-cover datasets and start collecting relevant datasets and observations, building on ongoing activities | To climate change modellers, mitigation and adaptation user communities | Concept and approach by 2017; start Implementation by 2018 | Parties’ national services and research agencies, space agencies, GOFC-GOLD, NASA LCLUC, TOPC, UMD-GoogleEarth, CEOS, ESA, USGS, GOFC-GOLD, FAO, GEO | Product delivered and used | US$ 100 000–1 million | Y
Action T51: | Deforestation | Develop yearly deforestation (forest clearing) and degradation (partial clearing) for key regions that allow change assessment across time at 10 m–30 m spatial resolutions, according to internationally agreed definitions. | To provide annual monitoring of deforestation and forest degradation to support management and reporting | Concept and approach by 2017; implementation by 2018 | Parties’ national services and research agencies, space agencies, GOFC-GOLD, NASA LCLUC, UMD-GoogleEarth, TOPC. | Indicators-based standard validation approach for change of forest cover and attributions associated with deforestation and degradation; product delivered and used | US$ 100 000–1 million | Y
Action T52: | Collaboration on above ground biomass | Encourage inter-agency collaboration on developing optimal methods to combine biomass estimates from current and upcoming missions (e.g. ESA BIOMASS, NASA GEDI and NASA-ISRO NiSAR, JAXA PALSAR, CONAE SAOCOM) | Reduced error, cross-validation, combining strengths of different sensors in different biomass ranges | Most key missions are expected to be in orbit between 2016 and 2020 | ESA, NASA, JAXA, NASA-ISRO, CONAE | A strategy to combine biomass estimates from different sensors, together with algorithms and processing methods | US$ 100 000–1 million | Y | AGB | Feedback from ECV Inventory contents?
Action T53: | Above-ground biomass validation strategies | Encourage inter-agency collaboration to develop validation strategies for upcoming missions aimed at measuring biomass (e.g. ESA BIOMASS, NASA GEDI and NASA-ISRO NiSAR), to include combined use of in situ and airborne lidar biomass measurements | Potential to produce more comprehensive validation of biomass estimates by cost-sharing. Greater consistency between biomass estimates from different sensors because of assessment against common reference data | From now until the operational phase of the various sensors (2016–2022). | ESA, NASA, JAXA, NASA-ISRO, CONAE | Formal agreement between agencies on a strategy for joint gathering and sharing of validation data, together with funding of specific elements of the overall set of validation data | US$ 10 000–100 000 | Y
Action T54: | Above-ground biomass validation sites | Develop a set of validation sites covering the major forest types, especially in the tropics, at which high-quality biomass estimations can be made, using standard protocols developed from ground measurements or airborne lidar techniques | Essential to give confidence in satellite-derived biomass estimates at global scale | From now up to the operational phase of the various sensors (2018–2022) | Space agencies working with key in situ networks (e.g. RainFor, Afritron, the Smithsonian Center for Tropical Forest Science), GEO-GFOI | Establishment of a comprehensive network of ground sites with high-quality, in situ biomass estimates with uncertainty assessments suitable for validating the different sensors | US$ 30–100 million (50 tropical sites covering all forest types: US$ 20 million); estimate for temperate and boreal sites not yet formulated | Y
Action T55: | Above-ground biomass data access | Promote access to well-calibrated and validated regional- and national-scale biomass maps that are increasingly being produced from airborne lidar. | Greatly extends the representativeness of data available for validating satellite-derived biomass data, since a much greater range of land types and forest conditions will be covered | From now until the operational phase of the various sensors (2016–2022) | GEO-GFOI, other national and international bodies producing biomass maps | Availability of multiple regional- to country-scale maps of biomass derived from airborne lidar; use of standard protocols for uncertainty assessment of lidar estimation of biomass | US$ 10 000–100 000 (does not include monitoring costs) | Y
Action T56: | Above-ground biomass: forest inventories | Improve access to high-quality forest inventories, especially in the tropics, including those developed for research purposes and REDD+ | Extends the data available for validating satellite-derived biomass data | From now until the operational phase of the various sensors (2016–2022) | GEO-GFOI, other national and international bodies producing or funding forest inventories | Access to databases of georeferenced biomass measurements derived from ground measurements for forest-inventory purposes | US$ 10 000–100 000 | Y
Action T57: | Soil carbon: carbon mapping | Cooperate with the soil-carbon mapping exercises to advocate accurate maps of soil carbon | Improved data accuracy | Ongoing | TOPC and GCOS | Improved maps | US$1 000–10 000 | N
Action T58: | Soil-carbon change | Encourage flux sites to measure soil carbon at five-year intervals and record soil-management activities; use this to supplement long-term experiments that are monitoring soil carbon. | Improved in situ observations will improve accuracy. | Ongoing | TOPC and GCOS | Number of flux sites making measurements | US$10 000–100 000 | N
Action T59: | Soil carbon – histosols | Provide global maps of the extent of histosols (peatlands, wetlands and permafrost) and their depth | Improve understanding of carbon pools at risk from climate change | Ongoing | Research communities, ISRIC, HWSD and the Global Soil Map | Availability of maps | US$ 10 000–100 000 | N | Land cover? | ??? Not sure!...
Action T60: | Historic fire data | Reanalyse the historical fire-disturbance satellite data (1982 to present) | Climate-modelling communities | By 2020 | Space agencies, working with research groups coordinated by GOFC-GOLD-Fire By 2020 | Establishment of a consistent dataset, including the globally available AVHRR data record | US$ 1–10 million | Y | Fire | Feedback from ECV Inventory contents
Action T61: | Operational global burned area and fire radiative power | Continue the production of operational, global burned area active fire (with associated FRP) products, with metadata and uncertainty characterizations that meet threshold requirements and have necessary product back-up to ensure operational delivery of products to users. | Climate-modelling communities, space agencies, civil protection services, fire managers, other users | Continuous | Space agencies, Copernicus Global Land Service, Copernicus Atmospheric Monitoring Service, GOFC-GOLD | Availability of products that meet user needs | US$ 1–10 million | Y | Fire | Feedback from ECV Inventory contents
Action T62: | Fire maps | Consistently map global burned area at < 100m resolution on a near-daily basis from combinations of satellite products (Sentinel-2, Landsat, Sentinel-1, PROBA); work towards deriving consistent measures of fire severity, fire type, fuel moisture and related plant-fuel parameters | Climate-modelling communities , space agencies, civil protection services, fire managers, other users | By 2020 | Space agencies, research organizations, international organizations in collaboration with GOFC-GOLD-Fire | Availability of data and products | US$ 1–10 million | Y | Fire | Feedback from ECV Inventory contents?
Action T63: | Fire validation | Continuation of validation activity around the detection of fire-disturbed areas from satellites to show that threshold requirements are being met; work to reduce the errors of commission and omission; provide better than existing uncertainty characterization of fire-disturbance products. | Climate-modelling communities. | Continuous | Space agencies and research organizations, supported by CEOS LPV | Publication of temporal accuracy | US$ 1–10 million | Y | Fire | Feedback from ECV Inventory contents? Far-fetched…
Action T64: | Fire disturbance model development | Continuation of joint projects between research groups involved in the development of atmospheric transport models, dynamic vegetation models and GHG emission models, tthe climate-modelling and transport-modelling community and those involved in the continual algorithm development, validation and uncertainty characterization of fire-disturbance products from satellite data (the Earth observation and modelling community); contribute to better understanding of fire risk and fire-risk modelling | Climate-modelling communities, Copernicus Programme | Continuous | Space agencies (NASA, ESA, etc.), inter-agency bodies (GOFC-GOLD, CEOS, ECMWF, Meteosat, etc.), Copernicus Global Land Service, Copernicus Atmospheric Monitoring Service, GOFC-GOLD | Projects that engage climate and atmospheric transport modellers and product-development community | US$ 1–10 million | Y
Action T65: | Anthropogenic water use | Collect, archive and disseminate information related to anthropogenic water use | Accurate and up-to-date data on water availability and stress | Continuous | UN-Water, IWMI and FAO through AQUASTAT in collaboration with UN Statistics Division and other data sources | Information contained in the AQUASTAT database. | US$ 100 000–1 million | N
Action T66: | Pilot projects: anthropogenic water use | Develop and implement pilot data-collection exercises for water use | Demonstrate data-collection approaches for wide implementation | 2016–2019 | GTN-H, UN-Water, IWMI and FAO through AQUASTAT in collaboration with the Convention on the Protection and Use of Transboundary Watercourses and International Lakes | Completed data collection in pilot areas | US$ 100 000–1 million | N
Action T67: | Improve global estimates of anthropogenic greenhouse-gas emissions | Continue to produce annual global estimates of emissions from fossil fuel, industry, agriculture and waste; improve these estimates by following IPCC methods using Tier 2 for significant sectors; this will require a global knowledge of fuel carbon contents and a consideration of the accuracy of the statistics used | Improved tracking of global anthropogenic emissions | Ongoing, with annual updates | IEA, FAO, Global Carbon Project (GCP), Carbon Dioxide Information Analysis Centre (CDIAC), Emissions Database for Global Atmospheric Research (EDGAR) | Availability of Improved estimates. | US$ 10 000–100 000 | N
Action T68: | Use of satellites for Land use, land-use change and forestry emissions/removals | Support the improvement of estimates of emissions and removals from Forestry and Land-use change by using satellite data to monitor changes where ground-based data are insufficient. | Improved global and national monitoring of LULUCF | Ongoing. | National reporting supported by international agencies through programmes such as UNREDD and GFOI | Availability of satellite data | US$ 100 000–1 million | Y | Land cover | Feedback from ECV Inventory contents? Far-fetched…
Action T69: | Research on the land sink | Research to better understand the land sink, its processes and magnitudes | Better understanding of the global carbon cycle | Ongoing | GCP, research groups | Published results | US$ 100 000–1 million | N
Action T70: | Use of Inverse modelling techniques to support emission inventories | Develop inverse modelling methods to support and add credibility to emission inventories; develop and disseminate examples for several GHGs | Added credibility of national emission/removal estimates and demonstration of inventory completeness | Ongoing | National Inventory agencies, researchers | Published results | US$ 1–10 million | N
Action T71: | Prepare for a carbon-monitoring system | Preparatory work to develop a carbon monitoring system to be operational by 2035; Development development of comprehensive monitoring systems of measurements of atmospheric concentrations and of emission fluxes from anthropogenic area and point sources to include space-based monitoring, in situ flask and flux tower measurements and the necessary transport and assimilation models | Improved estimates of national emissions and removals | Initial demonstration results by 2023 – complete systems unlikely before 2030 | Space agencies | Published results | US$ 10–100 billion | Y | GHG | Related to the GHG Monitoring activities
Action T72: | Prepare for a latent and sensible heat flux ECV | Review the feasibility of global monitoring of latent and sensible heat fluxes form the land surface; prepare proposals for such an ECV. Development of comprehensive monitoring systems of measurements of atmospheric concentrations and emission fluxes from anthropogenic point sources, to include space-based monitoring, in situ flask and flux tower measurements and the necessary transport and assimilation models. | Improve understanding of heat fluxes over land | 2017 | TOPC | Proposals for consideration by GCOS Steering Committee | US$10 000–100 000 | N